## SAP Timeline
APM - SAP Activity & Support Plan ¦ SAP Timeline (Weekly)
SAP schedule view for SAP-only stakeholders - read-only: dates/status LINK from the 'APM Plan & FTE' tab (edit them there, this view updates automatically) ¦ orange header + gray band = current week; red block = Go-Live week ¦ AS OF 27 AUG 2026 - SAP Go-Live 1 Jul 2027
Phase: | A | B | C | D | E |  | No required info
[8 empty] | Feb | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan 27 |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
# | Key Activities & Scope | Status | SAP Start | SAP End | Dur (d) | Mock Readiness | Remark | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01 | 2027-11-08 | 2027-11-15 | 2027-11-22 | 2027-11-29 | 2027-12-06 | 2027-12-13 | 2027-12-20 | 2027-12-27
A.Impact Analysis — impact assessment and mapping
1 | Risk, action, issue tracking | In progress | 2026-04-01 | 2027-09-30 | 548 |  | + Monitor all project life cycle
B.Testing Support — for Accenture (ACN) and End Users
2 | CIT | In progress | 2026-09-23 | 2026-09-28 | 6 |  | + Depending on cr, currently approved and done cr 15 Sep 2026 ¦ PM-I-109 (APM - SAP) under JIRA SHANA-168749
3 | SIT (mc1) | Not started | 2026-10-01 | 2026-12-20 | 81 |  | + Waiting for confirmation date from SHANA + Waiting for revised test case from SHANA + Depending on CIT and ACN fixed FD look like
4 | UAT (mc2) | Not started | 2027-01-04 | 2027-03-15 | 71 |  | + Wait for confirmation date from SHANA
5 | Business Simulation (mc3) | Not started | 2027-03-20 | 2027-04-30 | 42 |  | + Wait for confirmation date from SHANA
C.Mock Validation — align with S/4HANA by switch source appoach
6 | Mock 1 Execution (SIT) | Completed | 2026-04-01 | 2026-06-30 | 91 | 2026-05-01 | + Already validated and done
7 | Mock 2 Execution (UAT) | Not started | 2026-04-01 | 2026-11-30 | 244 | 2026-09-21 | + Post load to GCP 21 Sep 2026 + Required another 2 weeks (10 working days) for GCP team to prepares data
8 | Mock 3 Execution/FDR | Not started | 2026-12-01 | 2027-03-31 | 121 | TBC | + Wait for confirmation date from SHANA
D.Cutover & Go-Live — prep and alignment with end users
9 | Ramp Down (ACO) | Not started | 2027-05-03 | 2027-06-25 | 54
10 | Blackout Period: Deploy APM to Production (DB, BE, FE) | Not started | 2027-06-26 | 2027-06-30 | 5 |  | + SAP Go-Live, 1 Jul 2027
11 | Ramp Up | Not started | 2027-07-01 | 2027-07-31 | 31 |  | + After Go-Live
E.Training & Post Go-Live — hypercare support & monitoring
12 | Hypercare support operations & incident management | Not started | TBC | 0 |  |  | + Plan: Jul–Sep 2027 (PGLS phase)
SAP Go-Live (Milestone) |  |  | 2027-07-01
Notes:
1. READ-ONLY SAP schedule view. Dates, status and the Go-Live date are linked formulas from the 'APM Plan & FTE' tab - edit them there, this view updates automatically.
2. One row per activity = the SAP window (phase color). APM's own dates and FTE planning live on the 'APM Plan & FTE' tab.
3. Many dates are TBC - waiting for confirmation from SHANA (SIT, UAT, Business Sim, Mock 3, Ramp Down, Blackout, Ramp Up, Hypercare).
4. Orange header + gray band = current week; red block = SAP Go-Live week (1 Jul 2027).

## APM Plan & FTE
APM - SAP Activity & Support Plan ¦ Gantt (Weekly) + FTE Tracking
Two stacked bars per activity: phase color = SAP window (SAP Start/End D:E); blue = APM's own window (APM Start/End F:G; red TBC = not confirmed yet) ¦ Edit dates/Status/FTE here - bars, Dur and FTE shading update automatically ¦ FTE grid below: role rows x weeks, values inside each activity's APM window ¦ orange header + gray band = current week; red block = Go-Live week ¦ AS OF 27 AUG 2026 - SAP Go-Live 1 Jul 2027
Phase: | A | B | C | D | E |  |  | APM own window (cols F-G)
[10 empty] | Feb | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan 27 |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
# | Key Activities & Scope | Status | SAP Start | SAP End | APM Start | APM End | Dur (d) | Mock Readiness | Remark | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01 | 2027-11-08 | 2027-11-15 | 2027-11-22 | 2027-11-29 | 2027-12-06 | 2027-12-13 | 2027-12-20 | 2027-12-27
A.Impact Analysis — impact assessment and mapping
1 | Risk, action, issue tracking | In progress | 2026-04-01 | 2027-09-30 |  |  | 548 |  | + Monitor all project life cycle
[5 empty] | 2026-04-01 | 2027-09-30
B.Testing Support — for Accenture (ACN) and End Users
2 | CIT | In progress | 2026-09-23 | 2026-09-28 |  |  | 6 |  | + Depending on cr, currently approved and done cr 15 Sep 2026 ¦ PM-I-109 (APM - SAP) under JIRA SHANA-168749
[5 empty] | 2026-09-23 | 2026-09-28
3 | SIT (mc1) | Not started | 2026-10-01 | 2026-12-20 |  |  | 81 |  | + Waiting for confirmation date from SHANA + Waiting for revised test case from SHANA + Depending on CIT and ACN fixed FD look like
TBC
4 | UAT (mc2) | Not started | 2027-01-04 | 2027-03-15 |  |  | 71 |  | + Wait for confirmation date from SHANA
TBC
5 | Business Simulation (mc3) | Not started | 2027-03-20 | 2027-04-30 |  |  | 42 |  | + Wait for confirmation date from SHANA
TBC
C.Mock Validation — align with S/4HANA by switch source appoach
6 | Mock 1 Execution (SIT) | Completed | 2026-04-01 | 2026-06-30 |  |  | 91 | 2026-05-01 | + Already validated and done
TBC
7 | Mock 2 Execution (UAT) | Not started | 2026-04-01 | 2026-11-30 |  |  | 244 | 2026-09-21 | + Post load to GCP 21 Sep 2026 + Required another 2 weeks (10 working days) for GCP team to prepares data
[5 empty] | 2026-10-09 | 2026-10-09
8 | Mock 3 Execution/FDR | Not started | 2026-12-01 | 2027-03-31 |  |  | 121 | TBC | + Wait for confirmation date from SHANA
TBC
D.Cutover & Go-Live — prep and alignment with end users
9 | Ramp Down (ACO) | Not started | 2027-05-03 | 2027-06-25 |  |  | 54
TBC
10 | Blackout Period: Deploy APM to Production (DB, BE, FE) | Not started | 2027-06-26 | 2027-06-30 |  |  | 5 |  | + SAP Go-Live, 1 Jul 2027
TBC
11 | Ramp Up | Not started | 2027-07-01 | 2027-07-31 |  |  | 31 |  | + After Go-Live
TBC
E.Training & Post Go-Live — hypercare support & monitoring
12 | Hypercare support operations & incident management | Not started | TBC | [5 empty] | + Plan: Jul–Sep 2027 (PGLS phase)
TBC
SAP Go-Live (Milestone) |  |  | 2027-07-01
FTE TRACKING - monthly FTE by position (Feb'26 to Dec'27)
1.0 = one person for the full month. One row per person (position repeated per person). Values are MOCK SAMPLES - type over them. The 'Total FTE' row auto-sums each month.
| Position | [8 empty] | Feb'26 | Mar'26 |  |  |  |  | Apr'26 |  |  |  | May'26 |  |  |  | Jun'26 |  |  |  |  | Jul'26 |  |  |  | Aug'26 |  |  |  |  | Sep'26 |  |  |  | Oct'26 |  |  |  | Nov'26 |  |  |  |  | Dec'26 |  |  |  | Jan'27 |  |  |  | Feb'27 |  |  |  | Mar'27 |  |  |  |  | Apr'27 |  |  |  | May'27 |  |  |  |  | Jun'27 |  |  |  | Jul'27 |  |  |  | Aug'27 |  |  |  |  | Sep'27 |  |  |  | Oct'27 |  |  |  | Nov'27 |  |  |  |  | Dec'27
| ITPM | [8 empty] | 0 | 0 |  |  |  |  | 0.2 |  |  |  | 0.1 |  |  |  | 0.11 |  |  |  |  | 0.11 |  |  |  | 0.1 |  |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.1 |  |  |  | 0.11 |  |  |  |  | 0.11 |  |  |  | 0.1 |  |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  |  | 0.2 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Scrum Master | [8 empty] | 0 | 0 |  |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  | 0.4 |  |  |  |  | 0.4 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| BA | [8 empty] | 0 | 0 |  |  |  |  | 0.95 |  |  |  | 0.95 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.95 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0.95 |  |  |  | 0.95 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.95 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| UX/UI Designer | [8 empty] | 0 | 0 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Frontend Developer | [8 empty] | 0 | 0 |  |  |  |  | 0.85 |  |  |  | 0.9 |  |  |  | 0.9 |  |  |  |  | 0.85 |  |  |  | 0.9 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0.85 |  |  |  | 0.9 |  |  |  | 0.9 |  |  |  |  | 0.85 |  |  |  | 0.9 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Frontend Developer | [8 empty] | 0 | 0 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Frontend Developer | [8 empty] | 0 | 0 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Backend Developer | [8 empty] | 0 | 0 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Backend Developer | [8 empty] | 0 | 0 |  |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  | 0.9 |  |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  |  | 0.65 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  | 0.9 |  |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  |  | 0.65 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| QA | [8 empty] | 0 | 0 |  |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  | 0.9 |  |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  |  | 0.8 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  | 0.9 |  |  |  |  | 0.75 |  |  |  | 0.9 |  |  |  |  | 0.8 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| QA | [8 empty] | 0 | 0 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| QA Automation | [8 empty] | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Data Analytics Services | [8 empty] | 0 | 0 |  |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  |  | 0.2 |  |  |  | 0.1 |  |  |  |  | 0.1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  |  | 0.2 |  |  |  | 0.1 |  |  |  |  | 0.1 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Data Scientist | [8 empty] | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
| Total FTE (all positions) | [8 empty] | 0 | 0 |  |  |  |  | 9.1 |  |  |  | 9.35 |  |  |  | 8.91 |  |  |  |  | 8.56 |  |  |  | 9.25 |  |  |  |  | 8.15 |  |  |  | 7.6 |  |  |  | 7.6 |  |  |  |  | 7.6 |  |  |  | 9.1 |  |  |  | 9.35 |  |  |  | 8.91 |  |  |  |  | 8.56 |  |  |  | 9.25 |  |  |  |  | 8.15 |  |  |  | 7.6 |  |  |  | 7.6 |  |  |  |  | 7.6 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Notes:
1. Each activity has TWO stacked bars: phase color = SAP window (SAP Start/End D:E); blue = APM's own window (APM Start/End F:G). Red 'TBC' = not confirmed yet - the blue bar appears once real dates are typed.
2. FTE grid below: position x month, one row per person (mock samples - type over them). 1.0 = one person for the full month. The 'Total FTE (all positions)' row auto-sums each month; monthly columns match the Gantt month bands (Feb'26 - Dec'27).
3. C. Mock Validation uses the switch-source approach; APM needs 5-10 extra days after post-load (GCP team prepares legacy data).
4. Many dates are TBC - waiting for confirmation from SHANA (SIT, UAT, Business Sim, Mock 3, Ramp Down, Blackout, Ramp Up, Hypercare).
5. Bars are conditional formatting; Dur (d) and FTE Total are formulas - all update automatically. Go-Live date is editable in its milestone row.
6. Status has a dropdown; SAP/APM date columns open a date picker.
7. 'Mock Readiness' (col I): readiness dates for Mock 1-3 (from source col E); grey hatch = not required.
8. APM dates seeded from source col F: #1 mirrors the SAP lifecycle; CIT and Mock 2 (9-Oct-26) parsed; every unconfirmed row is left as TBC - edit freely.
9. 'SAP Timeline' tab is a read-only linked view for stakeholders who only need the SAP schedule - edit nothing there.
10. Re-run build_gantt.py to regenerate from the source plan; previous versions are backed up automatically.