## Resource Plan
Project Information
Project Name : |  | S1 AI Advisory |  |  |  | Project Manager Name : |  |  | Parinya Kamnoed
Project ID : |  | <Project ID> |  |  |  | Initiative Lead (IL) Name :
Project Start Date : |  | 2026-01-05 |  |  |  | Digital Line Partner Name :
Project End Date : |  | 2026-12-30 |  |  |  | Product / Platform Owner Name : |  |  | Thapanic Khukhantin
Resource Plan
No. | Role | Ranking | Level | Area | Tentative Member Name | Assignment Start Date | Assignment End Date | Assignment (% per month) | Remark
Project Resource Plan

## Maintain List
Role | Ranking | Area
Analyst | Assistant Officer | Application
Back End | Officer | Data
Business Analyst | Senior Officer | AI
Data Analyst | Manager
Data and Enterprise Architect
Data Architecture & Engineering
Data Engineering
Data Management Support
Data Scientist
Devops
Enterprise Solution
Enterprise Solution & App Dev
Front End
Machine Learning Engineer
Quality Assurance
Senior Devops
Software Developer
UX/UI
Scrum Master

## FTE Plan - revise (bk1) (hidden)
As of 20 Feb 2026 | FTE Assessment - As of 20 Feb 2026
ITPM Validation | Project group | Group | Vendor | Position | Level | Member | Nickname | Project/Note | Reviewer | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26
| Production Asset |  |  | IT Project Manager | Senior | Parinya Kamnoed | Chaii | S1 AI Advisory | Navapol M. |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Production Asset |  |  | Data Architect |  | Pongsakorn Lekpojai | Bank | S1 AI Advisory |  |  |  | 0.2 | 0.2
| Production Asset |  |  | Data Science |  | Wiriya Thienthanukit | Mickey | S1 AI Advisory |  |  |  | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Production Asset |  |  | Data Science |  | Kantkanit Watanakun | Punn | S1 AI Advisory |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Production Asset |  |  | ML Engineer |  | Siwa Boonpunmongkol | Jui | S1 AI Advisory |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Production Asset |  |  | Data Analyst |  | Cholnisa Bhonprasit | Bom+ | S1 AI Advisory |  |  |  | 0.1 | 0.1 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
|  |  |  | IT Infrastructure |  | Pool Resource |  | S1 AI Advisory
|  |  |  | IT Cyber Security |  | Pool Resource |  | S1 AI Advisory
[10 empty] | 0.1 | 0.4 | 1.5 | 1.5 | 1.2 | 1.25 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05
Original - need to revised with team

## FTE Plan - revise (bk2) (hidden)
FTE Assessment - As of 17 Apr 2026 (after team estimation)
Project | Business Domain | Position | Name | Nickname | Nick Name | Vendor | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | Jun'26 | Jul'26 | Aug'26 | Sep'26 | Oct'26 | Nov'26 | Dec'26
S1 AI advisory flowline back pressure optimization | Production | ITPM | Parinya Kamnoed | Chaii | Chaii | EPAM | 0 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Wiriya Thienthanukit | Micky | Mickey | PTTEP | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Ami Toyoda | Meen | Meen | The Gang | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | TBC | #N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | ไม่ต้องแล้ว
S1 AI advisory flowline back pressure optimization | Production | Data Engineer | TBC | #N/A |  |  | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Data Architect | Pongsakorn Lekpojai | Bank | Bank | PTTEP | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Machine Learning Engineer | Siwa Boonpunmongkol | Jui | Jui | PTTEP | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.20
S1 AI advisory flowline back pressure optimization | Production | Data Analytics Services | Cholnisa Bhonprasit | Bom+ | Bom+ | PTTEP | 0 | 0 | 0.1 | 0.1 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
[7 empty] | 0 | 0.3 | 3.2 | 3.2 | 2.9 | 1.95 | 1.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.7

## Q&A
No. | Question | Alignment
1 | batch / ingest / frequency per day/month? | + never ingest, Direct retrieve (2025) ¦ GCP (2026), check iPOS phase 1 for data + PI to GCP need to validate more discus PI Server + no need to build model for DS + frequency followint data flow diagram + output -> text file (sharepoint): need human approve -> well test team load to P2 (ipos connect P2)
2 | data from PI real time or not ? | + PI on Prem to PI GCP + check data pipeline from existing iPOS 1/2, concern Name - summary separate project + data engineer - > use data analyst instead + adding Tag require K.Kate (Suwanna product owner PI) - contact by DS ¦ Pre-requitsite: tag name and more details
3 | clarify DE start before DS? | + don't need DE effort
4 | end of dec 2026, the project is still continue? | + plan to complete 120 well Oct, actuallly total 150-160 end Dec ->> KPI
5 | which selection Well for group1 and group2 deployment? | + POC 10 well aready + month 6 = 25 well, + month 10 = 120 well (26-120 well faster)
6 | ML pipeline | Only keep file on SharePoint check by human
7 | System Architecture and Data Architecture | Revised again after Gate 3, before Solar
8 | Resource DA | Just standby follow FTE sheet, mainly DS (Mickey) is the key person togather Requirement

## FTE Plan - revise
FTE Assessment - As of 17 Apr 2026 (after team estimation)
Project | Business Domain | Position | Name | Nickname | Nick Name | Vendor | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | Jun'26 | Jul'26 | Aug'26 | Sep'26 | Oct'26 | Nov'26 | Dec'26
S1 AI advisory flowline back pressure optimization | Production | ITPM | Parinya Kamnoed | Chaii | Chaii | EPAM | 0 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Wiriya Thienthanukit | Micky | Mickey | PTTEP | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Ami Toyoda | Meen | Meen | The Gang | 0 | 0 | 1 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | TBC | #N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | ไม่ต้องแล้ว
S1 AI advisory flowline back pressure optimization | Production | Data Engineer | TBC | #N/A |  |  | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Data Architect | Pongsakorn Lekpojai | Bank | Bank | PTTEP | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Machine Learning Engineer | Siwa Boonpunmongkol | Jui | Jui | PTTEP | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.20
S1 AI advisory flowline back pressure optimization | Production | Data Analytics Services | Cholnisa Bhonprasit | Bom+ | Bom+ | PTTEP | 0 | 0 | 0.1 | 0.1 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
[7 empty] | 0 | 0.1 | 3.2 | 3.2 | 2.4 | 1.45 | 1.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.7

## FTE Plan - revise(bk 20260417) (hidden)
FTE Assessment - As of 06 Mar 2026
Project | Business Domain | Position | Name | Nickname | Nick Name | Vendor | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | Jun'26 | Jul'26 | Aug'26 | Sep'26 | Oct'26 | Nov'26 | Dec'26
S1 AI advisory flowline back pressure optimization | Production | ITPM | Parinya Kamnoed | Chaii | Chaii | EPAM | 0 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Wiriya Thienthanukit | Micky | Mickey | PTTEP | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Ami Toyoda | Meen | Meen | The Gang | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | TBC | #N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
S1 AI advisory flowline back pressure optimization | Production | Data Engineer | TBC | #N/A |  |  | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Data Architect | Pongsakorn Lekpojai | Bank | Bank | PTTEP | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Machine Learning Engineer | Siwa Boonpunmongkol | Jui | Jui | PTTEP | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.20
S1 AI advisory flowline back pressure optimization | Production | Data Analytics Services | Cholnisa Bhonprasit | Bom+ | Bom+ | PTTEP | 0 | 0 | 0.1 | 0.1 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
[7 empty] | 0 | 0.3 | 3.2 | 3.2 | 2.9 | 1.95 | 1.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.7

## Project Plan (bk1) (hidden)
Actual | x % | Start: | 2026-01-01 |  | Start | 2026-01-05
Plan | x % | End: | 2026-12-01 |  | ...In Progress... |  |  | Link: | SOR Document
Year 2026
[5 empty] | 2026-01-15 |  |  |  | 2026-02-23 |  |  |  | 2026-03-30 |  |  |  |  | 2026-04-27 |  |  |  | 2026-05-25 |  |  |  | 2026-06-29 |  |  |  |  | 2026-07-27 |  |  |  | 2026-08-31 |  |  |  |  | 2026-09-28 |  |  |  | 2026-10-26 |  |  |  | 2026-11-30 |  |  |  |  | 2026-12-28
Project Roadmap/Timeline: [TBC with Team and Line Partner] | time axis 2026-01-05 to 2026-12-28
Main Activity | Sub Activity | Duration | Role | % Progress | time axis 2026-01-05 to 2026-12-28
Gather Requirement & Design |  | 1 months | DA(main), DArch | bar: 2026-02-16 to 2026-03-09
Consolidate Requirement (data requirement, KPI, etc.) | bar: 2026-02-16 to 2026-03-09
Design architecture | bar: 2026-02-16 to 2026-02-23
SOLAR + ARB | bar: 2026-03-02 to 2026-03-09
[Full scale] Data preparation |  | 3 months | DE(main), DA | bar: 2026-01-05 to 2026-03-30
Prepare data, sharing and permission | bar: 2026-01-05 to 2026-03-30
[Full scale] ML model development |  | 10 months | DS, ML | bar: 2026-03-02 to 2026-12-28
Model development | bar: 2026-03-02 to 2026-05-25
ML inference/prediction pipeline development | bar: 2026-03-02 to 2026-05-25
Deployment Group 1 | bar: 2026-06-01 to 2026-07-27
User feedback/improvement Group 1 | bar: 2026-08-03 to 2026-08-10
Deployment Group 2 | bar: 2026-10-19 to 2026-12-14
User feedback/improvement Group 2 | bar: 2026-12-21 to 2026-12-28
UAT & Model adoption to input IPOS |  | 4 months | DA, DS, ML | bar: 2026-06-01 to 2026-12-28
Technical Integration: API (GCP to IPOS) | bar: 2026-06-01 to 2026-12-14
Verification: Results vs. hub separators | bar: 2026-12-14 to 2026-12-21
Go-Live | bar: 2026-12-21 to 2026-12-28
Handover: Final manuals and training | bar: 2026-12-28
Post-golive |  | Start at lease 3 months | TBC
Advisory Ops: Real-time ON/OFF recommendations
Maintenance: Automated retraining loops
Cyclic Optimization
|  |  | milestone | ♦️ | 2026-01-05: Note:
Note: |  |  |  |  | 2026-01-05: Holiday Note; 2026-02-02: Risk/Issue; 2026-02-23: Deliverable.; 2026-03-23: Question:; 2026-04-20: Repository
04/02/26 - SOR Highlivel Requirement latest alignment |  |  |  |  | 2026-01-05: 1; 2026-01-12: xxx; 2026-02-23: 1 xxxx; 2026-03-23: end goal???
[5 empty] | 1 | xxx | [5 empty] | 2 trouble shoot
Original - need to revise with team |  |  |  |  | 2026-01-05: 3; 2026-01-12: xxx
[5 empty] | 4 | xxx

## FTE Plan - revise (3) 20260424) (hidden)
FTE Assessment - As of 17 Apr 2026 (after team estimation)
Project | Business Domain | Position | Name | Nickname | Nick Name | Vendor | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | Jun'26 | Jul'26 | Aug'26 | Sep'26 | Oct'26 | Nov'26 | Dec'26
S1 AI advisory flowline back pressure optimization | Production | ITPM | Parinya Kamnoed | Chaii | Chaii | EPAM | 0 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Wiriya Thienthanukit | Micky | Mickey | PTTEP | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | Ami Toyoda | Meen | Meen | The Gang | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
S1 AI advisory flowline back pressure optimization | Production | Data Scientist | TBC | #N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | ไม่ต้องแล้ว
S1 AI advisory flowline back pressure optimization | Production | Data Engineer | TBC | #N/A |  |  | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Data Architect | Pongsakorn Lekpojai | Bank | Bank | PTTEP | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 AI advisory flowline back pressure optimization | Production | Machine Learning Engineer | Siwa Boonpunmongkol | Jui | Jui | PTTEP | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.20
S1 AI advisory flowline back pressure optimization | Production | Data Analytics Services | Cholnisa Bhonprasit | Bom+ | Bom+ | PTTEP | 0 | 0 | 0.1 | 0.1 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
[7 empty] | 0 | 0.1 | 3.2 | 3.2 | 2.9 | 1.95 | 1.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.7

## Project Plan
Actual | 62.89% |  |  |  |  | Start: | 2026-03-02 | Start | 2026-01-05 |  |  | Current Week | [5 empty] | Revised | [40 empty] | ♦️[25 Dec] Handover
Plan | 55.8% |  |  |  |  | End: | 2026-12-27 |  |  |  | Link: | SOR Document | [20 empty] | ♦️[30 Jun] Group 1: 25 Wells | [16 empty] | ♦️[30 Oct] Group 2: 26 - 120 Wells | [6 empty] | ♦️[14 Dec] Group 3: 121 - 160 Wells
*count progress to handover | [7 empty] | Year 2026 | [51 empty] | Year 2027
[8 empty] | 2026-01-15 |  |  |  | 2026-02-23 |  |  |  | 2026-03-30 |  |  |  |  | 2026-04-27 |  |  |  | 2026-05-25 |  |  |  | 2026-06-29 |  |  |  |  | 2026-07-27 |  |  |  | 2026-08-31 |  |  |  |  | 2026-09-28 |  |  |  | 2026-10-26 |  |  |  | 2026-11-30 |  |  |  |  | 2026-12-28 |  |  |  | 2027-01-25 |  |  |  | 2027-02-22 |  |  |  | 2027-03-22
Project Roadmap/Timeline: |  |  |  | 4 | time axis 2026-01-05 to 2027-03-22
Main Activity | Sub Activity | Start | End 1 (for calculation) | End | Duration | % Progress | Role | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Gather Requirement & Design |  |  |  |  | 2 months |  | DS(main), DArch | bar: 2026-02-16 to 2026-04-06
| Consolidate Requirement (data requirement, KPI, etc.) | 2026-02-16 | 2026-03-09 | 2026-03-13 | 20 | 100% | bar: 2026-02-16 to 2026-03-09
| Design architecture | 2026-03-16 | 2026-04-23 | 2026-04-27 | 10 | 100% | bar: 2026-03-16 to 2026-04-06
| SOLAR + ARB | 2026-03-30 | 2026-04-06 | 2026-04-10 | 10 | 100% | bar: 2026-03-30 to 2026-04-06
[Full scale] ML model development |  |  |  |  | 10 months |  | DS, ML | bar: 2026-03-02 to 2026-12-28
| Prepare data, sharing and permission | 2026-03-02 | 2026-05-25 | 2026-05-29 | 65 | 100% | bar: 2026-03-02 to 2026-05-25
| Model Development & Prediction Pipeline | 2026-03-02 | 2026-05-25 | 2026-05-29 | 65 | 100%
| Deployment Group 1 (1-25 Wells) | 2026-06-01 | 2026-06-29 | 2026-07-03 | 25 | 100% | bar: 2026-06-01 to 2026-06-29
| User feedback/improvement Group 1 | 2026-07-06 | 2026-07-27 | 2026-07-31 | 15 | 100% | bar: 2026-07-06 to 2026-07-20
| Model Adjustment | 2026-07-27 | 2026-09-28 | 2026-10-02 | 50 | 100% | bar: 2026-07-27 to 2026-09-28
| Deployment Group 2 (26-120 Wells) | 2026-10-05 | 2026-10-26 | 2026-10-30 | 20 | 70% | bar: 2026-10-05 to 2026-10-26
| User feedback/improvement Group 2 | 2026-11-02 | 2026-11-16 | 2026-11-20 | 15 | 60% | bar: 2026-11-02 to 2026-11-16
| Deployment The Rest Group (121-160 Wells) | 2026-11-23 | 2026-12-14 | 2026-12-18 | 20 | 0% | bar: 2026-11-23 to 2026-12-14
| User feedback/improvement The Rest Group | 2026-12-21 | 2026-12-28 | 2027-01-01 | 10 | 0% | bar: 2026-12-21 to 2026-12-28
Integration and Handover |  |  |  |  | 3 months |  | DA, DS, ML | bar: 2026-06-01 to 2026-08-10; 2026-12-21 to 2026-12-28
| IPOS Phase 2: Integration Support | 2026-06-01 | 2026-08-10 | 2026-08-14 | 55 | 0% | bar: 2026-06-01 to 2026-08-10
| Handover: Final manuals and training | 2026-12-21 | 2026-12-28 | 2027-01-01 | 10 | 0% | bar: 2026-12-21 to 2026-12-28
Post-golive TBC with support team |  |  |  |  | 3 months |  | OMS Support, DS | bar: 2027-01-04 to 2027-03-22
| Operation Support (Tier 1, Tier 2) | 2026-01-04 | 2026-03-21 | 2026-03-25 | 60 | 0%
[6 empty] | Measurement |  | 2026-01-05: Deliverable(Overall); 2026-02-09: Ref. Task Document & Handover; 2026-04-06: Post Go-Live
[6 empty] | Target: MAPE < 25% |  | 2026-01-05: ML; 2026-01-12: Source of data and model development; 2026-04-06: Tier; 2026-04-13: Document; 2026-05-18: Support Level
[8 empty] | DS | Algorithm & Logic, Result (experiment/measurement e.g. MAPE, R2, MAE) | [11 empty] | Tier 1 | High Level |  |  |  |  | High Level
[8 empty] | *format document/wiki | [12 empty] | Tier 2 | Technical Level |  |  |  |  | Technical Level
Integration with IPOS Phase 2
[8 empty] | Team | Action |  |  |  | Output
[8 empty] | S1 AI | deploy models |  |  |  | text files on sharepoint
[8 empty] | User | validate and upload data |  |  |  | PDMS, GCP
[8 empty] | IPOS | integrate |  |  |  | GCP
Deliverable: Milestone 1 - 25 Wells
[8 empty] | 1) | Source code deployment
[8 empty] | 2) | Excel Virtual Flow Meeting (per Well per Day)
Deliverable: Milestone 2 - 26 to 120 Wells
[8 empty] | 1) | Source code deployment
[8 empty] | 2) | Excel Virtual Flow Meeting (per Well per Day)
Deliverable: Milestone 3 - 121 to 160 Wells (TBD)
[8 empty] | 1) | Source code deployment
[8 empty] | 2) | Excel Virtual Flow Meeting (per Well per Day)
Note: the user is required to test each milestone [Testing->Improvement Process]
Note:
04/02/26 - SOR Highlivel Requirement latest alignment
Original - need to revise with team
Note: will be deleted soon
output, excel and sharepoint -> validate -> P2 -> GCP
[10 empty] | text on sharepoint |  |  | S1 Team
[10 empty] | validate -> P2 |  |  | user
[10 empty] | GCP |  |  | IPOS phase 2
[10 empty] | post golive |  |  |  | document
[11 empty] | 1 | support |  | slide(ml: resource), (ds: algorith)
[11 empty] | 2 | ds | [7 empty] | more technical
deliverable
slide(ml: resource), (ds: algorith, wiki model exeriment)
[11 empty] | ds | algo, logic
result (KPI R2, Mape, model performance)
Formulas:
End = Table1[[#This Row],[End 1 (for calculation)]]+E5

## Project Plan (2) (hidden)
Actual | 22.5% | Start: | 2026-03-02 |  | Start | 2026-01-05 |  |  | Current Week | [5 empty] | Revised | [40 empty] | ♦️[25 Dec] Handover
Plan | 54.67% | End: | 2026-12-27 |  |  |  |  | Link: | SOR Document | [20 empty] | ♦️[30 Jun] Group 1: 25 Wells | [16 empty] | ♦️[30 Oct] Group 2: 26 - 120 Wells | [6 empty] | ♦️[14 Dec] Group 3: 121 - 160 Wells
[5 empty] | Year 2026 | [51 empty] | Year 2027
[5 empty] | 2026-01-15 |  |  |  | 2026-02-23 |  |  |  | 2026-03-30 |  |  |  |  | 2026-04-27 |  |  |  | 2026-05-25 |  |  |  | 2026-06-29 |  |  |  |  | 2026-07-27 |  |  |  | 2026-08-31 |  |  |  |  | 2026-09-28 |  |  |  | 2026-10-26 |  |  |  | 2026-11-30 |  |  |  |  | 2026-12-28 |  |  |  | 2027-01-25 |  |  |  | 2027-02-22 |  |  |  | 2027-03-22
Project Roadmap/Timeline: As of 20 Feb 2026 | time axis 2026-01-05 to 2027-03-22
Main Activity | Sub Activity | Duration | Role | % Progress | time axis 2026-01-05 to 2027-03-22
Gather Requirement & Design |  | 2 months | DS(main), DArch | bar: 2026-02-16 to 2026-04-06
| Consolidate Requirement (data requirement, KPI, etc.) |  |  | 90% | bar: 2026-02-16 to 2026-03-09
| Design architecture |  |  | 100% | bar: 2026-03-16 to 2026-04-06
| SOLAR + ARB |  |  | 80% | bar: 2026-03-30 to 2026-04-06
[Full scale] ML model development |  | 10 months | DS, ML | bar: 2026-03-02 to 2026-12-28
| Prepare data, sharing and permission |  |  | 45% | bar: 2026-03-02 to 2026-05-25
| Model development 1 |  |  | 45% | bar: 2026-03-02 to 2026-05-25
| ML inference/prediction pipeline development |  |  | 0% | bar: 2026-03-02 to 2026-05-25
| Deployment Group 1 (1-25 Wells) |  |  | 0% | bar: 2026-06-01 to 2026-06-29
| User feedback/improvement Group 1 |  |  | 0% | bar: 2026-07-06 to 2026-07-20
| Model Adjustment |  |  | 0% | bar: 2026-07-27 to 2026-09-28
| Deployment Group 2 (26-120 Wells) |  |  | 0% | bar: 2026-10-05 to 2026-10-26
| User feedback/improvement Group 2 |  |  | 0% | bar: 2026-11-02 to 2026-11-16
| Deployment The Rest Group (121-160 Wells) |  |  | 0% | bar: 2026-11-23 to 2026-12-14
| User feedback/improvement The Rest Group |  |  | 0% | bar: 2026-12-21 to 2026-12-28
Integration and Handover |  | 3 months | DA, DS, ML | bar: 2026-06-01 to 2026-08-10; 2026-12-21 to 2026-12-28
| IPOS Phase 2: Integration Support |  |  | 0% | bar: 2026-06-01 to 2026-08-10
| Handover: Final manuals and training |  |  | 0% | bar: 2026-12-21 to 2026-12-28
Post-golive TBC with support team |  | 3 months | OMS Support, DS | bar: 2027-01-04 to 2027-03-22
| Operation Support (Tier 1, Tier 2) |  |  | 0%
Note:
04/02/26 - SOR Highlivel Requirement latest alignment
Original - need to revise with team
[9 empty] | Deliverable as of 06 Mar 2026 | [17 empty] | Post Go-Live
[9 empty] | ML | Source of data and model development | [16 empty] | Tier | Document |  |  |  |  | Support Level
[9 empty] | DS | Algorithm & Logic, Result (experiment/measurement e.g. MAPE, R2, MAE) | [16 empty] | Tier 1 | High Level |  |  |  |  | High Level
[9 empty] | *format document/wiki | [17 empty] | Tier 2 | Technical Level |  |  |  |  | Technical Level
Integration with IPOS Phase 2
[9 empty] | Team | Action |  |  |  | Output
[9 empty] | S1 AI | deploy models |  |  |  | text files on sharepoint
[9 empty] | User | validate and upload data |  |  |  | PDMS, GCP
[9 empty] | IPOS | integrate |  |  |  | GCP
Note: will be deleted soon
output, excel and sharepoint -> validate -> P2 -> GCP
[7 empty] | text on sharepoint |  |  | S1 Team
[7 empty] | validate -> P2 |  |  | user
[7 empty] | GCP |  |  | IPOS phase 2
[7 empty] | post golive |  |  |  | document
[8 empty] | 1 | support |  | slide(ml: resource), (ds: algorith)
[8 empty] | 2 | ds | [7 empty] | more technical
deliverable
slide(ml: resource), (ds: algorith, wiki model exeriment)
[8 empty] | ds | algo, logic
result (KPI R2, Mape, model performance)

## Project Plan (BK2) (hidden)
Actual | 43.74% | WIP Revise %Actual |  |  |  | Start: | 2026-03-02 | Start | 2026-01-05 |  |  | Current Week | [5 empty] | Revised | [40 empty] | ♦️[25 Dec] Handover
Plan | 55.8% |  |  |  |  | End: | 2026-12-27 |  |  |  | Link: | SOR Document | [20 empty] | ♦️[30 Jun] Group 1: 25 Wells | [16 empty] | ♦️[30 Oct] Group 2: 26 - 120 Wells | [6 empty] | ♦️[14 Dec] Group 3: 121 - 160 Wells
*count progress to handover | [7 empty] | Year 2026 | [51 empty] | Year 2027
[8 empty] | 2026-01-15 |  |  |  | 2026-02-23 |  |  |  | 2026-03-30 |  |  |  |  | 2026-04-27 |  |  |  | 2026-05-25 |  |  |  | 2026-06-29 |  |  |  |  | 2026-07-27 |  |  |  | 2026-08-31 |  |  |  |  | 2026-09-28 |  |  |  | 2026-10-26 |  |  |  | 2026-11-30 |  |  |  |  | 2026-12-28 |  |  |  | 2027-01-25 |  |  |  | 2027-02-22 |  |  |  | 2027-03-22
Project Roadmap/Timeline: As of 20 Feb 2026 |  |  |  | 4 | time axis 2026-01-05 to 2027-03-22
Main Activity | Sub Activity | Start | End 1 (for calculation) | End | Duration | % Progress | Role | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Gather Requirement & Design |  |  |  |  | 2 months |  | DS(main), DArch | bar: 2026-02-16 to 2026-04-06
| Consolidate Requirement (data requirement, KPI, etc.) | 2026-02-16 | 2026-03-09 | 2026-03-13 | 20 | 100% | bar: 2026-02-16 to 2026-03-09
| Design architecture | 2026-03-16 | 2026-04-23 | 2026-04-27 | 10 | 100% | bar: 2026-03-16 to 2026-04-06
| SOLAR + ARB | 2026-03-30 | 2026-04-06 | 2026-04-10 | 10 | 100% | bar: 2026-03-30 to 2026-04-06
[Full scale] ML model development |  |  |  |  | 10 months |  | DS, ML | bar: 2026-03-02 to 2026-12-28
| Prepare data, sharing and permission | 2026-03-02 | 2026-05-25 | 2026-05-29 | 65 | 95% | bar: 2026-03-02 to 2026-05-25
| Model development 1 | 2026-03-02 | 2026-05-25 | 2026-05-29 | 65 | 95%
| ML inference/prediction pipeline development | 2026-03-02 | 2026-05-25 | 2026-05-29 | 65 | 95%
| Deployment Group 1 (1-25 Wells) | 2026-06-01 | 2026-06-29 | 2026-07-03 | 25 | 0% | bar: 2026-06-01 to 2026-06-29
| User feedback/improvement Group 1 | 2026-07-06 | 2026-07-27 | 2026-07-31 | 15 | 0% | bar: 2026-07-06 to 2026-07-20
| Model Adjustment | 2026-07-27 | 2026-09-28 | 2026-10-02 | 50 | 0% | bar: 2026-07-27 to 2026-09-28
| Deployment Group 2 (26-120 Wells) | 2026-10-05 | 2026-10-26 | 2026-10-30 | 20 | 0% | bar: 2026-10-05 to 2026-10-26
| User feedback/improvement Group 2 | 2026-11-02 | 2026-11-16 | 2026-11-20 | 15 | 0% | bar: 2026-11-02 to 2026-11-16
| Deployment The Rest Group (121-160 Wells) | 2026-11-23 | 2026-12-14 | 2026-12-18 | 20 | 0% | bar: 2026-11-23 to 2026-12-14
| User feedback/improvement The Rest Group | 2026-12-21 | 2026-12-28 | 2027-01-01 | 10 | 0% | bar: 2026-12-21 to 2026-12-28
Integration and Handover |  |  |  |  | 3 months |  | DA, DS, ML | bar: 2026-06-01 to 2026-08-10; 2026-12-21 to 2026-12-28
| IPOS Phase 2: Integration Support | 2026-06-01 | 2026-08-10 | 2026-08-14 | 55 | 0% | bar: 2026-06-01 to 2026-08-10
| Handover: Final manuals and training | 2026-12-21 | 2026-12-28 | 2027-01-01 | 10 | 0% | bar: 2026-12-21 to 2026-12-28
Post-golive TBC with support team |  |  |  |  | 3 months |  | OMS Support, DS | bar: 2027-01-04 to 2027-03-22
| Operation Support (Tier 1, Tier 2) | 2026-01-04 | 2026-03-21 | 2026-03-25 | 60 | 0%
[8 empty] | Deliverable(Overall) |  |  |  |  | Ref. Task Document & Handover | [7 empty] | Post Go-Live
[8 empty] | ML | Source of data and model development | [11 empty] | Tier | Document |  |  |  |  | Support Level
[8 empty] | DS | Algorithm & Logic, Result (experiment/measurement e.g. MAPE, R2, MAE) | [11 empty] | Tier 1 | High Level |  |  |  |  | High Level
[8 empty] | *format document/wiki | [12 empty] | Tier 2 | Technical Level |  |  |  |  | Technical Level
Integration with IPOS Phase 2
[8 empty] | Team | Action |  |  |  | Output
[8 empty] | S1 AI | deploy models |  |  |  | text files on sharepoint
[8 empty] | User | validate and upload data |  |  |  | PDMS, GCP
[8 empty] | IPOS | integrate |  |  |  | GCP
Deliverable: Milestone 1 - 25 Wells
[8 empty] | 1) | Source code deployment
[8 empty] | 2) | Excel Virtual Flow Meeting (per Well per Day)
Deliverable: Milestone 2 - 26 to 120 Wells
[8 empty] | 1) | Source code deployment
[8 empty] | 2) | Excel Virtual Flow Meeting (per Well per Day)
Deliverable: Milestone 3 - 121 to 160 Wells (TBD)
[8 empty] | 1) | Source code deployment
[8 empty] | 2) | Excel Virtual Flow Meeting (per Well per Day)
Note: the user is required to test each milestone [Testing->Improvement Process]
Note:
04/02/26 - SOR Highlivel Requirement latest alignment
Original - need to revise with team
Note: will be deleted soon
output, excel and sharepoint -> validate -> P2 -> GCP
[10 empty] | text on sharepoint |  |  | S1 Team
[10 empty] | validate -> P2 |  |  | user
[10 empty] | GCP |  |  | IPOS phase 2
[10 empty] | post golive |  |  |  | document
[11 empty] | 1 | support |  | slide(ml: resource), (ds: algorith)
[11 empty] | 2 | ds | [7 empty] | more technical
deliverable
slide(ml: resource), (ds: algorith, wiki model exeriment)
[11 empty] | ds | algo, logic
result (KPI R2, Mape, model performance)
Formulas:
End = Table15[[#This Row],[End 1 (for calculation)]]+E5

## Risk Issue
Id | Issue | Type | Status | Priority | Create Date | Target Date | PIC (raise topic) | Note (dd/mm/yy) | Dropdown: | Type | Priority | Status
1 | Set budget for upcoming wells in the future | issue | pending | low | 2026-04-24 |  | Naruedon T. | 24/04/26: + Ground work and structure already set in 2026, just add data source. Team will discuss again |  | issue | high | open
2 | Initial MAPE measurement should be less than 25% (ref. SOR) | issue | open | low | 2026-05-20 | 2026-05-27 | Chain S. | 20/05/26: + Wait for development team readiness assessment for the next weekly sync up again |  | risk | medium | in progress
3 | [Note] S1 AI model development data will not affect with iPOS project as iPOS retrieves data from GCP, and already use Well test data | issue | close | low | 2026-05-20 | 2026-05-20 | Naruedon T., Parinya K. | 20/05/26: + Wait for development team readiness assessment for next weekly sync up again |  | risk | medium | pending
4 | Validate model and accuracy on MAPE measurement | issue | open | medium | 2026-05-27 |  | Chain S. Witaya T. |  |  |  |  | close
5 | PDMS align format (enhance K.Kae acknowledge - to register) | issue | open | medium | 2026-05-27 | 2026-09-30 | Naruedon T. | 10/06/26: + Already discussed with involved person, and extend tentative target date to end of Jul 26 18/06/26: + User waiting for uploading files -> Map usage Cell to P2 (PDMS) -> back to Development team.
6 | Revised and combine tasks; Model development 1 and ML inference/prediction pipeline development to "Model Development & Prediction Pipeline" | issue | close | medium | 2026-05-27 | 2026-06-08 | Parinya K.
7 | Wait for discussion After Testing and Estimate on 5 well and good Oil Flow: ○ Address Outliers: values are "jumping" significantly far from reality; we need to investigate the data cleansing logic for these instances. ○ Well Behavior Logic: We need to define which wells should decline OR sustained strength ○ Zero-Value Investigation: Some estimates are currently returning as "0"; we need to verify if this is a sensor data issue or a model logic error. Mechanism Focus on Beam Pumps: ○ Status Filtering: For training, focus on active/open status for Gas-lift wells to ensure the models aren't being skewed by "closed" well data. "BSW" Factor Integration: ○ Reporting: include BSW factors are included in the final SharePoint Well Test reports. | issue | close | high | 2026-06-10 | 2026-06-26 | Nareudon T. Witaya T. | 10/06/26: + Wait for discussion 18/06/26: + BSW will be fixed after fixing model. + Based on P2:PI Tag data, retrieving history of well test data n-1 day (n=well test date), then wait and see the result. 24/06/26: + already train n-1 then run new model and compare with old model -> MAPE still high on production + quick solution: putting assumption by well behaviror (exploring)
8 | Milestone: Well 1-25th - verify and align deliverables with team | Issue | open | low | 2026-06-18 | TBC | Parinya K.
9 | Model Logic Improve and Feedback Loop to meet MAPE < 25% | Issue | open | low | 2026-07-01 | TBC | Team | 1/07/26: On solution discussion 1) Request PTTD upload history PI data 2) PFO2/O working on explore VFM, and sending sample data for S1 AI team to try (K.Chain) -- align with team again
10 | Confirm well th 121-160 | Issue | open | low | 2026-08-04 | TBC | Parinya K. | 05/08/26: 1) focus and finalize well 1-120 before discussion the rest of well
11 | Finding more approachs by talking to Weatherford | Issue | open | high | 2026-08-05 | TBC | Naruedon T. | 05/08/26: 1) wait for a session with Weatherford to analysis the approach for S1 AI project