## Table of Contents
EP APM S/4HANA Integration WBS Master Template
Document Control & Metadata
Project Name | PTTEP S/4HANA Implementation (SHANA)
Application Name | EP APM (Asset Performance Management)
Version | v3.0 (Mock column & Gantt Chart integrated)
Target Go-Live Date | July 1, 2027
Primary Contact | ITPM APM Workstream
Generated Date | August 2026
Formatting Legend
Input Cell | User-editable fields (dates, duration, status)
Calculated Cell | Summary data and percentage completion formulas
Section Header | Workstream phase separations
Standard Row | Task listings and detailed rationale
Navigational Link
Go to APM WBS Schedule →
Go to MNT12 Detailed Cutover Plan →

## APM WBS Schedule
PTTEP EP APM S/4HANA Integration - Work Breakdown Structure (WBS)
KPI Metrics | Total Tasks: |  | Project Plan %: |  | Project Actual %:
WBS Code | Task Description | Ownership | Recommended Duration (Days) | Planned Start Date | Planned End Date | Predecessors | Status | % Plan | % Actual | Mock Number | Detailed ITPM Rationale & Scope | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27 | Apr '27 | May '27 | Jun '27 | Jul '27
1.0 | EP APM S/4HANA Integration Project | Shared |  | 2026-08-21 | 2027-07-31 |  | In Progress |  |  | Mock 1, 2, 3 | Root baseline wrapping all deliverables for the APM S/4HANA cutover and go-live.
1.1 | Project Management & Governance | Shared |  | 2026-08-21 | 2027-07-21 |  | In Progress |  |  | N/A | Continuous oversight, risk tracking, and PMO reporting.
1.1.1 | Schedule & Swimlane Synchronization | Shared | 334 | 2026-08-21 | 2027-07-21 |  | In Progress |  |  | N/A | Aligning APM cutover timelines with corporate SHANA Key Dates.
1.1.2 | Risk, Action & Issue Tracking | Shared | 334 | 2026-08-21 | 2027-07-21 |  | In Progress |  |  | N/A | Tracking system bugs in SHANA_SIT Issue Tracker.
1.1.3 | PMO Status Reporting & Milestone Gates | Shared | 334 | 2026-08-21 | 2027-07-21 |  | In Progress |  |  | N/A | Reporting progress to central PMO to pass program milestone gates.
1.2 | Impact Analysis & Solution Design | Shared |  | 2026-08-21 | 2026-09-30 |  | Complete |  |  | Mock 1 | Assessing database and schema impacts on downstream APM schemas.
1.2.1 | S/4HANA Structural Change Assessment | APM Team | 25 | 2026-08-21 | 2026-09-15 |  | Complete |  |  | Mock 1 | Assessing impacts on Equipment, Functional Location, and Measurement Documents.
1.2.2 | Interface Mapping Design (PM-I-109 API) | Shared | 30 | 2026-08-25 | 2026-09-24 | 1.2.1 | Complete |  |  | Mock 1 | Mapping standard SAP fields via CPI / API Gateways to APM endpoints.
1.2.3 | GCP Datamart & BigQuery Schema Confirmation | Shared | 30 | 2026-08-25 | 2026-09-24 | 1.2.1 | Complete |  |  | Mock 1 | Designing target datamarts for APM transactional consumption.
1.3 | System Development & Unit Testing | Shared |  | 2026-09-15 | 2026-10-30 | 1.2 | Complete |  |  | Mock 1 | Remediating application core code and pipeline setups.
1.3.1 | API Gateway Connectivity Build | SAP Team | 20 | 2026-09-15 | 2026-10-05 | 1.2.2 | Complete |  |  | Mock 1 | Configuring Apigee and CPI outbound secure communication.
1.3.2 | GCP Data Platform ETL Pipeline Build | SAP Team | 25 | 2026-09-20 | 2026-10-15 | 1.2.3 | Complete |  |  | Mock 1 | Bluebik and ODC developers establishing GCP staging loads.
1.3.3 | APM Core Application Remediation | APM Team | 30 | 2026-10-01 | 2026-10-30 | 1.2.1 | Complete |  |  | Mock 1 | Vendor modifying backend to align with new location and equipment names.
1.4 | System Integration Testing (SIT) | Shared |  | 2026-10-15 | 2026-11-24 | 1.3 | In Progress |  |  | Mock 1 | Testing all data streams between S/4HANA and APM backend.
1.4.1 | Test Script Prep & Metadata Alignment | Shared | 15 | 2026-10-15 | 2026-10-30 | 1.3.3 | Complete |  |  | Mock 1 | Reviewing test cases in SIT Baseline 1 and SharePoint folder 04. MNT.
1.4.2 | Interface End-to-End Execution (PM-I-109) | Shared | 20 | 2026-11-01 | 2026-11-20 | 1.4.1 | In Progress |  |  | Mock 1 | Executing synchronous real-time notification syncs.
1.4.3 | Defect Remediation & Re-testing Cycle | Shared | 15 | 2026-11-10 | 2026-11-24 | 1.4.2 | Not Started |  |  | Mock 1 | Resolving bugs via SHANA_SIT tracker.
1.5 | User Acceptance Testing (UAT) | Shared |  | 2026-08-21 | 2027-02-15 | 1.4 | In Progress |  |  | Mock 2 | Testing business scenarios with key users on Mock 2.
1.5.1 | Environment Prep & User ID Provisioning | Shared | 11 | 2026-08-21 | 2026-09-01 |  | Complete |  |  | Mock 2 | Submitting Matrix 3 on 1-Sep and provisioning user IDs in Azure AD.
1.5.2 | Business Scenario Selection & Test Data | APM Team | 25 | 2026-08-21 | 2026-09-15 |  | Complete |  |  | Mock 2 | Key users drafting scenarios and preparing validation criteria.
1.5.3 | UAT Execution, Defect Resolution & Sign-off | APM Team | 62 | 2026-12-15 | 2027-02-15 | 1.4.2 | Not Started |  |  | Mock 2 | UAT Execution Kick-Off starting Dec 15 with 100+ site users.
1.6 | Mock Cutover & Dress Rehearsals | Shared |  | 2026-09-01 | 2027-06-03 | 1.3 | In Progress |  |  | Mock 1, 2, 3 | Conducting mock cutovers of increasing complexity.
1.6.1 | Mock 1 Execution (Initial Connectivity) | Shared | 15 | 2026-09-01 | 2026-09-15 | 1.3.1 | Complete |  |  | Mock 1 | Testing initial data ingest in staging environment.
1.6.2 | Mock 2 Execution (Data Conversion) | Shared | 30 | 2026-11-15 | 2026-12-15 | 1.6.1 | In Progress |  |  | Mock 2 | Executing location-to-plantsection data mapping on GCP.
1.6.3 | Mock 3 Execution (Full Dress Rehearsal) | Shared | 167 | 2026-12-18 | 2027-06-03 | 1.6.2 | Not Started |  |  | Mock 3 | Comprehensive timed simulation mimicking ACO blackout.
1.7 | Cutover & Go-Live Execution (ACO) | Shared |  | 2027-04-19 | 2027-07-01 | 1.6.3 | Not Started |  |  | Mock 3 | Executing the actual cutover and launch sequence.
1.7.1 | Ramp Down Activities | APM Team | 15 | 2027-06-01 | 2027-06-15 | 1.7.2 | Not Started |  |  | Mock 3 | Freezing and cleansing legacy notifications.
1.7.2 | Blackout Window Execution | Shared | 5 | 2027-06-25 | 2027-06-30 | 1.7.1 | Not Started |  |  | Mock 3 | Stopping data creation, backup, and GCP data conversion.
1.7.3 | Ramp Up (Application Startup & Go-Live) | Shared | 1 | 2027-07-01 | 2027-07-01 | 1.7.2 | Not Started |  |  | Mock 3 | APM Application startup at 08:01 on July 1 target date.
1.8 | Training & Post Go-Live Support | Shared |  | 2027-06-01 | 2027-07-31 | 1.7.3 | Not Started |  |  | Mock 3 | Providing Hypercare and change enablement to users.
1.8.1 | Key User Training & End User Training | APM Team | 30 | 2027-06-01 | 2027-06-30 | 1.5.3 | Not Started |  |  | Mock 3 | Conducting KUT and EUT to prepare site maintenance engineers.
1.8.2 | Hypercare Support Operations | Shared | 30 | 2027-07-01 | 2027-07-31 | 1.7.3 | Not Started |  |  | Mock 3 | War-room support post-launch (PGLS phase).

## MNT12 Detailed Cutover Plan
PTTEP EP APM (MNT12) - Detailed Cutover Plan & Runbook
KPI Metrics | Total Tasks: |  | Complete %:
WBS Code | Stage | Task Description | Ownership | Planned Start Date/Time | Planned End Date/Time | Status | % Plan | % Actual | Detailed Description & Rationale (Thai/English)
MNT12.01 | Ramp Down | Create ticket to deploy APIgee service | APM Team | 2026-12-05 | 2026-12-18 23:59 | Not Started |  |  | APM: สร้าง Ticket เพื่อเตรียม Deploy Apigee service (CPI outbound) ระหว่าง Ramp down [Ref: Slide: GCP Swimlane]
MNT12.02 | Ramp Down | Master data sync up to legacy #1 Batch 1.1-1.6 | SAP Team | 2026-12-19 | 2026-12-21 23:59 | Not Started |  |  | SAP: ข้อมูล Master Data Object จาก SAP เริ่มทยอยไหลไปที่ APM [Ref: Slide: GCP Swimlane]
MNT12.03 | Ramp Down | Last Create Notification, PM Work Order (SAP) | SAP Team | 2026-12-24 12:00 | 2026-12-24 12:00 | Not Started |  |  | SAP กำหนดให้วันที่ 24 Dec เป็นรายการสุดท้ายของ Notification และ PM Work Order [Ref: Slide: Maintenance]
MNT12.04 | Ramp Down | Last Create Notification, PM Work Order (APM) | APM Team | 2026-12-24 12:01 | 2026-12-24 12:01 | Not Started |  |  | APM หยุดสร้าง Notification, PM Work Order (dependency no. 2) [Ref: Slide: Maintenance]
MNT12.05 | Ramp Down | Deploy Apigee service to PRD | SAP Team | 2026-12-25 08:00 | 2026-12-25 17:00 | Not Started |  |  | CPI ทำการ Deploy Apigee service to PRD [Ref: Slide: GCP Swimlane]
MNT12.06 | Ramp Down | Open Notification, PM Order, Measurement Document | SAP Team | 2026-12-25 18:01 | 2026-12-31 23:59 | Not Started |  |  | SAP: ข้อมูล Transaction Data จาก SAP เริ่มทยอยไหลไปที่ APM ระหว่าง blackout [Ref: Slide: Transaction Data]
MNT12.07 | Blackout | APIHUB via Apigee connectivity readiness | SAP Team | 2026-12-26 08:00 | 2026-12-26 08:00 | Not Started |  |  | GCP: ข้อมูลจาก Data Sphere เริ่มไหลมาที่ GCP [Ref: Slide: GCP]
MNT12.08 | Blackout | Application shutdown | APM Team | 2026-12-26 08:00 | 2027-01-01 08:00 | Not Started |  |  | APM ปิดระบบ เพื่อรอให้ทาง Data และ Technical เตรียม conversion และ deploy [Ref: Slide: GCP]
MNT12.09 | Blackout | Database backup | APM Team | 2026-12-26 08:00 | 2026-12-26 08:00 | Not Started |  |  | APM ทำการ Backup Database [Ref: Slide: GCP]
MNT12.10 | Blackout | Data Conversion and transformation to align with S/4 Structure | APM Team | 2026-12-26 10:00 | 2026-12-30 23:59 | Not Started |  |  | APM ทำการ Conversion และ Transformation ข้อมูลให้ตรงตาม S/4 Structure [Ref: Slide: GCP]
MNT12.11 | Blackout | New deployment (DB, BE, FE) | APM Team | 2026-12-29 13:00 | 2026-12-29 13:00 | Not Started |  |  | APM ทำการ Deploy (DB, BE, FE) [Ref: Slide: GCP]
MNT12.12 | Ramp Up | Application startup | APM Team | 2027-01-04 08:01 | 2027-01-04 08:01 | Not Started |  |  | APM เปิดระบบ กลับมาใช้งานได้ตามปกติ [Ref: Slide: GCP]
MNT12.13 | Ramp Up | Hypercare, system monitoring | Shared | 2027-01-04 | 2027-01-16 23:59 | Not Started |  |  | APM เตรียม Stand by ดูความเรียบร้อย และประเมินระบบหลังขึ้นระบบจริง [Ref: Slide: GCP]