## dashboard v1 (hidden)
Baseline VS Activity
Activity

## Baseline V1 (hidden)
Actual | 42.73% | [6 empty] | Year 2026
Plan | 75.62% | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
Varience | behide | [6 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
 | time axis 2026-01-05 to 2026-12-28
 | time axis 2026-01-05 to 2026-12-28
module | feature | story id | start | end | sprint no. | % plan | % actual
MVP1 | User Authentication | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 | 100% | 100%
|  | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 | 100% | 100%
|  | S2: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 | 100% | 100%
| Task Management | S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 | 100% | 100%
|  | S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 | 100% | 100%
|  | S3: Due Date Reminders | 2026-03-02 | 2026-03-13 | Sprint 5 | 100% | 100%
|  | S4: Task Archiving | 2026-03-16 | 2026-03-27 | Sprint 6 | 100% | 100%
MVP2 | Calendar Integration | S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 | 100% | 100%
|  | S2: Drag-and-Drop Scheduling | 2026-04-20 | 2026-05-01 | Sprint 8 | 100% | 100%
|  | S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 | 100% | 20%
| Progress Tracking | S1: Daily Progress Dashboard | 2026-05-18 | 2026-05-29 | Sprint 10 | 100% | 10%
|  | S2: Weekly Productivity Reports | 2026-06-01 | 2026-06-12 | Sprint 11 | 100% | 10%
|  | S3: Streak/Gamification | 2026-06-15 | 2026-06-26 | Sprint 12 | 100% | 0%
Ph3 | Collaboration | S1: Shared Task Lists | 2026-07-06 | 2026-07-17 | Sprint 13 | 100% | 0%
|  | S2: Team Comments/Mentions | 2026-07-20 | 2026-07-31 | Sprint 14 | 100% | 0%
|  | S3: Role-based Permissions | 2026-08-03 | 2026-08-14 | Sprint 15 | 100% | 0%
| Advanced Tools | S1: Pomodoro Timer | 2026-08-17 | 2026-08-28 | Sprint 16 | 63.64% | 0%
|  | S2: Focus Mode | 2026-08-31 | 2026-09-11 | Sprint 17 | 0% | 0%
QA/Go-Live | Final Stabilization | S1: UAT & Bug Fixing | 2026-10-05 | 2026-10-16 | Sprint 20 | 0% | 0%
|  | S2: Performance Tuning | 2026-10-19 | 2026-10-30 | Sprint 21 | 0% | 0%
|  | S3: Deployment & Go-Live | 2026-11-02 | 2026-11-13 | Sprint 22 | 0% | 0%
| Post-Launch | S1: Maintenance & Feedback | 2026-11-16 | 2026-12-25 | Sprint 23-25 | 0% | 0%

## Baseline V2 (hidden)
Actual | 59.94% | [6 empty] | Year 2026
Plan | 100% | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
Varience | behide | [6 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
 | time axis 2026-01-05 to 2026-12-28
 | time axis 2026-01-05 to 2026-12-28
module | feature | story id | start | end | sprint no. | % plan | % actual
MVP1 |  |  | 2026-01-05 | 2026-03-27 |  |  | 100%
| User Authentication |  | 2026-01-05 | 2026-01-30 |  | 100% | 100%
|  | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 | 100% | 100%
|  | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 | 100% | 100%
|  | S2: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 | 100% | 100%
| Task Management |  | 2026-02-02 | 2026-03-27 |  | 49% | 50%
|  | S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 | 100% | 50%
|  | S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 | 100% | 50%
|  | S3: Due Date Reminders | 2026-03-02 | 2026-03-13 | Sprint 5 | 100% | 50%
|  | S4: Task Archiving | 2026-03-16 | 2026-03-27 | Sprint 6 | 100% | 50%
MVP2 |  |  | 2026-04-06 | 2026-06-26
| Calendar Integration |  | 2026-04-06 | 2026-05-15
|  | S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 | 100% | 100%
|  | S2: Drag-and-Drop Scheduling | 2026-04-20 | 2026-05-01 | Sprint 8 | 100% | 100%
|  | S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 | 100% | 9%
| Progress Tracking |  | 2026-05-18 | 2026-06-26
|  | S1: Daily Progress Dashboard | 2026-05-18 | 2026-05-29 | Sprint 10 | 100% | 0%
|  | S2: Weekly Productivity Reports | 2026-06-01 | 2026-06-12 | Sprint 11 | 100% | 0%
|  | S3: Streak/Gamification | 2026-06-15 | 2026-06-26 | Sprint 12 | 100% | 0%

## Master Plan V1 (hidden)
Project Actual: | 88.62%
Project Plan: | 100%
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual
MVP1: ASM |  | 2026-01-05 | 2026-03-27 | Ongoing | Green | 100% | 88.62%
CMMS |  | 2026-01-05 | 2026-01-30 |  | Green | 100%
| S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100% | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100% | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  | 100% | 100%
AI |  | 2026-02-02 | 2026-03-27 |  | Green | 100%
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  | 100% | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  | 100% | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 | Upcoming | Green | 100%
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  | Green | 100%
| S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  | 100% | 100%
| S2: Drag-and-Drop | 2026-04-20 | 2026-05-01 | Sprint 8 |  | 100% | 100%
| S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  | 100% | 9%

## Master Plan V2 (hidden)
Project Actual: | 84.83%
Project Plan: | 100%
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual
MVP1: ASM |  | 2026-01-05 | 2026-03-27 | Ongoing | Green | 100% | 100%
CMMS |  | 2026-01-05 | 2026-01-30 |  | Green | 100% | 100%
| S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100% | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100% | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  | 100% | 100%
AI |  | 2026-02-02 | 2026-03-27 |  | Green | 100% | 100%
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  | 100% | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  | 100% | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 | Upcoming | Green | 100% | 69.67%
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  | Green | 100% | 69.67%
| S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  | 100% | 100%
| S2: Drag-and-Drop | 2026-04-20 | 2026-05-01 | Sprint 8 |  | 100% | 100%
| S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  | 100% | 9%

## master Plan V3 (hidden)
Project Actual: | 84.83% |  | Project start | 2026-01-05 |  |  |  | Year 2026
Project Plan: | 100% | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[8 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
 | time axis 2026-01-05 to 2026-12-28
[8 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
MVP1: ASM |  | 2026-01-05 | 2026-03-27 |  | Green | 100% | 100%
CMMS |  | 2026-01-05 | 2026-01-30 |  | Green | 100% | 100%
| S1: Login/Signup | 2026-01-05 | 2026-01-17 | Sprint 1 |  | 100% | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100% | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  | 100% | 100%
AI |  | 2026-02-02 | 2026-03-27 |  | Green | 100% | 100%
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  | 100% | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  | 100% | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 |  | Green | 100% | 69.67% | bar: 2026-01-05
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  | Green | 100% | 69.67% | bar: 2026-01-05
| S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  | 100% | 100% | bar: 2026-01-05 to 2026-01-12
| S2: Drag-and-Drop | 2026-04-20 | 2026-05-01 | Sprint 8 |  | 100% | 100%
| S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  | 100% | 9%

## master plan V4 (hidden)
Project Actual: | 85% |  | Project start | 2026-01-05 |  |  |  | Year 2026
Project Plan: | 100% | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[8 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
 | time axis 2026-01-05 to 2026-12-28
[8 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
MVP1: ASM |  | 2026-01-05 | 2026-03-27 |  | Category | 100% | 100%
CMMS |  | 2026-01-05 | 2026-01-30 |  |  | 100% | 100%
| S1: Login/Signup | 2026-01-05 | 2026-01-17 | Sprint 1 |  | 100% | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100% | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  | 100% | 100%
AI |  | 2026-02-02 | 2026-03-27 |  |  | 100% | 100%
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  | 100% | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  | 100% | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 |  |  | 100% | 70%
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  |  | 100% | 70%
| [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 2026-04-06 | 2026-04-17 | Sprint 7 |  | 100% | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 2026-04-20 | 2026-05-01 | Sprint 8 |  | 100% | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 2026-05-04 | 2026-05-15 | Sprint 9 |  | 100% | 10%
Additional Requirement |  | 2026-04-06 | 2026-05-15
| [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 2026-04-20 | 2026-05-01 | Sprint 1 |  | 100% | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 2026-05-04 | 2026-05-15 | Sprint 1 |  | 100% | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 2026-04-20 | 2026-05-01 | Sprint 2 |  | 100% | 0%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 2026-06-03 | 2026-06-30 | Sprint 9 |  | 100% | 10%

## master plan V5 (hidden)
Project Plan: | 100% | Project start: | 2026-01-05
Project Actual: | 93.33% | Project end: | 2026-05-15 | [5 empty] | Year 2026
[9 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[9 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
[9 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
Module | Feature | Start | End | Sprint | Working Day | % Plan | % Actual | status | Jan 5 W1: sp18; Jan 12 W2: sp19; Jan 26 W4: sp20; Feb 9 W6: sp21; Feb 23 W8: sp22; Mar 9 W10: sp23; Mar 23 W12: sp24; Apr 6 W14: sp25; Apr 20 W16: sp26; May 4 W18: sp27; May 18 W20: sp28; Jun 1 W22: sp29; Jun 15 W24: sp30; Jun 29 W26: sp31; Jul 13 W28: sp32; Jul 27 W30: sp33; Aug 10 W32: sp34; Aug 24 W34: sp35; Sep 7 W36: sp36; Sep 21 W38: sp37; Oct 5 W40: sp38; Oct 19 W42: sp39; Nov 2 W44: sp40; Nov 16 W46: sp41; Nov 30 W48: sp42; Dec 14 W50: sp43; Dec 28 W52: sp44
MVP1: ASM
| feature a | 2026-01-05 | 2026-01-23 | 18-19 | 15 | 100% | 100% | completed
| feature b | 2026-01-26 | 2026-02-20 | 20-21 | 20 | 100% | 100% | completed
| feature c | 2026-01-26 | 2026-02-20 | 20-21 | 20 | 100% | 100% | completed
MVP2: RCA
| feature d | 2026-02-09 | 2026-03-20 | 21-23 | 29 | 100% | 100% | completed
| feature d | 2026-03-23 | 2026-04-17 | 23-25 | 16 | 100% | 100% | completed
| feature e | 2026-04-20 | 2026-05-15 | 25-26 | 18 | 100% | 66.67% | in progress
Formulas:
Working Day = NETWORKDAYS([Start], [End], holiday!$A2:A18)

## Requirement Baseline v5 (hidden)
Module | Feature Name | User Story ID | Sprint | Status (1=Done, 0=Progress)
ASM | feature A | us1 | 18 | 1
ASM | feature A | us2 | 18 | 1
ASM | feature A | us3 | 19 | 1
ASM | feature B | us1 | 20 | 1
ASM | feature B | us2 | 21 | 1
ASM | feature B | us3 | 21 | 1
RCA | feature C | us1 | 21 | 1
RCA | feature C | us2 | 22 | 1
RCA | feature C | us3 | 23 | 1
RCA | feature D | us1 | 23 | 1
RCA | feature D | us2 | 24 | 1
RCA | feature D | us3 | 25 | 1
RCA | feature E | us1 | 25 | 1
RCA | feature E | us2 | 25 | 1
RCA | feature E | us3 | 26 | 0

## master plan v6 (hidden)
Project Plan: | 44.28% | Project start: | 2026-01-05
Project Actual: | 37.5% | Project end: | 2026-12-25 | [6 empty] | Year 2026
|  | Baseline: | 2026-12-25 | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
 | time axis 2026-01-05 to 2026-12-28
 | time axis 2026-01-05 to 2026-12-28
[10 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43 |  | sp44
Module | Feature | Start | End | Sprint | % Weight | Working Day | % Plan | % Actual | status
MVP1: ASM+AI |  | 2026-01-05 | 2026-05-15 |  |  | 97 | 100% | 100%
| Revision | 2026-01-05 | 2026-01-23 | 18-19 | 75% | 15 | 100% | 100% | completed
| CMMS | 2026-01-26 | 2026-05-15 | 20-27 | 91% | 73 | 100% | 100% | completed
| AI | 2026-02-23 | 2026-03-06 | 22 | 90% | 9 | 100% | 100% | completed
MVP2: RCA |  | 2026-05-04 | 2026-09-04 |  |  | 131 | 77.11% | 50%
| Case Creation - Create/Edit Analysis | 2026-05-04 | 2026-07-10 | 27-31 | 94% | 47 | 100% | 100% | completed
| Case Approval | 2026-06-29 | 2026-07-24 | 31-32 | 100% | 20 | 100% | 100% | completed
| Report | 2026-07-13 | 2026-08-07 | 32-33 | 90% | 18 | 100% | 100% | completed
| RCA Dashboard. | 2026-07-27 | 2026-08-21 | 33-34 | 85% | 17 | 100% | 0% | in progress
| User Management | 2026-08-10 | 2026-09-04 | 34-35 | 95% | 19 | 52.63% | 0% | in progress
| Noti Email | 2026-08-24 | 2026-09-04 | 35 | 100% | 10 | 10% | 0% | in progress
UI Improvement |  | 2026-09-07 | 2026-11-27 |  |  | 58 | 0% | 0%
| Requirement & Design | 2026-09-07 | 2026-10-02 | 36-37 | 100% | 20 | 0% | 0% | not start yet
| Implementation, Testing, and Deploy | 2026-10-05 | 2026-11-27 | 38-41 | 100% | 38 | 0% | 0% | not start yet
Handover |  | 2026-11-30 | 2026-12-25 |  |  | 19 | 0% | 0%
| Document | 2026-11-30 | 2026-12-11 | 42 | 100% | 9 | 0% | 0% | not start yet
| Knowledge Transfer | 2026-12-14 | 2026-12-25 | 43 | 100% | 10 | 0% | 0% | not start yet
Assumption:
1) the project plan based on the requirement baseline sheet "baseline"
2) additional improvement and scope can be discussed in terms of trade-off OR additional requirement
3) the actual % is weighted by working days, excluding holidays
Formulas:
Start = MIN([Start, row below]:D11)
End = MAX([Start, row below]:D11)
Working Day = NETWORKDAYS([Start], [End], holiday!$A2:A18)

## master plan bk1 (hidden)
Project Plan: | 85.43% | Project start: | 2026-01-05 |  | Baseline | 2026-09-04
Project Actual: | 68.18% | Project end: | 2026-09-04 | [6 empty] | Year 2026
|  | total user story: | 0 | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
 | time axis 2026-01-05 to 2026-12-28
 | time axis 2026-01-05 to 2026-12-28
[10 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43 |  | sp44
Module | Feature | Start | End | Sprint | % Weight | Working Day | % Plan | % Actual | status
MVP1: ASM+AI |  | 2026-01-05 | 2026-05-15 |  |  |  | 100% | 100%
| Revision | 2026-01-05 | 2026-01-23 | 18-19 | 75% | 15 | 100% | 100% | completed
| CMMS | 2026-01-26 | 2026-05-15 | 20-27 | 91% | 73 | 100% | 100% | completed
| AI | 2026-02-23 | 2026-03-06 | 22 | 90% | 9 | 100% | 100% | completed
MVP2: RCA |  | 2026-05-04 | 2026-09-04 |  |  |  | 77.11% | 50%
| Case Creation - Create/Edit Analysis | 2026-05-04 | 2026-07-10 | 27-31 | 94% | 47 | 100% | 100% | completed
| Case Approval | 2026-06-29 | 2026-07-24 | 31-32 | 100% | 20 | 100% | 100% | in progress
| Report | 2026-07-13 | 2026-08-07 | 32-33 | 90% | 18 | 100% | 100% | in progress
| RCA Dashboard. | 2026-07-27 | 2026-08-21 | 33-34 | 85% | 17 | 100% | 0% | in progress
| User Management | 2026-08-10 | 2026-09-04 | 34-35 | 95% | 19 | 52.63% | 0% | in progress
| Noti Email | 2026-08-24 | 2026-09-04 | 35 | 100% | 10 | 10% | 0% | in progress
UI Improvement |  | 0 | 0 | bar: 2026-09-07 to 2026-10-26
Analysis
Estimation
Implementation
Handover |  | 0 | 0 | bar: 2026-11-02 to 2026-11-23
Documentation
Knowledge transfer
Formulas:
Start = MIN([Start, row below]:D11)
End = MAX([Start, row below]:D11)
Working Day = NETWORKDAYS([Start], [End], holiday!$A2:A18)

## baseline v4 (hidden)
Module | Feature Name | User Story ID | User Story Description | Sprint | start | end | Status (1=Done, 0=Progress) | Is Baseline | Change Type | Note | Module ¦ Feature ¦ Sprint | [5 empty] | Baseline vs change record
asm | revision | EAPM-906 | [Improvement][Home][GeneralDetails] My Tasks - Add checked Group Permission for Waiting for Approval Box. | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti | Module | Sprint | start | end | Feature Name | Count of User Story Description | Module | Count of Is Baseline
asm | revision | EAPM-278 | [ASM][AssetStrategy] Email Notification Message - Template 2 (Review) | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti | asm |  |  |  |  | 90 | asm | 90
asm | revision | EAPM-923 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Add Description for Failure Impact + Change Field Name | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti |  | 18 | 2026-01-05 | 2026-01-09 | revision | 8 | handover | 2
asm | revision | EAPM-244 | [Improvement][ASM][AssetStrategy] Strategies Table List V3. - Add column | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti |  | 19 | 2026-01-12 | 2026-01-23 | revision | 14 | rca | 41
asm | revision | EAPM-922 | [ASM][AssetStrategy] Integrate FDP (GCP) - [BE] | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 20 | 2026-01-26 | 2026-02-06 | cmms | 14 | ui improvement | 6
asm | revision | EAPM-919 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk/Task Panel - Change Icon Yellow Alert to Arrow Icon + Abbreviate Interval + SCE Tag | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 21 | 2026-02-09 | 2026-02-20 | cmms | 8 | Grand Total | 139
asm | revision | EAPM-882 | [ASM] Apply a consistent design standard to all action buttons. [FE] | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 22 | 2026-02-23 | 2026-03-06 | ai | 7
asm | revision | EAPM-1071 | [Improvement][ASM][AssetStrategy] All Table List - Change Design the shown numbers as total, select items, filter results | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  |  |  |  | cmms | 4
asm | revision | EAPM-10 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 23 | 2026-03-09 |  |  | 7
asm | revision | EAPM-11 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 24 | 2026-03-23 | 2026-04-03 | cmms | 11
asm | revision | EAPM-7 | [ASM][AssetStrategy][Revisions] Revision Details - Risks and Tasks | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 25 | 2026-04-06 | 2026-04-17 | cmms | 5
asm | revision | EAPM-25 | [ASM][AssetStrategy][Revisions] Revision Details - Risks Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 26 | 2026-04-20 | 2026-05-01 | cmms | 6
asm | revision | EAPM-26 | [ASM][AssetStrategy][Revisions] Revision Details - Task Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | cmms | 5
asm | revision | EAPM-8 | [ASM][AssetStrategy][Revisions] Revision Details - Risk Analysis | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | ai | 1
asm | revision | EAPM-9 | [ASM][AssetStrategy][Revisions] Revision Details - Maintenance Plans | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  | rca |  |  |  |  | 57
asm | revision | EAPM-1255 | [ASM][AssetStrategy] Trigger an update for all data retrieved from GCP. (Location, FDP, Maintenance Plan, ...) | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | Case creation - Create/Edit Analysis | 6
asm | revision | EAPM-1302 | [Improvement][Home][GeneralDetails] My Task - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 28 | 2026-05-18 | 2026-05-29 | Case creation - Create/Edit Analysis | 10
asm | revision | EAPM-1303 | [Improvement][Admin] User Management - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | Case creation - Create/Edit Analysis | 7
asm | revision | EAPM-1304 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Maintenance Plan table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | Case creation - Create/Edit Analysis | 4
asm | revision | EAPM-1392 | [Improvement][ASM][AssetStrategy] Strategy Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 31 | 2026-06-29 | 2026-07-10 | case approval | 2
asm | revision | EAPM-1393 | [Improvement][ASM][AssetStrategy][Revision] Revision Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline | [6 empty] | Case creation - Create/Edit Analysis | 3
asm | revision | EAPM-1394 | [Improvement][ASM][AssetStrategy][Overview] Risk Matrix by Active Strategy Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 32 | 2026-07-13 | 2026-07-24 | case approval | 14
asm | cmms | EAPM-1150 | [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-349 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #1 | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 33 | 2026-07-27 | 2026-08-07 | RCA Dashboard. | 2
asm | cmms | EAPM-1309 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #2 | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-2000 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add dropdown "Work Center" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 34 | 2026-08-10 | 2026-08-21 | RCA Dashboard. | 2
asm | cmms | EAPM-1999 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details V3. | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | User Management | 1
asm | cmms | EAPM-1585 | [Improvement][FE][ASM][RisksAndTasks] Risk Property - Add more suggestion to 3M, 6M, 12M, 18M, 24M | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 35 | 2026-08-24 | 2026-09-04 | Noti Email | 2
asm | cmms | EAPM-1883 | [Improvement][ASM][RisksAndTasks] - Risk Detail / Task Detail - Add more suggestion | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | User Management | 2
asm | cmms | EAPM-2003 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Change Logic | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  | handover |  |  |  |  | 2
asm | cmms | EAPM-2006 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details - Set default ROI to "-1" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 42 | 2026-11-30 | 2026-12-11 | Document | 1
asm | cmms | EAPM-2004 | [Improvement][ASM][AssetStrategy][SummaryDetails] Change default "Plant Length =20" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 43 | 2026-12-14 | 2026-12-25 | Knowledge Transfer | 1
asm | cmms | EAPM-1314 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  | ui improvement |  |  |  |  | 6
asm | cmms | EAPM-599 | [ASM][AssetStrategy][MaintenancePlans] Table List - Submit Change Request Flow | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 36 | 2026-09-07 | 2026-09-18 | Requirement & Design | 1
asm | cmms | EAPM-1305 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 37 | 2026-09-21 | 2026-10-02 | Requirement & Design | 1
asm | cmms | EAPM-1799 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action - Export Excel | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 38 | 2026-10-05 | 2026-10-16 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2423 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 39 | 2026-10-19 | 2026-10-30 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2487 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Converted interval value K = 000H | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 40 | 2026-11-02 | 2026-11-13 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-33 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (RequestInfo) #1 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 41 | 2026-11-16 | 2026-11-27 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1306 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #1 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  | (blank) |  |  |  |  | 7
asm | cmms | EAPM-1801 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #2 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | (blank) | 7
asm | cmms | EAPM-1955 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #3 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  | Grand Total |  |  |  |  | 162
asm | cmms | EAPM-1307 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) - Add/Duplicate/Delete row | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline
asm | cmms | EAPM-2486 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Scale Bar - Icon U / M | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline
asm | ai | EAPM-1308 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (ObjectList) + Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | ai | EAPM-1310 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #1 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | ai | EAPM-1844 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #2 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | ai | EAPM-1311 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | ai | EAPM-1312 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #1 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | ai | EAPM-1845 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #2 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | ai | EAPM-1313 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2745 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - CMMS Form(PreFilled) - MaintenancePlanItem - Case: Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2779 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2780 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2759 | [ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Request Sub." | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1318 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (AttachJobCard) | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-32 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Initial + Before | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-1803 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - After | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2488 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Related Strategy | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2672 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Calculate Summary Interval | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2945 | [FE][POC][ASM][AssetStrategy][MaintenancePlan] POC CMMS Final Form - UI Screen + Export Excel | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2946 | [FE][Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Work Center" field | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2007 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Initial + Request Info | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2933 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Plan Item | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2934 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Item (Object List) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2935 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Header) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2936 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Operation) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2937 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Attach Job Card | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2362 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - save data to APM DB | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3352 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - "Submit / Back" Button | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3448 | [BE][ASM][AssetStrategy] Sync all "ASM Strategies" to GCP | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3445 | [FE][RCA] POC powerpoint | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline |  | rca
asm | cmms | EAPM-3717 | [ASM] Update schema follow s4AHANA format | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-3727 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-1160 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - After Submit CMMS - Add logic Submit button | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-3797 | [POC][FE][RCA] Logic Tree - Diagram | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline |  | rca
asm | cmms | EAPM-3875 | [Improvement][ASM][FE] Abbreviate number when exceeding digit threshold | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-4027 | [Improvement][ASM][BE] tuning performance Graph | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-4042 | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-3671 | [Improvement][AssetStrategy][CMMS] Add column “SCE Group” + Prefill Operation Short Text + Add K logic | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-3355 | [ASM][AssetStrategy][MaintenancePlans] Table List - Change Request No. - Hyperlink - modal Final, SG preview, related SG | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-1316 | [ASM][AssetStrategy][CMMS] CMMS History Log - table + click button + Overview | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-2808 | [ASM][AssetStrategy][CMMS] CMMS History Log - Click Hyperlink - View CMMS Final Form Details | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-3926 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel (Submitted Final Form) | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-2809 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel Table View | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4289 | [RCA] Initial Layout | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3416 | [RCA][createNewAnalysis] modal input Case name >> save draft | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4296 | [RCA][Dashboard] RCA Analysis (All) - table list | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3420 | [RCA][createNewAnalysis] Common Header | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-1800 | [ASM][FE] Upgrade Version Angular | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4447 | [ASM] Sustainable Tuning for support 2-3x or more data | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | moved | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-4356 | [Improvement][SAP] change toast error message after submit CMMS | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4355 | [Improvement][SAP] Error Handling from SAP response | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | moved | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-3407 | [RCA][createNewAnalysis] Team Member | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3408 | [RCA][createNewAnalysis] Case Background | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3409 | [RCA][createNewAnalysis] Problem Analysis | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3410 | [RCA][createNewAnalysis] Incident Timeline | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | moved | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-4730 | [Improvement][ASM][CMMS] Submit CMMS - Add PackageNo not found page | 28 | 2026-05-18 | 2026-05-29 | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM-4731 | [Improvement][ASM][CMMS] Submit CMMS - Change logic field "Updated Field" | 28 | 2026-05-18 | 2026-05-29 | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM-3752 | [Improvement][ASM][AssetStrategy][Revision] disabled icon restore | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3898 | [Improvement][ASM][BE+FE] Abbreviate number when exceeding digit threshold | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis |  | [RCA][createNewAnalysis] Incident Timeline - Export PDF | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | removed | remove
asm | ai | EAPM-347 | [ASM][AssetStrategy][RisksAndTasks] Risk tap Details - Integrate AI Suggestion | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3411 | [RCA][createNewAnalysis] Finding | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | moved | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-3412 | [RCA][createNewAnalysis] Logic Tree | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Logic Tree - Box Details | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4516 | [RCA][createNewAnalysis] Logic Tree - Box Details - Actions | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Verification Action | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | split | breakdown 5217, move to sprint 30
rca | Case creation - Create/Edit Analysis | EAPM-4567 | [RCA][createNewAnalysis] Verification Action - Noti | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3414 | [RCA][createNewAnalysis] RCA Recommendations | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | split | breakdown 5234
rca | Case creation - Create/Edit Analysis | EAPM-3415 | [RCA][createNewAnalysis] Other Recommendations | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | split | breakdown 5235
rca | Case creation - Create/Edit Analysis | EAPM-4568 | [RCA][createNewAnalysis] Reference Document - Table 1 | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4569 | [RCA][createNewAnalysis] Reference Document - Table 2 | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | moved | move to backlog
rca |  | EAPM-5493 | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca |  | EAPM-5158 | [Improvement][RCA][createNewAnalysis] change source of PTTEP Risk Matrix + Add last updated date | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca |  | EAPM-5241 | [Improvement][RCA][createNewAnalysis] Verification Actions - Table List - allow assigned group email from azure + add column "Last Updated by" | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca |  | EAPM-5397 | [RCA] Sharepoint Structure | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca |  | EAPM-5395 | [Improvement][RCA][createNewAnalysis] add asset when create new RCA + add validate input format "RCA Case Name" | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca |  | EAPM-5434 | [Improvement][RCA][FE][createNewAnalysis] change save button name + change placeholder | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca |  | EAPM-5572 | [ServerError] HTTP Status Error 5xx | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-3406 | [RCA][createNewAnalysis] Executive Summary | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | moved | move to sprint 30
rca | case approval | EAPM-5023 | [RCA][Approval Flow] Case Approval - Approval detail + progress - Fa view | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | moved | move to sprint 32
rca | case approval | EAPM-5237 | [RCA][Approval Flow] Case Approval - Approval detail + progress - approver view | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | moved | move to sprint 32
rca | Case creation - Create/Edit Analysis | EAPM-5812 | [Improvement][RCA][createNewAnalysis] Logic Tree - Main diagram | 31 | 2026-06-29 | 2026-07-10 | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM 5848 | [Improvement][RCA][createNewAnalysis] Add validation - Folder Name in Sharepoint | 31 | 2026-06-29 | 2026-07-10 | 1 |  | added | add on
rca | case approval | EAPM 5024 | [RCA][Approval Flow] Case Approval - Approval detail + progress - viewer | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 6178 | [RCA][Approval Flow] Case Approval - Approval Progress - Super User view | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 5847 | [RCA][Approval Flow] Case Approval - Approval History | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 5027 | [RCA][Approval Flow] Case Approval - Noti Email - Inform | 32 | 2026-07-13 | 2026-07-24 | 1 |  | moved | move to sprint 33
rca | Report | EAPM 5028 | [RCA] Export Report | 32 | 2026-07-13 | 2026-07-24 | 1 |  | moved | move to sprint 33
rca | case approval | EAPM-5022 | [RCA][Approval Flow] RCA Approval Tracking modal - Structure | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5026 | [RCA][Approval Flow] Case Status - Permission | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5059 | [RCA][UserManagement] Master Data Setting "RCA Type" | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5236 | [RCA][Approval Flow] Submit RCA Case - “Start Investigation” button | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6028 | [RCA][createNewAnalysis] Executive Summary - Design Request/Response JSON for AI | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6231 | [RCA] Add Permission to all pages in RCA | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6367 | [RCA][Approval Flow] Submit RCA Case - Flow Start Investigation | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6368 | [RCA][Approval Flow] Submit RCA Case - Waiting Verification | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6369 | [RCA][Approval Flow] Submit RCA Case - Approve | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6370 | [RCA][Approval Flow] Submit RCA Case - Implementing Action and Complete | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | Report | EAPM 5029 | [RCA] Export Report - ppt >> PDF | 33 | 2026-07-27 | 2026-08-07 | 1 | baseline
rca | RCA Dashboard. | EAPM-3417 | [RCA][createNewAnalysis] Dash Board - Graph | 33 | 2026-07-27 | 2026-08-07 | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Analysis(All) | 33 | 2026-07-27 | 2026-08-07 | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Verification (Pending) | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Recommendation (Pending) | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Azure | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline | moved | move to sprint 31, breakerdown 5038, 5058
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - Add input setting | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline | moved | move to sprint 31, breakerdown 5056, 5057, 5036, 5037
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - display | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline | moved | move to sprint 31, breakdown 5034, 5035, 5020
rca | Noti Email |  | [RCA] Notification Email - Monthly 16th | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline
rca | Noti Email |  | [RCA] Notification Email - Monthly 1st | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #1 | 36 | 2026-09-07 | 2026-09-18 | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #2 | 37 | 2026-09-21 | 2026-10-02 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #1 | 38 | 2026-10-05 | 2026-10-16 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #2 | 39 | 2026-10-19 | 2026-10-30 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #3 | 40 | 2026-11-02 | 2026-11-13 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #4 | 41 | 2026-11-16 | 2026-11-27 | 0 | baseline
handover | Document |  | [Document] system and user manual, sonaqube result | 42 | 2026-11-30 | 2026-12-11 | 0 | baseline
handover | Knowledge Transfer |  | [KT] knowledge transfer | 43 | 2026-12-14 | 2026-12-25 | 0 | baseline
Formulas:
start = VLOOKUP([Sprint], sprintday!$A6:C32, 2, FALSE)
end = VLOOKUP([Sprint], sprintday!$A6:C32, 3, FALSE)

## Summary
APM Project – Summary & Dashboard
Project: S1 AI Advisory Flowline Back Pressure Optimization ¦ ITPM: Parinya Kamnoed (Chaii)
Baseline established: April 2026 ¦ As of: 24 Aug 2026
1 ¦ EXECUTIVE SUMMARY – Project Status (PMO View)
✔ PROJECT ON TRACK – Timeline unchanged, RCA on plan to finish Sprint 35, SAP activities accommodated without impact
Item | Detail | Impact on Timeline
Project Timeline (Sprint 18 – 43) | 05 Jan 2026 – 25 Dec 2026 | NOT affected – unchanged from baseline
RCA Module Completion | RCA still planned to complete at Sprint 35 | NOT affected – on schedule
SAP Activities (ECC → S/4HANA) | 8 SAP items across Sprint 20-30 | NOT affected – accommodated within existing timeline
Change Types Impact | Added: 11 ¦ Moved: 13 ¦ Removed: 1 ¦ Split: 26 | NOT affected – all within original timeline
Customer/User Focus | User focus from RCA onward (Sprint 24+); ASM already passed & accepted | N/A – ASM phase complete
2 ¦ DASHBOARD – Baseline vs Current Scope
2a ¦ Scope Overview
Metric | Value | Comment
Baseline scope (items) | 139 | Original baseline at SOR 2026
Current scope (items) | 162 | Everything in the plan today
Net change (items) | 23 | Track of change
Net change (%) | 0.16547
– New add-on requests (Added) | 11 | New scope items
– Items broken down (Split) | 26 | Same scope, more detailed tickets
– Items moved to another sprint | 13 | Sequence changed, scope unchanged
– Items removed (de-scoped) | 1 | Removed from plan
SAP Activities (highlighted) | 8 | ECC → S/4HANA migration tasks
Timeline (start – end) | 05 Jan 26 – 25 Dec 26 | Unchanged from baseline
2b ¦ Change Breakdown by Module
Module | Baseline Items | Added | Split | Moved | Removed | Current Items
ASM | 85 | 3 | 0 | 1 | 0 | 88
RCA | 37 | 7 | 26 | 11 | 1 | 56
UI IMPROVEMENT | 6 | 0 | 0 | 0 | 0 | 6
HANDOVER | 2 | 0 | 0 | 0 | 0 | 2
SAP | 7 | 1 | 0 | 1 | 0 | 8
TOTAL | 137 | 11 | 26 | 13 | 1 | 160
3 ¦ SAP ACTIVITY HIGHLIGHTS (ECC → S/4HANA Migration)
Note: SAP items are highlighted in the 'baseline' sheet (module = 'sap'). These activities relate to ECC → S/4HANA migration and have been accommodated within the existing sprint plan without timeline impact.
Sprint | Story ID | Feature | Description | Status | Change Type | Note
Sprint 20 | EAPM-1314 | cmms | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | Done | baseline
Sprint 21 | EAPM-2423 | cmms | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | Done | baseline
Sprint 25 | EAPM-3717 | sap | [ASM] Update schema follow s4AHANA format | Done | baseline
Sprint 25 | EAPM-3727 | cmms | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | Done | baseline
Sprint 26 | EAPM-4042 | cmms | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | Done | baseline
Sprint 27 | EAPM-4356 | cmms | [Improvement][SAP] change toast error message after submit CMMS | Done | baseline
Sprint 28 | EAPM-4355 | cmms | [Improvement][SAP] Error Handling from SAP response | Done | moved | move to 28
Sprint 30 | EAPM-5493 | cmms | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | Done | added | add on, no impact
4 ¦ EXCLUSIVE SUMMARY – PMO Assurance Message
To PMO & Stakeholders, The APM project (S1 AI Advisory – Flowline Back Pressure Optimization) remains ON TRACK per the original baseline established in April 2026. Key points: 1. Project timeline (Sprint 18 – 43, ending 25 Dec 2026) is UNCHANGED. 2. RCA module is on plan to complete at Sprint 35 as originally scheduled. 3. SAP activities (ECC → S/4HANA migration) have been integrated into Sprints 20–30 and do NOT impact the project timeline. 4. All change types (Added, Moved, Removed, Split) have been absorbed within the original plan without extending the schedule. 5. ASM module (Sprint 18–27) is COMPLETE. User/customer focus is now on RCA and subsequent modules. The project remains green – no timeline extension required.
5 ¦ REFERENCE & NOTES
Item | Detail
Data Source | 'baseline' sheet – item-level plan with Is Baseline and Change Type columns
Sprint Calendar | 'sprintday' sheet – Sprint 18 (05 Jan 2026) to Sprint 43 (25 Dec 2026)
Change Types | Added = new scope, Moved = sprint re-sequence, Removed = de-scoped, Split = broken down into sub-tickets
SAP Module | SAP tasks relate to ECC → S/4HANA migration; highlighted in yellow on the 'baseline' sheet
RCA Focus | Customer/user focus starts from RCA (Sprint 24 onward); ASM (Sprint 18–27) already passed and accepted
6 ¦ GANTT CHART – Sprint Timeline by Module
Color bars indicate which modules are active in each sprint. Yellow = SAP activity (ECC to S/4HANA). Current date: 24 Aug 2026 (approx Sprint 34).
Module | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | TOTAL
Start Date | 05-Jan | 12-Jan | 26-Jan | 09-Feb | 23-Feb | 09-Mar | 23-Mar | 06-Apr | 20-Apr | 04-May | 18-May | 01-Jun | 15-Jun | 29-Jun | 13-Jul | 27-Jul | 10-Aug | 24-Aug | 07-Sep | 21-Sep | 05-Oct | 19-Oct | 02-Nov | 16-Nov | 30-Nov | 14-Dec
ASM | 8 | 14 | 13 | 7 | 11 | 7 | 10 | 2 | 5 | 6 | 5 | 1 | 1 | [13 empty] | 90
SAP |  |  | 1 | 1 |  |  |  | 2 | 1 | 1 | 1 |  | 1 | [13 empty] | 8
RCA | [6 empty] | 1 | 1 |  | 4 | 4 | 7 | 9 | 5 | 15 | 3 | 3 | 4 | [8 empty] | 56
UI IMPROVEMENT | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6
HANDOVER | [24 empty] | 1 | 1 | 2
SPRINT TOTAL | 8 | 14 | 14 | 8 | 11 | 7 | 11 | 5 | 6 | 11 | 10 | 8 | 11 | 5 | 15 | 3 | 3 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 162
LEGEND | ASM |  | RCA |  | UI IMP |  | HANDOVER |  | SAP
7 ¦ SPRINT-BY-SPRINT BREAKDOWN
Sprint | Date Range | ASM | SAP | RCA | UI IMP | HANDOVER | Total
Sprint 18 | 05 Jan 2026 | 8 | 0 | 0 | 0 | 0 | 8
Sprint 19 | 12 Jan 2026 | 14 | 0 | 0 | 0 | 0 | 14
Sprint 20 | 26 Jan 2026 | 13 | 1 | 0 | 0 | 0 | 14
Sprint 21 | 09 Feb 2026 | 7 | 1 | 0 | 0 | 0 | 8
Sprint 22 | 23 Feb 2026 | 9 | 0 | 0 | 0 | 0 | 9
Sprint 23 | 09 Mar 2026 | 7 | 0 | 0 | 0 | 0 | 7
Sprint 24 | 23 Mar 2026 | 10 | 0 | 1 | 0 | 0 | 11
Sprint 25 | 06 Apr 2026 | 2 | 2 | 1 | 0 | 0 | 5
Sprint 26 | 20 Apr 2026 | 5 | 1 | 0 | 0 | 0 | 6
Sprint 27 | 04 May 2026 | 6 | 1 | 4 | 0 | 0 | 11
Sprint 28 | 18 May 2026 | 5 | 1 | 4 | 0 | 0 | 10
Sprint 29 | 01 Jun 2026 | 1 | 0 | 7 | 0 | 0 | 8
Sprint 30 | 15 Jun 2026 | 1 | 1 | 9 | 0 | 0 | 11
Sprint 31 | 29 Jun 2026 | 0 | 0 | 5 | 0 | 0 | 5
Sprint 32 | 13 Jul 2026 | 0 | 0 | 15 | 0 | 0 | 15
Sprint 33 | 27 Jul 2026 | 0 | 0 | 3 | 0 | 0 | 3
Sprint 34 | 10 Aug 2026 | 0 | 0 | 3 | 0 | 0 | 3
Sprint 35 | 24 Aug 2026 | 0 | 0 | 4 | 0 | 0 | 4
Sprint 36 | 07 Sep 2026 | 0 | 0 | 0 | 1 | 0 | 1
Sprint 37 | 21 Sep 2026 | 0 | 0 | 0 | 1 | 0 | 1
Sprint 38 | 05 Oct 2026 | 0 | 0 | 0 | 1 | 0 | 1
Sprint 39 | 19 Oct 2026 | 0 | 0 | 0 | 1 | 0 | 1
Sprint 40 | 02 Nov 2026 | 0 | 0 | 0 | 1 | 0 | 1
Sprint 41 | 16 Nov 2026 | 0 | 0 | 0 | 1 | 0 | 1
Sprint 42 | 30 Nov 2026 | 0 | 0 | 0 | 0 | 1 | 1
Sprint 43 | 14 Dec 2026 | 0 | 0 | 0 | 0 | 1 | 1
TOTAL |  | 88 | 8 | 56 | 6 | 2 | 160

## dashboard
Baseline vs Change — Project Scope Dashboard
Source: 'baseline' sheet (item-level plan) and 'sprintday' sheet (sprint calendar). Timeline and budget are FIXED — Sprint 18 to 43.
AS of 06 Aug 2026: not impact project timeline
Chart data (do not delete)
Module | Baseline | Current |  | Change type | Items
asm | 85 | 88 |  | Added (new scope) | 11
rca | 37 | 56 |  | Broken down (re-planned) | 12
ui improvement | 6 | 6 |  | Moved to another sprint | 13
handover | 2 | 2 |  | Removed | 1
|  |  |  | Sap | 8
1 ¦ SCOPE: BASELINE vs CURRENT
Metric | Value | Comment
Baseline scope agreed (items) | 139 | At revision baseline on SOR 2026
Current scope in plan (items) | 162 | Everything in the plan today
Net change vs baseline (items) | 23 | Track of change (additional, in original)
Net change (%) | 16.55%
– New add-on requests | 11 | New scope
– Original baseline items broken down | 12 | Same scope, more detailed tickets
SAP Activity | 8 | Sap Activities
Items de-scoped / removed | 1
Items moved to another sprint | 13 | Sequence changed, scope unchanged
Timeline (start – end) | 05 Jan 26 – 25 Dec 26 | Unchanged from baseline
2 ¦ CHANGE BY MODULE
Module | Baseline items | New items | Removed | Moved to another sprint | Current items | Net change
asm | 85 | 3 | 0 | 1 | 88 | 3
rca | 37 | 19 | 1 | 11 | 56 | 19
ui improvement | 6 | 0 | 0 | 0 | 6 | 0
handover | 2 | 0 | 0 | 0 | 2 | 0
Total | 130 | 22 | 1 | 12 | 152 | 22

## dashboard v2 (hidden)
Baseline vs Change — Project Scope Dashboard
Source: 'baseline' sheet (item-level plan) and 'sprintday' sheet (sprint calendar). Timeline and budget are FIXED — Sprint 18 to 43.
AS of 06 Aug 2026
Chart data (do not delete)
Module | Baseline | Current |  | Change type | Items
asm | 85 | 88 |  | Added (new scope) | 11
rca | 37 | 56 |  | Broken down (re-planned) | 12
ui improvement | 6 | 6 |  | Moved to another sprint | 13
handover | 2 | 2 |  | Removed | 1
1 ¦ SCOPE: BASELINE vs CURRENT
Metric | Value | Comment
Baseline scope agreed (items) | 139 | At revision baseline on SOR 2026
Current scope in plan (items) | 162 | Everything in the plan today
Net change vs baseline (items) | 23 | Track of change (additional, in original)
Net change (%) | 16.55%
– New add-on requests | 11 | New scope
– Original baseline items broken down | 12 | Same scope, more detailed tickets
Items de-scoped / removed | 1
Items moved to another sprint | 13 | Sequence changed, scope unchanged
Timeline (start – end) | 05 Jan 26 – 25 Dec 26 | Unchanged from baseline
2 ¦ CHANGE BY MODULE
Module | Baseline items | New items | Removed | Moved to another sprint | Current items | Net change
asm | 85 | 3 | 0 | 1 | 88 | 3
rca | 37 | 19 | 1 | 11 | 56 | 19
ui improvement | 6 | 0 | 0 | 0 | 6 | 0
handover | 2 | 0 | 0 | 0 | 2 | 0
Total | 130 | 22 | 1 | 12 | 152 | 22

## master plan
Project Plan: | 68.85% | Project start: | 2026-01-05
Project Actual: | 66.34% | Project end: | 2026-12-25 | [5 empty] | Year 2026
|  | Baseline: | 2026-12-25 | [5 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
 | time axis 2026-01-05 to 2026-12-28
 | time axis 2026-01-05 to 2026-12-28
[9 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43 |  | sp44
Module | Feature | Start | End | Sprint | Working Day | % Plan | % Actual | status
MVP1: ASM+AI |  | 2026-01-05 | 2026-05-15 |  | 97 | 100% | 100%
| Revision | 2026-01-05 | 2026-01-23 | 18-19 | 15 | 100% | 100% | completed
| CMMS | 2026-01-26 | 2026-05-15 | 20-27 | 73 | 100% | 100% | completed
| AI | 2026-02-23 | 2026-03-06 | 22 | 9 | 100% | 100% | completed
MVP2: RCA |  | 2026-05-04 | 2026-09-04 |  | 131 | 86.26% | 80.42%
| Case Creation - Create/Edit Analysis | 2026-05-04 | 2026-07-10 | 27-31 | 47 | 100% | 100% | completed
| Case Approval | 2026-06-29 | 2026-07-24 | 31-32 | 20 | 100% | 100% | completed
| Report | 2026-07-13 | 2026-08-07 | 32-33 | 18 | 100% | 100% | completed
| RCA Dashboard. | 2026-07-27 | 2026-08-21 | 33-34 | 17 | 100% | 75% | in progress
| User Management | 2026-08-10 | 2026-09-04 | 34-35 | 19 | 52.63% | 40% | in progress
| Noti Email | 2026-08-24 | 2026-09-04 | 35 | 10 | 10% | 0% | in progress
UI Improvement |  | 2026-09-07 | 2026-11-27 |  | 58 | 0% | 0%
| Requirement & Design | 2026-09-07 | 2026-10-02 | 36-37 | 20 | 0% | 0% | not start yet
| Implementation, Testing, and Deploy | 2026-10-05 | 2026-11-27 | 38-41 | 38 | 0% | 0% | not start yet
Handover |  | 2026-11-30 | 2026-12-25 |  | 19 | 0% | 0%
| Document | 2026-11-30 | 2026-12-11 | 42 | 9 | 0% | 0% | not start yet
| Knowledge Transfer | 2026-12-14 | 2026-12-25 | 43 | 10 | 0% | 0% | not start yet
Assumption:
1) the project plan based on the requirement baseline sheet "baseline"
2) additional improvement and scope can be discussed in terms of trade-off OR additional requirement
3) the actual % is weighted by working days, excluding holidays
Formulas:
Start = MIN([Start, row below]:D11)
End = MAX([Start, row below]:D11)
Working Day = NETWORKDAYS([Start], [End], [1]holiday!$A2:A18)

## baseline
Module | Feature Name | User Story ID | User Story Description | Sprint | start | end | Status (1=Done, 0=Progress) | Is Baseline | Change Type | Note | Module ¦ Feature ¦ Sprint | [5 empty] | Baseline vs change record
asm | improvement - MyTasks | EAPM-906 | [Improvement][Home][GeneralDetails] My Tasks - Add checked Group Permission for Waiting for Approval Box. | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti | Module | Sprint | start | end | Feature Name | Count of User Story Description | Module | Count of Is Baseline
asm | notiEmail | EAPM-278 | [ASM][AssetStrategy] Email Notification Message - Template 2 (Review) | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti | asm |  |  |  |  | 90 | asm | 90
asm | improvement - RisksAndTasks | EAPM-923 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Add Description for Failure Impact + Change Field Name | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti |  | 18 | 2026-01-05 | 2026-01-09 | revision | 8 | handover | 2
asm | improvement - TableList | EAPM-244 | [Improvement][ASM][AssetStrategy] Strategies Table List V3. - Add column | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti |  | 19 | 2026-01-12 | 2026-01-23 | revision | 14 | rca | 41
asm | GCP | EAPM-922 | [ASM][AssetStrategy] Integrate FDP (GCP) - [BE] | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 20 | 2026-01-26 | 2026-02-06 | cmms | 14 | ui improvement | 6
asm | improvement - RisksAndTasks | EAPM-919 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk/Task Panel - Change Icon Yellow Alert to Arrow Icon + Abbreviate Interval + SCE Tag | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 21 | 2026-02-09 | 2026-02-20 | cmms | 8 | Total Result | 139
asm | asm | EAPM-882 | [ASM] Apply a consistent design standard to all action buttons. [FE] | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 22 | 2026-02-23 | 2026-03-06 | ai | 7
asm | improvement - TableList | EAPM-1071 | [Improvement][ASM][AssetStrategy] All Table List - Change Design the shown numbers as total, select items, filter results | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  |  |  |  | cmms | 4
asm | revision | EAPM-10 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 23 | 2026-03-09 | 2026-03-20 | cmms | 7
asm | revision | EAPM-11 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 24 | 2026-03-23 | 2026-04-03 | cmms | 11
asm | revision | EAPM-7 | [ASM][AssetStrategy][Revisions] Revision Details - Risks and Tasks | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 25 | 2026-04-06 | 2026-04-17 | cmms | 5
asm | revision | EAPM-25 | [ASM][AssetStrategy][Revisions] Revision Details - Risks Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 26 | 2026-04-20 | 2026-05-01 | cmms | 6
asm | revision | EAPM-26 | [ASM][AssetStrategy][Revisions] Revision Details - Task Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | cmms | 5
asm | revision | EAPM-8 | [ASM][AssetStrategy][Revisions] Revision Details - Risk Analysis | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | ai | 1
asm | revision | EAPM-9 | [ASM][AssetStrategy][Revisions] Revision Details - Maintenance Plans | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  | rca |  |  |  |  | 64
asm | GCP | EAPM-1255 | [ASM][AssetStrategy] Trigger an update for all data retrieved from GCP. (Location, FDP, Maintenance Plan, ...) | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | Case creation - Create/Edit Analysis | 6
asm | improvement - MyTasks | EAPM-1302 | [Improvement][Home][GeneralDetails] My Task - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 28 | 2026-05-18 | 2026-05-29 | Case creation - Create/Edit Analysis | 10
asm | improvement - UserManagement | EAPM-1303 | [Improvement][Admin] User Management - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | Case creation - Create/Edit Analysis | 7
asm | improvement - MaintenancePlan | EAPM-1304 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Maintenance Plan table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | Case creation - Create/Edit Analysis | 4
asm | improvement - TableList | EAPM-1392 | [Improvement][ASM][AssetStrategy] Strategy Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline | [6 empty] | (empty) | 7
asm | improvement - Revision | EAPM-1393 | [Improvement][ASM][AssetStrategy][Revision] Revision Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 31 | 2026-06-29 | 2026-07-10 | case approval | 2
asm | improvement - RisksAndTasks | EAPM-1394 | [Improvement][ASM][AssetStrategy][Overview] Risk Matrix by Active Strategy Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline | [6 empty] | Case creation - Create/Edit Analysis | 3
asm | improvement - TableList | EAPM-1150 | [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 32 | 2026-07-13 | 2026-07-24 | case approval | 14
asm | improvement - Excel | EAPM-349 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #1 | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | Report | 1
asm | improvement - Excel | EAPM-1309 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #2 | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 33 | 2026-07-27 | 2026-08-07 | RCA Dashboard. | 2
asm | improvement - MaintenancePlan | EAPM-2000 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add dropdown "Work Center" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | Report | 1
asm | improvement - RisksAndTasks | EAPM-1999 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details V3. | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 34 | 2026-08-10 | 2026-08-21 | RCA Dashboard. | 2
asm | improvement - RisksAndTasks | EAPM-1585 | [Improvement][FE][ASM][RisksAndTasks] Risk Property - Add more suggestion to 3M, 6M, 12M, 18M, 24M | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | User Management | 1
asm | improvement - RisksAndTasks | EAPM-1883 | [Improvement][ASM][RisksAndTasks] - Risk Detail / Task Detail - Add more suggestion | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 35 | 2026-08-24 | 2026-09-04 | Noti Email | 2
asm | improvement - RisksAndTasks | EAPM-2003 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Change Logic | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | User Management | 2
asm | improvement - RisksAndTasks | EAPM-2006 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details - Set default ROI to "-1" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  | handover |  |  |  |  | 2
asm | improvement - StrategySummary | EAPM-2004 | [Improvement][ASM][AssetStrategy][SummaryDetails] Change default "Plant Length =20" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 42 | 2026-11-30 | 2026-12-11 | Document | 1
sap | cmms | EAPM-1314 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 43 | 2026-12-14 | 2026-12-25 | Knowledge Transfer | 1
asm | cmms | EAPM-599 | [ASM][AssetStrategy][MaintenancePlans] Table List - Submit Change Request Flow | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  | ui improvement |  |  |  |  | 6
asm | cmms | EAPM-1305 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 36 | 2026-09-07 | 2026-09-18 | Requirement & Design | 1
asm | cmms | EAPM-1799 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action - Export Excel | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 37 | 2026-09-21 | 2026-10-02 | Requirement & Design | 1
sap | cmms | EAPM-2423 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 38 | 2026-10-05 | 2026-10-16 | Implementation, Testing, and Deploy | 1
asm | improvement - MaintenancePlan | EAPM-2487 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Converted interval value K = 000H | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 39 | 2026-10-19 | 2026-10-30 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-33 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (RequestInfo) #1 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 40 | 2026-11-02 | 2026-11-13 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1306 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #1 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 41 | 2026-11-16 | 2026-11-27 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1801 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #2 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  | Total Result |  |  |  |  | 162
asm | cmms | EAPM-1955 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #3 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline
asm | cmms | EAPM-1307 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) - Add/Duplicate/Delete row | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline
asm | improvement - RisksAndTasks | EAPM-2486 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Scale Bar - Icon U / M | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline
asm | cmms | EAPM-1308 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (ObjectList) + Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1310 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #1 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1844 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #2 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1311 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
4 ¦ EXCLUSIVE SUMMARY – PMO Assurance Message | cmms | EAPM-1312 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #1 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
To PMO & Stakeholders, The APM project (S1 AI Advisory – Flowline Back Pressure Optimization) remains ON TRACK per the original baseline established in April 2026. Key points: 1. Project timeline (Sprint 18 – 43, ending 25 Dec 2026) is UNCHANGED. 2. RCA module is on plan to complete at Sprint 35 as originally scheduled. 3. SAP activities (ECC → S/4HANA migration) have been integrated into Sprints 20–30 and do NOT impact the project timeline. 4. All change types (Added, Moved, Removed, Split) have been absorbed within the original plan without extending the schedule. 5. ASM module (Sprint 18–27) is COMPLETE. User/customer focus is now on RCA and subsequent modules. The project remains green – no timeline extension required. | cmms | EAPM-1845 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #2 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1313 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2745 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - CMMS Form(PreFilled) - MaintenancePlanItem - Case: Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2779 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2780 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | improvement - MaintenancePlan | EAPM-2759 | [ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Request Sub." | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1318 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (AttachJobCard) | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-32 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Initial + Before | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-1803 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - After | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2488 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Related Strategy | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2672 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Calculate Summary Interval | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2945 | [FE][POC][ASM][AssetStrategy][MaintenancePlan] POC CMMS Final Form - UI Screen + Export Excel | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | improvement - MaintenancePlan | EAPM-2946 | [FE][Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Work Center" field | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2007 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Initial + Request Info | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2933 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Plan Item | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2934 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Item (Object List) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2935 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Header) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2936 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Operation) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2937 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Attach Job Card | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2362 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - save data to APM DB | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3352 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - "Submit / Back" Button | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | GCP | EAPM-3448 | [BE][ASM][AssetStrategy] Sync all "ASM Strategies" to GCP | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | Migrate Data | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3445 | [FE][RCA] POC powerpoint | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline |  | rca
sap | sap | EAPM-3717 | [ASM] Update schema follow s4AHANA format | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
sap | cmms | EAPM-3727 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | improvement - MaintenancePlan | EAPM-1160 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - After Submit CMMS - Add logic Submit button | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3797 | [POC][FE][RCA] Logic Tree - Diagram | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline |  | rca
asm | improvement - RisksAndTasks | EAPM-3875 | [Improvement][ASM][FE] Abbreviate number when exceeding digit threshold | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | improvement - Overview | EAPM-4027 | [Improvement][ASM][BE] tuning performance Graph | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
sap | cmms | EAPM-4042 | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-3671 | [Improvement][AssetStrategy][CMMS] Add column “SCE Group” + Prefill Operation Short Text + Add K logic | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-3355 | [ASM][AssetStrategy][MaintenancePlans] Table List - Change Request No. - Hyperlink - modal Final, SG preview, related SG | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | Migrate Data | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms history log | EAPM-1316 | [ASM][AssetStrategy][CMMS] CMMS History Log - table + click button + Overview | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms history log | EAPM-2808 | [ASM][AssetStrategy][CMMS] CMMS History Log - Click Hyperlink - View CMMS Final Form Details | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms history log | EAPM-3926 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel (Submitted Final Form) | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms history log | EAPM-2809 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel Table View | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4289 | [RCA] Initial Layout | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3416 | [RCA][createNewAnalysis] modal input Case name >> save draft | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4296 | [RCA][Dashboard] RCA Analysis (All) - table list | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3420 | [RCA][createNewAnalysis] Common Header | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | asm | EAPM-1800 | [ASM][FE] Upgrade Version Angular | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | asm | EAPM-4447 | [ASM] Sustainable Tuning for support 2-3x or more data | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | moved | move to 28
sap | cmms | EAPM-4356 | [Improvement][SAP] change toast error message after submit CMMS | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
sap | cmms | EAPM-4355 | [Improvement][SAP] Error Handling from SAP response | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | moved | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-3407 | [RCA][createNewAnalysis] Team Member | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3408 | [RCA][createNewAnalysis] Case Background | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3409 | [RCA][createNewAnalysis] Problem Analysis | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3410 | [RCA][createNewAnalysis] Incident Timeline | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | moved | move to 29
asm | cmms | EAPM-4730 | [Improvement][ASM][CMMS] Submit CMMS - Add PackageNo not found page | 28 | 2026-05-18 | 2026-05-29 | 1 |  | added | add on
asm | cmms | EAPM-4731 | [Improvement][ASM][CMMS] Submit CMMS - Change logic field "Updated Field" | 28 | 2026-05-18 | 2026-05-29 | 1 |  | added | add on
asm | improvement - Revision | EAPM-3752 | [Improvement][ASM][AssetStrategy][Revision] disabled icon restore | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
asm | improvement - RisksAndTasks | EAPM-3898 | [Improvement][ASM][BE+FE] Abbreviate number when exceeding digit threshold | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis |  | [RCA][createNewAnalysis] Incident Timeline - Export PDF | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | removed | remove
asm | ai | EAPM-347 | [ASM][AssetStrategy][RisksAndTasks] Risk tap Details - Integrate AI Suggestion | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3411 | [RCA][createNewAnalysis] Finding | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | moved | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-3412 | [RCA][createNewAnalysis] Logic Tree | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Logic Tree - Box Details | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4516 | [RCA][createNewAnalysis] Logic Tree - Box Details - Actions | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Verification Action | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | split | breakdown 5217, move to sprint 30
rca | Case creation - Create/Edit Analysis | EAPM-4567 | [RCA][createNewAnalysis] Verification Action - Noti | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3414 | [RCA][createNewAnalysis] RCA Recommendations | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | split | breakdown 5234
rca | Case creation - Create/Edit Analysis | EAPM-3415 | [RCA][createNewAnalysis] Other Recommendations | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | split | breakdown 5235
rca | Case creation - Create/Edit Analysis | EAPM-4568 | [RCA][createNewAnalysis] Reference Document - Table 1 | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4569 | [RCA][createNewAnalysis] Reference Document - Table 2 | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | moved | move to backlog
sap | cmms | EAPM-5493 | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5158 | [Improvement][RCA][createNewAnalysis] change source of PTTEP Risk Matrix + Add last updated date | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5241 | [Improvement][RCA][createNewAnalysis] Verification Actions - Table List - allow assigned group email from azure + add column "Last Updated by" | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-5397 | [RCA] Sharepoint Structure | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5395 | [Improvement][RCA][createNewAnalysis] add asset when create new RCA + add validate input format "RCA Case Name" | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5434 | [Improvement][RCA][FE][createNewAnalysis] change save button name + change placeholder | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
asm | asm | EAPM-5572 | [ServerError] HTTP Status Error 5xx | 30 | 2026-06-15 | 2026-06-26 | 1 |  | added | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-3406 | [RCA][createNewAnalysis] Executive Summary | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | moved | move to sprint 30
rca | case approval | EAPM-5023 | [RCA][Approval Flow] Case Approval - Approval detail + progress - Fa view | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | moved | move to sprint 32
rca | case approval | EAPM-5237 | [RCA][Approval Flow] Case Approval - Approval detail + progress - approver view | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | moved | move to sprint 32
rca | Case creation - Create/Edit Analysis | EAPM-5812 | [Improvement][RCA][createNewAnalysis] Logic Tree - Main diagram | 31 | 2026-06-29 | 2026-07-10 | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM 5848 | [Improvement][RCA][createNewAnalysis] Add validation - Folder Name in Sharepoint | 31 | 2026-06-29 | 2026-07-10 | 1 |  | added | add on
rca | case approval | EAPM 5024 | [RCA][Approval Flow] Case Approval - Approval detail + progress - viewer | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 6178 | [RCA][Approval Flow] Case Approval - Approval Progress - Super User view | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 5847 | [RCA][Approval Flow] Case Approval - Approval History | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 5027 | [RCA][Approval Flow] Case Approval - Noti Email - Inform | 32 | 2026-07-13 | 2026-07-24 | 1 |  | moved | move to sprint 33
rca | Report | EAPM 5028 | [RCA] Export Report | 32 | 2026-07-13 | 2026-07-24 | 1 |  | moved | move to sprint 33
rca | case approval | EAPM-5022 | [RCA][Approval Flow] RCA Approval Tracking modal - Structure | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5026 | [RCA][Approval Flow] Case Status - Permission | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | User Management | EAPM-5059 | [RCA][UserManagement] Master Data Setting "RCA Type" | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5236 | [RCA][Approval Flow] Submit RCA Case - “Start Investigation” button | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | ai | EAPM-6028 | [RCA][createNewAnalysis] Executive Summary - Design Request/Response JSON for AI | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | User Management | EAPM-6231 | [RCA] Add Permission to all pages in RCA | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6367 | [RCA][Approval Flow] Submit RCA Case - Flow Start Investigation | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6368 | [RCA][Approval Flow] Submit RCA Case - Waiting Verification | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6369 | [RCA][Approval Flow] Submit RCA Case - Approve | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6370 | [RCA][Approval Flow] Submit RCA Case - Implementing Action and Complete | 32 | 2026-07-13 | 2026-07-24 | 1 |  | Split | breakdown to srpint 32
rca | Report | EAPM 5029 | [RCA] Export Report - ppt >> PDF | 33 | 2026-07-27 | 2026-08-07 | 1 | baseline
rca | RCA Dashboard. | EAPM-3417 | [RCA][createNewAnalysis] Dash Board - Graph | 33 | 2026-07-27 | 2026-08-07 | 1 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Analysis(All) | 33 | 2026-07-27 | 2026-08-07 | 1 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Verification (Pending) | 34 | 2026-08-10 | 2026-08-21 | 1 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Recommendation (Pending) | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Azure | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline | moved | move to sprint 31, breakerdown 5038, 5058
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - Add input setting | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline | moved | move to sprint 31, breakerdown 5056, 5057, 5036, 5037
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - display | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline | moved | move to sprint 31, breakdown 5034, 5035, 5020
rca | Noti Email |  | [RCA] Notification Email - Monthly 16th | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline
rca | Noti Email |  | [RCA] Notification Email - Monthly 1st | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #1 | 36 | 2026-09-07 | 2026-09-18 | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #2 | 37 | 2026-09-21 | 2026-10-02 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #1 | 38 | 2026-10-05 | 2026-10-16 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #2 | 39 | 2026-10-19 | 2026-10-30 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #3 | 40 | 2026-11-02 | 2026-11-13 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #4 | 41 | 2026-11-16 | 2026-11-27 | 0 | baseline
handover | Document |  | [Document] system and user manual, sonaqube result | 42 | 2026-11-30 | 2026-12-11 | 0 | baseline
handover | Knowledge Transfer |  | [KT] knowledge transfer | 43 | 2026-12-14 | 2026-12-25 | 0 | baseline
Formulas:
start = VLOOKUP([Sprint], [1]sprintday!$A6:C32, 2, FALSE())
end = VLOOKUP([Sprint], [1]sprintday!$A6:C32, 3, FALSE())

## sprintday (hidden)
| team velocity | 30 | story point/sprint
| full | 10 | working day/sprint
ref. holiday
Sprint | Start Date (Mon) | End Date (Fri) | Working Day | Est. Story Point | % Weight Resoure Sprint Utilize | Remark | Sprint | Average of % Weight Resoure Sprint Utilize
18 | 2026-01-05 | 2026-01-09 | 5 | 15 | 50% | half sprint | 18 | 50%
19 | 2026-01-12 | 2026-01-23 | 10 | 30 | 100% | full | 19 | 100%
20 | 2026-01-26 | 2026-02-06 | 10 | 30 | 100% | full | 20 | 100%
21 | 2026-02-09 | 2026-02-20 | 10 | 30 | 100% | full | 21 | 100%
22 | 2026-02-23 | 2026-03-06 | 9 | 27 | 90% | full | 22 | 90%
23 | 2026-03-09 | 2026-03-20 | 10 | 30 | 100% | full | 23 | 100%
24 | 2026-03-23 | 2026-04-03 | 10 | 30 | 100% | full | 24 | 100%
25 | 2026-04-06 | 2026-04-17 | 6 | 18 | 60% | full | 25 | 60%
26 | 2026-04-20 | 2026-05-01 | 9 | 27 | 90% | full | 26 | 90%
27 | 2026-05-04 | 2026-05-15 | 9 | 27 | 90% | full | 27 | 90%
28 | 2026-05-18 | 2026-05-29 | 10 | 30 | 100% | full | 28 | 100%
29 | 2026-06-01 | 2026-06-12 | 8 | 24 | 80% | full | 29 | 80%
30 | 2026-06-15 | 2026-06-26 | 10 | 30 | 100% | full | 30 | 100%
31 | 2026-06-29 | 2026-07-10 | 10 | 30 | 100% | full | 31 | 100%
32 | 2026-07-13 | 2026-07-24 | 10 | 30 | 100% | full | 32 | 100%
33 | 2026-07-27 | 2026-08-07 | 8 | 24 | 80% | full | 33 | 80%
34 | 2026-08-10 | 2026-08-21 | 9 | 27 | 90% | full | 34 | 90%
35 | 2026-08-24 | 2026-09-04 | 10 | 30 | 100% | full | 35 | 100%
36 | 2026-09-07 | 2026-09-18 | 10 | 30 | 100% | full | 36 | 100%
37 | 2026-09-21 | 2026-10-02 | 10 | 30 | 100% | full | 37 | 100%
38 | 2026-10-05 | 2026-10-16 | 9 | 27 | 90% | full | 38 | 90%
39 | 2026-10-19 | 2026-10-30 | 9 | 27 | 90% | full | 39 | 90%
40 | 2026-11-02 | 2026-11-13 | 10 | 30 | 100% | full | 40 | 100%
41 | 2026-11-16 | 2026-11-27 | 10 | 30 | 100% | full | 41 | 100%
42 | 2026-11-30 | 2026-12-11 | 9 | 27 | 90% | full | 42 | 90%
43 | 2026-12-14 | 2026-12-25 | 10 | 30 | 100% | full | 43 | 100%
44 | 2026-12-28 | 2027-01-08 | 9 | 27 | 90% | half sprint | 44 | 90%
[7 empty] | Grand Total | 92.22%
Formulas:
Working Day = NETWORKDAYS([Start Date (Mon)], [End Date (Fri)], holiday!$A2:A18)

## holiday (hidden)
Date | Holiday Name
2026-01-01 | New Year's Day
2026-03-03 | Makha Bucha Day
2026-04-06 | Chakri Memorial Day
2026-04-13 | Songkran
2026-04-14 | Songkran
2026-04-15 | Songkran
2026-05-01 | National Labor Day
2026-05-04 | Coronation Day
2026-06-01 | Sub. Visakha Bucha
2026-06-03 | Queen's Birthday
2026-07-28 | King's Birthday
2026-07-29 | Asarnha Bucha Day
2026-08-12 | Mother's Day
2026-10-13 | King Bhumibol Memorial
2026-10-23 | King Chulalongkorn Memorial
2026-12-07 | Sub. Father's Day
2026-12-31 | New Year's Eve

## baseline V3 (hidden)
Module | Feature Name | User Story ID | User Story Description | Sprint | start | end | Status (1=Done, 0=Progress) | Is Baseline | Change Record | note original | Module ¦ Feature ¦ Sprint
asm | revision | EAPM-906 | [Improvement][Home][GeneralDetails] My Tasks - Add checked Group Permission for Waiting for Approval Box. | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti | Module | Sprint | start | end | Feature Name | Count of User Story Description
asm | revision | EAPM-278 | [ASM][AssetStrategy] Email Notification Message - Template 2 (Review) | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti | asm |  |  |  |  | 90
asm | revision | EAPM-923 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Add Description for Failure Impact + Change Field Name | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti |  | 18 | 2026-01-05 | 2026-01-09 | revision | 8
asm | revision | EAPM-244 | [Improvement][ASM][AssetStrategy] Strategies Table List V3. - Add column | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | email noti |  | 19 | 2026-01-12 | 2026-01-23 | revision | 14
asm | revision | EAPM-922 | [ASM][AssetStrategy] Integrate FDP (GCP) - [BE] | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 20 | 2026-01-26 | 2026-02-06 | cmms | 14
asm | revision | EAPM-919 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk/Task Panel - Change Icon Yellow Alert to Arrow Icon + Abbreviate Interval + SCE Tag | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 21 | 2026-02-09 | 2026-02-20 | cmms | 8
asm | revision | EAPM-882 | [ASM] Apply a consistent design standard to all action buttons. [FE] | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  | 22 | 2026-02-23 | 2026-03-06 | ai | 7
asm | revision | EAPM-1071 | [Improvement][ASM][AssetStrategy] All Table List - Change Design the shown numbers as total, select items, filter results | 18 | 2026-01-05 | 2026-01-09 | 1 | baseline |  | integration |  |  |  |  | cmms | 4
asm | revision | EAPM-10 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 23 | 2026-03-09 |  |  | 7
asm | revision | EAPM-11 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 24 | 2026-03-23 | 2026-04-03 | cmms | 11
asm | revision | EAPM-7 | [ASM][AssetStrategy][Revisions] Revision Details - Risks and Tasks | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 25 | 2026-04-06 | 2026-04-17 | cmms | 5
asm | revision | EAPM-25 | [ASM][AssetStrategy][Revisions] Revision Details - Risks Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 26 | 2026-04-20 | 2026-05-01 | cmms | 6
asm | revision | EAPM-26 | [ASM][AssetStrategy][Revisions] Revision Details - Task Details | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | cmms | 5
asm | revision | EAPM-8 | [ASM][AssetStrategy][Revisions] Revision Details - Risk Analysis | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | ai | 1
asm | revision | EAPM-9 | [ASM][AssetStrategy][Revisions] Revision Details - Maintenance Plans | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  | rca |  |  |  |  | 57
asm | revision | EAPM-1255 | [ASM][AssetStrategy] Trigger an update for all data retrieved from GCP. (Location, FDP, Maintenance Plan, ...) | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | Case creation - Create/Edit Analysis | 6
asm | revision | EAPM-1302 | [Improvement][Home][GeneralDetails] My Task - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 28 | 2026-05-18 | 2026-05-29 | Case creation - Create/Edit Analysis | 10
asm | revision | EAPM-1303 | [Improvement][Admin] User Management - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | Case creation - Create/Edit Analysis | 7
asm | revision | EAPM-1304 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Maintenance Plan table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | Case creation - Create/Edit Analysis | 4 | asm
asm | revision | EAPM-1392 | [Improvement][ASM][AssetStrategy] Strategy Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 31 | 2026-06-29 | 2026-07-10 | case approval | 2 | rca
asm | revision | EAPM-1393 | [Improvement][ASM][AssetStrategy][Revision] Revision Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline | [6 empty] | Case creation - Create/Edit Analysis | 3 | ui improvement
asm | revision | EAPM-1394 | [Improvement][ASM][AssetStrategy][Overview] Risk Matrix by Active Strategy Table list - Apply standard design for table list | 19 | 2026-01-12 | 2026-01-23 | 1 | baseline |  |  |  | 32 | 2026-07-13 | 2026-07-24 | case approval | 14 | handover
asm | cmms | EAPM-1150 | [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-349 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #1 | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 33 | 2026-07-27 | 2026-08-07 | RCA Dashboard. | 2
asm | cmms | EAPM-1309 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #2 | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-2000 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add dropdown "Work Center" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 34 | 2026-08-10 | 2026-08-21 | RCA Dashboard. | 2
asm | cmms | EAPM-1999 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details V3. | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | User Management | 1
asm | cmms | EAPM-1585 | [Improvement][FE][ASM][RisksAndTasks] Risk Property - Add more suggestion to 3M, 6M, 12M, 18M, 24M | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 35 | 2026-08-24 | 2026-09-04 | Noti Email | 2
asm | cmms | EAPM-1883 | [Improvement][ASM][RisksAndTasks] - Risk Detail / Task Detail - Add more suggestion | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline | [6 empty] | User Management | 2
asm | cmms | EAPM-2003 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Change Logic | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  | handover |  |  |  |  | 2
asm | cmms | EAPM-2006 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details - Set default ROI to "-1" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 42 | 2026-11-30 | 2026-12-11 | Document | 1
asm | cmms | EAPM-2004 | [Improvement][ASM][AssetStrategy][SummaryDetails] Change default "Plant Length =20" | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 43 | 2026-12-14 | 2026-12-25 | Knowledge Transfer | 1
asm | cmms | EAPM-1314 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  | ui improvement |  |  |  |  | 6
asm | cmms | EAPM-599 | [ASM][AssetStrategy][MaintenancePlans] Table List - Submit Change Request Flow | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 36 | 2026-09-07 | 2026-09-18 | Requirement & Design | 1
asm | cmms | EAPM-1305 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 37 | 2026-09-21 | 2026-10-02 | Requirement & Design | 1
asm | cmms | EAPM-1799 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action - Export Excel | 20 | 2026-01-26 | 2026-02-06 | 1 | baseline |  |  |  | 38 | 2026-10-05 | 2026-10-16 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2423 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 39 | 2026-10-19 | 2026-10-30 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2487 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Converted interval value K = 000H | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 40 | 2026-11-02 | 2026-11-13 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-33 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (RequestInfo) #1 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 41 | 2026-11-16 | 2026-11-27 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1306 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #1 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  | (blank) |  |  |  |  | 7
asm | cmms | EAPM-1801 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #2 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | (blank) | 7
asm | cmms | EAPM-1955 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #3 | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  | Grand Total |  |  |  |  | 162
asm | cmms | EAPM-1307 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) - Add/Duplicate/Delete row | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline
asm | cmms | EAPM-2486 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Scale Bar - Icon U / M | 21 | 2026-02-09 | 2026-02-20 | 1 | baseline |  |  | Baseline user story
asm | ai | EAPM-1308 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (ObjectList) + Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | Module | Count of User Story Description
asm | ai | EAPM-1310 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #1 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | asm | 90
asm | ai | EAPM-1844 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #2 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | handover | 2
asm | ai | EAPM-1311 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | rca | 57
asm | ai | EAPM-1312 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #1 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | ui improvement | 6
asm | ai | EAPM-1845 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #2 | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | (blank) | 7
asm | ai | EAPM-1313 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add/Duplicate/Delete row | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline |  |  | Grand Total | 162
asm | cmms | EAPM-2745 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - CMMS Form(PreFilled) - MaintenancePlanItem - Case: Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2779 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2780 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add New Sub | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-2759 | [ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Request Sub." | 22 | 2026-02-23 | 2026-03-06 | 1 | baseline
asm | cmms | EAPM-1318 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (AttachJobCard) | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-32 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Initial + Before | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-1803 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - After | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2488 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Related Strategy | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2672 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Calculate Summary Interval | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2945 | [FE][POC][ASM][AssetStrategy][MaintenancePlan] POC CMMS Final Form - UI Screen + Export Excel | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2946 | [FE][Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Work Center" field | 23 | 2026-03-09 | 2026-03-20 | 1 | baseline
asm | cmms | EAPM-2007 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Initial + Request Info | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2933 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Plan Item | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2934 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Item (Object List) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2935 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Header) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2936 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Operation) | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2937 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Attach Job Card | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2362 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - save data to APM DB | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3352 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - "Submit / Back" Button | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3448 | [BE][ASM][AssetStrategy] Sync all "ASM Strategies" to GCP | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline
asm | cmms | EAPM-3445 | [FE][RCA] POC powerpoint | 24 | 2026-03-23 | 2026-04-03 | 1 | baseline |  | rca
asm | cmms | EAPM-3717 | [ASM] Update schema follow s4AHANA format | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-3727 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-1160 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - After Submit CMMS - Add logic Submit button | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-3797 | [POC][FE][RCA] Logic Tree - Diagram | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline |  | rca
asm | cmms | EAPM-3875 | [Improvement][ASM][FE] Abbreviate number when exceeding digit threshold | 25 | 2026-04-06 | 2026-04-17 | 1 | baseline
asm | cmms | EAPM-4027 | [Improvement][ASM][BE] tuning performance Graph | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-4042 | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-3671 | [Improvement][AssetStrategy][CMMS] Add column “SCE Group” + Prefill Operation Short Text + Add K logic | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-3355 | [ASM][AssetStrategy][MaintenancePlans] Table List - Change Request No. - Hyperlink - modal Final, SG preview, related SG | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 26 | 2026-04-20 | 2026-05-01 | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-1316 | [ASM][AssetStrategy][CMMS] CMMS History Log - table + click button + Overview | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-2808 | [ASM][AssetStrategy][CMMS] CMMS History Log - Click Hyperlink - View CMMS Final Form Details | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-3926 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel (Submitted Final Form) | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
asm | cmms | EAPM-2809 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel Table View | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4289 | [RCA] Initial Layout | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3416 | [RCA][createNewAnalysis] modal input Case name >> save draft | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4296 | [RCA][Dashboard] RCA Analysis (All) - table list | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3420 | [RCA][createNewAnalysis] Common Header | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-1800 | [ASM][FE] Upgrade Version Angular | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4447 | [ASM] Sustainable Tuning for support 2-3x or more data | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-4356 | [Improvement][SAP] change toast error message after submit CMMS | 27 | 2026-05-04 | 2026-05-15 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4355 | [Improvement][SAP] Error Handling from SAP response | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-3407 | [RCA][createNewAnalysis] Team Member | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3408 | [RCA][createNewAnalysis] Case Background | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3409 | [RCA][createNewAnalysis] Problem Analysis | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3410 | [RCA][createNewAnalysis] Incident Timeline | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-4730 | [Improvement][ASM][CMMS] Submit CMMS - Add PackageNo not found page | 28 | 2026-05-18 | 2026-05-29 | 1 | add on | add on
rca | Case creation - Create/Edit Analysis | EAPM-4731 | [Improvement][ASM][CMMS] Submit CMMS - Change logic field "Updated Field" | 28 | 2026-05-18 | 2026-05-29 | 1 | add on | add on
rca | Case creation - Create/Edit Analysis | EAPM-3752 | [Improvement][ASM][AssetStrategy][Revision] disabled icon restore | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3898 | [Improvement][ASM][BE+FE] Abbreviate number when exceeding digit threshold | 28 | 2026-05-18 | 2026-05-29 | 1 | baseline
rca | Case creation - Create/Edit Analysis |  | [RCA][createNewAnalysis] Incident Timeline - Export PDF | 28 | 2026-05-18 | 2026-05-29 | 1 | remove | remove
asm | ai | EAPM-347 | [ASM][AssetStrategy][RisksAndTasks] Risk tap Details - Integrate AI Suggestion | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3411 | [RCA][createNewAnalysis] Finding | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-3412 | [RCA][createNewAnalysis] Logic Tree | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Logic Tree - Box Details | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4516 | [RCA][createNewAnalysis] Logic Tree - Box Details - Actions | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Verification Action | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline | bread down 5217, move to sprint 30
rca | Case creation - Create/Edit Analysis | EAPM-4567 | [RCA][createNewAnalysis] Verification Action - Noti | 29 | 2026-06-01 | 2026-06-12 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3414 | [RCA][createNewAnalysis] RCA Recommendations | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | breakdown 5234
rca | Case creation - Create/Edit Analysis | EAPM-3415 | [RCA][createNewAnalysis] Other Recommendations | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | breakdown 5235
rca | Case creation - Create/Edit Analysis | EAPM-4568 | [RCA][createNewAnalysis] Reference Document - Table 1 | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4569 | [RCA][createNewAnalysis] Reference Document - Table 2 | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | move to backlog
|  | EAPM-5493 | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
|  | EAPM-5158 | [Improvement][RCA][createNewAnalysis] change source of PTTEP Risk Matrix + Add last updated date | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
|  | EAPM-5241 | [Improvement][RCA][createNewAnalysis] Verification Actions - Table List - allow assigned group email from azure + add column "Last Updated by" | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
|  | EAPM-5397 | [RCA] Sharepoint Structure | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
|  | EAPM-5395 | [Improvement][RCA][createNewAnalysis] add asset when create new RCA + add validate input format "RCA Case Name" | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
|  | EAPM-5434 | [Improvement][RCA][FE][createNewAnalysis] change save button name + change placeholder | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
|  | EAPM-5572 | [ServerError] HTTP Status Error 5xx | 30 | 2026-06-15 | 2026-06-26 | 1 | baseline | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-3406 | [RCA][createNewAnalysis] Executive Summary | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | move to sprint 30
rca | case approval | EAPM-5023 | [RCA][Approval Flow] Case Approval - Approval detail + progress - Fa view | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | move to sprint 32
rca | case approval | EAPM-5237 | [RCA][Approval Flow] Case Approval - Approval detail + progress - approver view | 31 | 2026-06-29 | 2026-07-10 | 1 | baseline | move to sprint 32
rca | Case creation - Create/Edit Analysis | EAPM-5812 | [Improvement][RCA][createNewAnalysis] Logic Tree - Main diagram | 31 | 2026-06-29 | 2026-07-10 | 1 |  | add-on
rca | Case creation - Create/Edit Analysis | EAPM 5848 | [Improvement][RCA][createNewAnalysis] Add validation - Folder Name in Sharepoint | 31 | 2026-06-29 | 2026-07-10 | 1 |  | add-on
rca | case approval | EAPM 5024 | [RCA][Approval Flow] Case Approval - Approval detail + progress - viewer | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 6178 | [RCA][Approval Flow] Case Approval - Approval Progress - Super User view | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 5847 | [RCA][Approval Flow] Case Approval - Approval History | 32 | 2026-07-13 | 2026-07-24 | 1 | baseline
rca | case approval | EAPM 5027 | [RCA][Approval Flow] Case Approval - Noti Email - Inform | 32 | 2026-07-13 | 2026-07-24 | 1 |  | move to sprint 33
rca | Report | EAPM 5028 | [RCA] Export Report | 32 | 2026-07-13 | 2026-07-24 | 1 |  | move to sprint 33
rca | case approval | EAPM-5022 | [RCA][Approval Flow] RCA Approval Tracking modal - Structure | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-5026 | [RCA][Approval Flow] Case Status - Permission | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-5059 | [RCA][UserManagement] Master Data Setting "RCA Type" | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-5236 | [RCA][Approval Flow] Submit RCA Case - “Start Investigation” button | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6028 | [RCA][createNewAnalysis] Executive Summary - Design Request/Response JSON for AI | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6231 | [RCA] Add Permission to all pages in RCA | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6367 | [RCA][Approval Flow] Submit RCA Case - Flow Start Investigation | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6368 | [RCA][Approval Flow] Submit RCA Case - Waiting Verification | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6369 | [RCA][Approval Flow] Submit RCA Case - Approve | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6370 | [RCA][Approval Flow] Submit RCA Case - Implementing Action and Complete | 32 | 2026-07-13 | 2026-07-24 | 1 |  | breakdown to srpint 32
rca | Report | EAPM 5029 | [RCA] Export Report - ppt >> PDF | 33 | 2026-07-27 | 2026-08-07 | 0 | baseline
rca | RCA Dashboard. | EAPM-3417 | [RCA][createNewAnalysis] Dash Board - Graph | 33 | 2026-07-27 | 2026-08-07 | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Analysis(All) | 33 | 2026-07-27 | 2026-08-07 | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Verification (Pending) | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Recommendation (Pending) | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Azure | 34 | 2026-08-10 | 2026-08-21 | 0 | baseline | move to sprint 31, breakerdown 5038, 5058
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - Add input setting | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline | move to sprint 31, breakerdown 5056, 5057, 5036, 5037
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - display | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline | move to sprint 31, breakdown 5034, 5035, 5020
rca | Noti Email |  | [RCA] Notification Email - Monthly 16th | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline
rca | Noti Email |  | [RCA] Notification Email - Monthly 1st | 35 | 2026-08-24 | 2026-09-04 | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #1 | 36 | 2026-09-07 | 2026-09-18 | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #2 | 37 | 2026-09-21 | 2026-10-02 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #1 | 38 | 2026-10-05 | 2026-10-16 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #2 | 39 | 2026-10-19 | 2026-10-30 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #3 | 40 | 2026-11-02 | 2026-11-13 | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #4 | 41 | 2026-11-16 | 2026-11-27 | 0 | baseline
handover | Document |  | [Document] system and user manual, sonaqube result | 42 | 2026-11-30 | 2026-12-11 | 0 | baseline
handover | Knowledge Transfer |  | [KT] knowledge transfer | 43 | 2026-12-14 | 2026-12-25 | 0 | baseline
Formulas:
start = VLOOKUP([Sprint], sprintday!$A6:C32, 2, FALSE)
end = VLOOKUP([Sprint], sprintday!$A6:C32, 3, FALSE)