## dashboard v1 (hidden)
Baseline VS Activity
Activity

## Baseline V1 (hidden)
Actual | [7 empty] | Year 2026
Plan | [7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
Varience | [7 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
[8 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
module | feature | story id | start | end | sprint no. | % plan | % actual
MVP1 | User Authentication | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100%
|  | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100%
|  | S2: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  | 100%
| Task Management | S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  | 100%
|  | S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  | 100%
|  | S3: Due Date Reminders | 2026-03-02 | 2026-03-13 | Sprint 5 |  | 100%
|  | S4: Task Archiving | 2026-03-16 | 2026-03-27 | Sprint 6 |  | 100%
MVP2 | Calendar Integration | S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  | 100%
|  | S2: Drag-and-Drop Scheduling | 2026-04-20 | 2026-05-01 | Sprint 8 |  | 100%
|  | S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  | 20%
| Progress Tracking | S1: Daily Progress Dashboard | 2026-05-18 | 2026-05-29 | Sprint 10 |  | 10%
|  | S2: Weekly Productivity Reports | 2026-06-01 | 2026-06-12 | Sprint 11 |  | 10%
|  | S3: Streak/Gamification | 2026-06-15 | 2026-06-26 | Sprint 12 |  | 0%
Ph3 | Collaboration | S1: Shared Task Lists | 2026-07-06 | 2026-07-17 | Sprint 13 |  | 0%
|  | S2: Team Comments/Mentions | 2026-07-20 | 2026-07-31 | Sprint 14 |  | 0%
|  | S3: Role-based Permissions | 2026-08-03 | 2026-08-14 | Sprint 15 |  | 0%
| Advanced Tools | S1: Pomodoro Timer | 2026-08-17 | 2026-08-28 | Sprint 16 |  | 0%
|  | S2: Focus Mode | 2026-08-31 | 2026-09-11 | Sprint 17 |  | 0%
QA/Go-Live | Final Stabilization | S1: UAT & Bug Fixing | 2026-10-05 | 2026-10-16 | Sprint 20 |  | 0%
|  | S2: Performance Tuning | 2026-10-19 | 2026-10-30 | Sprint 21 |  | 0%
|  | S3: Deployment & Go-Live | 2026-11-02 | 2026-11-13 | Sprint 22 |  | 0%
| Post-Launch | S1: Maintenance & Feedback | 2026-11-16 | 2026-12-25 | Sprint 23-25 |  | 0%

## Baseline V2 (hidden)
Actual | [7 empty] | Year 2026
Plan | [7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
Varience | [7 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
[8 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
module | feature | story id | start | end | sprint no. | % plan | % actual
MVP1 |  |  | 2026-01-05 | 2026-03-27 |  |  | 100%
| User Authentication |  | 2026-01-05 | 2026-01-30 |  | 100% | 100%
|  | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100%
|  | S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  | 100%
|  | S2: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  | 100%
| Task Management |  | 2026-02-02 | 2026-03-27 |  | 49% | 50%
|  | S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  | 50%
|  | S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  | 50%
|  | S3: Due Date Reminders | 2026-03-02 | 2026-03-13 | Sprint 5 |  | 50%
|  | S4: Task Archiving | 2026-03-16 | 2026-03-27 | Sprint 6 |  | 50%
MVP2 |  |  | 2026-04-06 | 2026-06-26
| Calendar Integration |  | 2026-04-06 | 2026-05-15
|  | S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  | 100%
|  | S2: Drag-and-Drop Scheduling | 2026-04-20 | 2026-05-01 | Sprint 8 |  | 100%
|  | S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  | 9%
| Progress Tracking |  | 2026-05-18 | 2026-06-26
|  | S1: Daily Progress Dashboard | 2026-05-18 | 2026-05-29 | Sprint 10 |  | 0%
|  | S2: Weekly Productivity Reports | 2026-06-01 | 2026-06-12 | Sprint 11 |  | 0%
|  | S3: Streak/Gamification | 2026-06-15 | 2026-06-26 | Sprint 12 |  | 0%

## Master Plan V1 (hidden)
Project Actual:
Project Plan:
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual
MVP1: ASM |  | 2026-01-05 | 2026-03-27 | Ongoing | Green
CMMS |  | 2026-01-05 | 2026-01-30 |  | Green
| S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  |  | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  |  | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  |  | 100%
AI |  | 2026-02-02 | 2026-03-27 |  | Green
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  |  | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  |  | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 | Upcoming | Green
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  | Green
| S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  |  | 100%
| S2: Drag-and-Drop | 2026-04-20 | 2026-05-01 | Sprint 8 |  |  | 100%
| S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  |  | 9%

## Master Plan V2 (hidden)
Project Actual:
Project Plan:
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual
MVP1: ASM |  | 2026-01-05 | 2026-03-27 | Ongoing | Green
CMMS |  | 2026-01-05 | 2026-01-30 |  | Green
| S1: Login/Signup | 2026-01-05 | 2026-01-16 | Sprint 1 |  |  | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  |  | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  |  | 100%
AI |  | 2026-02-02 | 2026-03-27 |  | Green
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  |  | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  |  | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 | Upcoming | Green
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  | Green
| S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  |  | 100%
| S2: Drag-and-Drop | 2026-04-20 | 2026-05-01 | Sprint 8 |  |  | 100%
| S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  |  | 9%

## master Plan V3 (hidden)
Project Actual: |  |  | Project start | 2026-01-05 |  |  |  | Year 2026
Project Plan: | [7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[8 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
[8 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
MVP1: ASM |  | 2026-01-05 | 2026-03-27 |  | Green
CMMS |  | 2026-01-05 | 2026-01-30 |  | Green
| S1: Login/Signup | 2026-01-05 | 2026-01-17 | Sprint 1 |  |  | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  |  | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  |  | 100%
AI |  | 2026-02-02 | 2026-03-27 |  | Green
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  |  | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  |  | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26 |  | Green
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15 |  | Green
| S1: Sync Google/Outlook | 2026-04-06 | 2026-04-17 | Sprint 7 |  |  | 100%
| S2: Drag-and-Drop | 2026-04-20 | 2026-05-01 | Sprint 8 |  |  | 100%
| S3: Conflict Detection | 2026-05-04 | 2026-05-15 | Sprint 9 |  |  | 9%

## master plan V4 (hidden)
Project Actual: |  |  | Project start | 2026-01-05 |  |  |  | Year 2026
Project Plan: | [7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[8 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
[8 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43
Module / Feature | Task / Story ID | Start | End | Sprint | Health | % Plan | % Actual | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
MVP1: ASM |  | 2026-01-05 | 2026-03-27 |  | Category
CMMS |  | 2026-01-05 | 2026-01-30
| S1: Login/Signup | 2026-01-05 | 2026-01-17 | Sprint 1 |  |  | 100%
| S2: Home Page | 2026-01-05 | 2026-01-16 | Sprint 1 |  |  | 100%
| S3: Profile Management | 2026-01-19 | 2026-01-30 | Sprint 2 |  |  | 100%
AI |  | 2026-02-02 | 2026-03-27
| S1: Create/Edit Tasks | 2026-02-02 | 2026-02-13 | Sprint 3 |  |  | 100%
| S2: Priority Labeling | 2026-02-16 | 2026-02-27 | Sprint 4 |  |  | 100%
MVP2: RCA |  | 2026-04-06 | 2026-06-26
Case creation - Create/Edit Analysis |  | 2026-04-06 | 2026-05-15
| [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 2026-04-06 | 2026-04-17 | Sprint 7 |  |  | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 2026-04-20 | 2026-05-01 | Sprint 8 |  |  | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 2026-05-04 | 2026-05-15 | Sprint 9 |  |  | 10%
Additional Requirement |  | 2026-04-06 | 2026-05-15
| [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 2026-04-20 | 2026-05-01 | Sprint 1 |  |  | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 2026-05-04 | 2026-05-15 | Sprint 1 |  |  | 100%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 2026-04-20 | 2026-05-01 | Sprint 2 |  |  | 0%
| [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 2026-06-03 | 2026-06-30 | Sprint 9 |  |  | 10%

## master plan V5 (hidden)
Project Plan: |  | Project start: | 2026-01-05
Project Actual: |  | Project end: | 2026-05-15 | [5 empty] | Year 2026
[9 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[9 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
[9 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
Module | Feature | Start | End | Sprint | Working Day | % Plan | % Actual | status | Jan 5 W1: sp18; Jan 12 W2: sp19; Jan 26 W4: sp20; Feb 9 W6: sp21; Feb 23 W8: sp22; Mar 9 W10: sp23; Mar 23 W12: sp24; Apr 6 W14: sp25; Apr 20 W16: sp26; May 4 W18: sp27; May 18 W20: sp28; Jun 1 W22: sp29; Jun 15 W24: sp30; Jun 29 W26: sp31; Jul 13 W28: sp32; Jul 27 W30: sp33; Aug 10 W32: sp34; Aug 24 W34: sp35; Sep 7 W36: sp36; Sep 21 W38: sp37; Oct 5 W40: sp38; Oct 19 W42: sp39; Nov 2 W44: sp40; Nov 16 W46: sp41; Nov 30 W48: sp42; Dec 14 W50: sp43; Dec 28 W52: sp44
MVP1: ASM
| feature a | 2026-01-05 | 2026-01-23 | 18-19 |  |  |  | completed
| feature b | 2026-01-26 | 2026-02-20 | 20-21 |  |  |  | completed
| feature c | 2026-01-26 | 2026-02-20 | 20-21 |  |  |  | completed
MVP2: RCA
| feature d | 2026-02-09 | 2026-03-20 | 21-23 |  |  |  | completed
| feature d | 2026-03-23 | 2026-04-17 | 23-25 |  |  |  | completed
| feature e | 2026-04-20 | 2026-05-15 | 25-26 |  |  |  | in progress
Formulas:
Working Day = NETWORKDAYS([Start], [End], holiday!$A2:A18)

## Requirement Baseline v5 (hidden)
Module | Feature Name | User Story ID | Sprint | Status (1=Done, 0=Progress)
ASM | feature A | us1 | 18 | 1
ASM | feature A | us2 | 18 | 1
ASM | feature A | us3 | 19 | 1
ASM | feature B | us1 | 20 | 1
ASM | feature B | us2 | 21 | 1
ASM | feature B | us3 | 21 | 1
RCA | feature C | us1 | 21 | 1
RCA | feature C | us2 | 22 | 1
RCA | feature C | us3 | 23 | 1
RCA | feature D | us1 | 23 | 1
RCA | feature D | us2 | 24 | 1
RCA | feature D | us3 | 25 | 1
RCA | feature E | us1 | 25 | 1
RCA | feature E | us2 | 25 | 1
RCA | feature E | us3 | 26 | 0

## master plan v6 (hidden)
Project Plan: |  | Project start: | 2026-01-05
Project Actual: |  | Project end: | [7 empty] | Year 2026
|  | Baseline: | [7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[10 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
[10 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43 |  | sp44
Module | Feature | Start | End | Sprint | % Weight | Working Day | % Plan | % Actual | status
MVP1: ASM+AI
| Revision | 2026-01-05 | 2026-01-23 | 18-19 | 75%
| CMMS | 2026-01-26 | 2026-05-15 | 20-27 | 91%
| AI | 2026-02-23 | 2026-03-06 | 22 | 90%
MVP2: RCA
| Case Creation - Create/Edit Analysis | 2026-05-04 | 2026-07-10 | 27-31 | 94%
| Case Approval | 2026-06-29 | 2026-07-24 | 31-32 | 100%
| Report | 2026-07-13 | 2026-08-07 | 32-33 | 90%
| RCA Dashboard. | 2026-07-27 | 2026-08-21 | 33-34 | 85%
| User Management | 2026-08-10 | 2026-09-04 | 34-35 | 95%
| Noti Email | 2026-08-24 | 2026-09-04 | 35 | 100%
UI Improvement
| Requirement & Design | 2026-09-07 | 2026-10-02 | 36-37 | 100%
| Implementation, Testing, and Deploy | 2026-10-05 | 2026-11-27 | 38-41 | 100%
Handover
| Document | 2026-11-30 | 2026-12-11 | 42 | 100%
| Knowledge Transfer | 2026-12-14 | 2026-12-25 | 43 | 100%
Assumption:
1) the project plan based on the requirement baseline sheet "baseline"
2) additional improvement and scope can be discussed in terms of trade-off OR additional requirement
3) the actual % is weighted by working days, excluding holidays
Formulas:
Working Day = NETWORKDAYS([Start], [End], holiday!$A2:A18)

## master plan bk1 (hidden)
Project Plan: |  | Project start: | 2026-01-05 |  | Baseline
Project Actual: |  | Project end: | [7 empty] | Year 2026
|  | total user story: | [7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[10 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
[10 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43 |  | sp44
Module | Feature | Start | End | Sprint | % Weight | Working Day | % Plan | % Actual | status
MVP1: ASM+AI
| Revision | 2026-01-05 | 2026-01-23 | 18-19 | 75% |  |  |  | completed
| CMMS | 2026-01-26 | 2026-05-15 | 20-27 | 91% |  |  |  | completed
| AI | 2026-02-23 | 2026-03-06 | 22 | 90% |  |  |  | completed
MVP2: RCA
| Case Creation - Create/Edit Analysis | 2026-05-04 | 2026-07-10 | 27-31 | 94% |  |  |  | completed
| Case Approval | 2026-06-29 | 2026-07-24 | 31-32 | 100% |  |  |  | in progress
| Report | 2026-07-13 | 2026-08-07 | 32-33 | 90% |  |  |  | in progress
| RCA Dashboard. | 2026-07-27 | 2026-08-21 | 33-34 | 85% |  |  |  | in progress
| User Management | 2026-08-10 | 2026-09-04 | 34-35 | 95% |  |  |  | in progress
| Noti Email | 2026-08-24 | 2026-09-04 | 35 | 100% |  |  |  | in progress
UI Improvement | bar: Sep W36 to Oct W43
Analysis
Estimation
Implementation
Handover | bar: Nov W44 to Nov W47
Documentation
Knowledge transfer
Formulas:
Working Day = NETWORKDAYS([Start], [End], holiday!$A2:A18)

## baseline v4 (hidden)
Module | Feature Name | User Story ID | User Story Description | Sprint | start | end | Status (1=Done, 0=Progress) | Is Baseline | Change Type | Note | Module ¦ Feature ¦ Sprint | [5 empty] | Baseline vs change record
asm | revision | EAPM-906 | [Improvement][Home][GeneralDetails] My Tasks - Add checked Group Permission for Waiting for Approval Box. | 18 |  |  | 1 | baseline |  | email noti | Module | Sprint | start | end | Feature Name | Count of User Story Description | Module | Count of Is Baseline
asm | revision | EAPM-278 | [ASM][AssetStrategy] Email Notification Message - Template 2 (Review) | 18 |  |  | 1 | baseline |  | email noti | asm |  |  |  |  | 90 | asm | 90
asm | revision | EAPM-923 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Add Description for Failure Impact + Change Field Name | 18 |  |  | 1 | baseline |  | email noti |  | 18 | 2026-01-05 | 2026-01-09 | revision | 8 | handover | 2
asm | revision | EAPM-244 | [Improvement][ASM][AssetStrategy] Strategies Table List V3. - Add column | 18 |  |  | 1 | baseline |  | email noti |  | 19 | 2026-01-12 | 2026-01-23 | revision | 14 | rca | 41
asm | revision | EAPM-922 | [ASM][AssetStrategy] Integrate FDP (GCP) - [BE] | 18 |  |  | 1 | baseline |  | integration |  | 20 | 2026-01-26 | 2026-02-06 | cmms | 14 | ui improvement | 6
asm | revision | EAPM-919 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk/Task Panel - Change Icon Yellow Alert to Arrow Icon + Abbreviate Interval + SCE Tag | 18 |  |  | 1 | baseline |  | integration |  | 21 | 2026-02-09 | 2026-02-20 | cmms | 8 | Grand Total | 139
asm | revision | EAPM-882 | [ASM] Apply a consistent design standard to all action buttons. [FE] | 18 |  |  | 1 | baseline |  | integration |  | 22 | 2026-02-23 | 2026-03-06 | ai | 7
asm | revision | EAPM-1071 | [Improvement][ASM][AssetStrategy] All Table List - Change Design the shown numbers as total, select items, filter results | 18 |  |  | 1 | baseline |  | integration |  |  |  |  | cmms | 4
asm | revision | EAPM-10 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 19 |  |  | 1 | baseline |  |  |  | 23 | 2026-03-09 |  |  | 7
asm | revision | EAPM-11 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 19 |  |  | 1 | baseline |  |  |  | 24 | 2026-03-23 | 2026-04-03 | cmms | 11
asm | revision | EAPM-7 | [ASM][AssetStrategy][Revisions] Revision Details - Risks and Tasks | 19 |  |  | 1 | baseline |  |  |  | 25 | 2026-04-06 | 2026-04-17 | cmms | 5
asm | revision | EAPM-25 | [ASM][AssetStrategy][Revisions] Revision Details - Risks Details | 19 |  |  | 1 | baseline |  |  |  | 26 | 2026-04-20 | 2026-05-01 | cmms | 6
asm | revision | EAPM-26 | [ASM][AssetStrategy][Revisions] Revision Details - Task Details | 19 |  |  | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | cmms | 5
asm | revision | EAPM-8 | [ASM][AssetStrategy][Revisions] Revision Details - Risk Analysis | 19 |  |  | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | ai | 1
asm | revision | EAPM-9 | [ASM][AssetStrategy][Revisions] Revision Details - Maintenance Plans | 19 |  |  | 1 | baseline |  |  | rca |  |  |  |  | 57
asm | revision | EAPM-1255 | [ASM][AssetStrategy] Trigger an update for all data retrieved from GCP. (Location, FDP, Maintenance Plan, ...) | 19 |  |  | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | Case creation - Create/Edit Analysis | 6
asm | revision | EAPM-1302 | [Improvement][Home][GeneralDetails] My Task - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 28 | 2026-05-18 | 2026-05-29 | Case creation - Create/Edit Analysis | 10
asm | revision | EAPM-1303 | [Improvement][Admin] User Management - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | Case creation - Create/Edit Analysis | 7
asm | revision | EAPM-1304 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Maintenance Plan table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | Case creation - Create/Edit Analysis | 4
asm | revision | EAPM-1392 | [Improvement][ASM][AssetStrategy] Strategy Table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 31 | 2026-06-29 | 2026-07-10 | case approval | 2
asm | revision | EAPM-1393 | [Improvement][ASM][AssetStrategy][Revision] Revision Table list - Apply standard design for table list | 19 |  |  | 1 | baseline | [6 empty] | Case creation - Create/Edit Analysis | 3
asm | revision | EAPM-1394 | [Improvement][ASM][AssetStrategy][Overview] Risk Matrix by Active Strategy Table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 32 | 2026-07-13 | 2026-07-24 | case approval | 14
asm | cmms | EAPM-1150 | [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 20 |  |  | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-349 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #1 | 20 |  |  | 1 | baseline |  |  |  | 33 | 2026-07-27 | 2026-08-07 | RCA Dashboard. | 2
asm | cmms | EAPM-1309 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #2 | 20 |  |  | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-2000 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add dropdown "Work Center" | 20 |  |  | 1 | baseline |  |  |  | 34 | 2026-08-10 | 2026-08-21 | RCA Dashboard. | 2
asm | cmms | EAPM-1999 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details V3. | 20 |  |  | 1 | baseline | [6 empty] | User Management | 1
asm | cmms | EAPM-1585 | [Improvement][FE][ASM][RisksAndTasks] Risk Property - Add more suggestion to 3M, 6M, 12M, 18M, 24M | 20 |  |  | 1 | baseline |  |  |  | 35 | 2026-08-24 | 2026-09-04 | Noti Email | 2
asm | cmms | EAPM-1883 | [Improvement][ASM][RisksAndTasks] - Risk Detail / Task Detail - Add more suggestion | 20 |  |  | 1 | baseline | [6 empty] | User Management | 2
asm | cmms | EAPM-2003 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Change Logic | 20 |  |  | 1 | baseline |  |  | handover |  |  |  |  | 2
asm | cmms | EAPM-2006 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details - Set default ROI to "-1" | 20 |  |  | 1 | baseline |  |  |  | 42 | 2026-11-30 | 2026-12-11 | Document | 1
asm | cmms | EAPM-2004 | [Improvement][ASM][AssetStrategy][SummaryDetails] Change default "Plant Length =20" | 20 |  |  | 1 | baseline |  |  |  | 43 | 2026-12-14 | 2026-12-25 | Knowledge Transfer | 1
asm | cmms | EAPM-1314 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | 20 |  |  | 1 | baseline |  |  | ui improvement |  |  |  |  | 6
asm | cmms | EAPM-599 | [ASM][AssetStrategy][MaintenancePlans] Table List - Submit Change Request Flow | 20 |  |  | 1 | baseline |  |  |  | 36 | 2026-09-07 | 2026-09-18 | Requirement & Design | 1
asm | cmms | EAPM-1305 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action | 20 |  |  | 1 | baseline |  |  |  | 37 | 2026-09-21 | 2026-10-02 | Requirement & Design | 1
asm | cmms | EAPM-1799 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action - Export Excel | 20 |  |  | 1 | baseline |  |  |  | 38 | 2026-10-05 | 2026-10-16 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2423 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | 21 |  |  | 1 | baseline |  |  |  | 39 | 2026-10-19 | 2026-10-30 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2487 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Converted interval value K = 000H | 21 |  |  | 1 | baseline |  |  |  | 40 | 2026-11-02 | 2026-11-13 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-33 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (RequestInfo) #1 | 21 |  |  | 1 | baseline |  |  |  | 41 | 2026-11-16 | 2026-11-27 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1306 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #1 | 21 |  |  | 1 | baseline |  |  | (blank) |  |  |  |  | 7
asm | cmms | EAPM-1801 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #2 | 21 |  |  | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | (blank) | 7
asm | cmms | EAPM-1955 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #3 | 21 |  |  | 1 | baseline |  |  | Grand Total |  |  |  |  | 162
asm | cmms | EAPM-1307 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) - Add/Duplicate/Delete row | 21 |  |  | 1 | baseline
asm | cmms | EAPM-2486 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Scale Bar - Icon U / M | 21 |  |  | 1 | baseline
asm | ai | EAPM-1308 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (ObjectList) + Add/Duplicate/Delete row | 22 |  |  | 1 | baseline
asm | ai | EAPM-1310 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #1 | 22 |  |  | 1 | baseline
asm | ai | EAPM-1844 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #2 | 22 |  |  | 1 | baseline
asm | ai | EAPM-1311 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add/Duplicate/Delete row | 22 |  |  | 1 | baseline
asm | ai | EAPM-1312 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #1 | 22 |  |  | 1 | baseline
asm | ai | EAPM-1845 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #2 | 22 |  |  | 1 | baseline
asm | ai | EAPM-1313 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add/Duplicate/Delete row | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2745 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - CMMS Form(PreFilled) - MaintenancePlanItem - Case: Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2779 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2780 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2759 | [ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Request Sub." | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1318 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (AttachJobCard) | 23 |  |  | 1 | baseline
asm | cmms | EAPM-32 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Initial + Before | 23 |  |  | 1 | baseline
asm | cmms | EAPM-1803 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - After | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2488 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Related Strategy | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2672 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Calculate Summary Interval | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2945 | [FE][POC][ASM][AssetStrategy][MaintenancePlan] POC CMMS Final Form - UI Screen + Export Excel | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2946 | [FE][Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Work Center" field | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2007 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Initial + Request Info | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2933 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Plan Item | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2934 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Item (Object List) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2935 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Header) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2936 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Operation) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2937 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Attach Job Card | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2362 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - save data to APM DB | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3352 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - "Submit / Back" Button | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3448 | [BE][ASM][AssetStrategy] Sync all "ASM Strategies" to GCP | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3445 | [FE][RCA] POC powerpoint | 24 |  |  | 1 | baseline |  | rca
asm | cmms | EAPM-3717 | [ASM] Update schema follow s4AHANA format | 25 |  |  | 1 | baseline
asm | cmms | EAPM-3727 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | 25 |  |  | 1 | baseline
asm | cmms | EAPM-1160 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - After Submit CMMS - Add logic Submit button | 25 |  |  | 1 | baseline
asm | cmms | EAPM-3797 | [POC][FE][RCA] Logic Tree - Diagram | 25 |  |  | 1 | baseline |  | rca
asm | cmms | EAPM-3875 | [Improvement][ASM][FE] Abbreviate number when exceeding digit threshold | 25 |  |  | 1 | baseline
asm | cmms | EAPM-4027 | [Improvement][ASM][BE] tuning performance Graph | 26 |  |  | 1 | baseline
asm | cmms | EAPM-4042 | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | 26 |  |  | 1 | baseline
asm | cmms | EAPM-3671 | [Improvement][AssetStrategy][CMMS] Add column “SCE Group” + Prefill Operation Short Text + Add K logic | 26 |  |  | 1 | baseline
asm | cmms | EAPM-3355 | [ASM][AssetStrategy][MaintenancePlans] Table List - Change Request No. - Hyperlink - modal Final, SG preview, related SG | 26 |  |  | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 26 |  |  | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 26 |  |  | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 27 |  |  | 1 | baseline
asm | cmms | EAPM-1316 | [ASM][AssetStrategy][CMMS] CMMS History Log - table + click button + Overview | 27 |  |  | 1 | baseline
asm | cmms | EAPM-2808 | [ASM][AssetStrategy][CMMS] CMMS History Log - Click Hyperlink - View CMMS Final Form Details | 27 |  |  | 1 | baseline
asm | cmms | EAPM-3926 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel (Submitted Final Form) | 27 |  |  | 1 | baseline
asm | cmms | EAPM-2809 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel Table View | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4289 | [RCA] Initial Layout | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3416 | [RCA][createNewAnalysis] modal input Case name >> save draft | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4296 | [RCA][Dashboard] RCA Analysis (All) - table list | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3420 | [RCA][createNewAnalysis] Common Header | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-1800 | [ASM][FE] Upgrade Version Angular | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4447 | [ASM] Sustainable Tuning for support 2-3x or more data | 28 |  |  | 1 | baseline | moved | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-4356 | [Improvement][SAP] change toast error message after submit CMMS | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4355 | [Improvement][SAP] Error Handling from SAP response | 28 |  |  | 1 | baseline | moved | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-3407 | [RCA][createNewAnalysis] Team Member | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3408 | [RCA][createNewAnalysis] Case Background | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3409 | [RCA][createNewAnalysis] Problem Analysis | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3410 | [RCA][createNewAnalysis] Incident Timeline | 29 |  |  | 1 | baseline | moved | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-4730 | [Improvement][ASM][CMMS] Submit CMMS - Add PackageNo not found page | 28 |  |  | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM-4731 | [Improvement][ASM][CMMS] Submit CMMS - Change logic field "Updated Field" | 28 |  |  | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM-3752 | [Improvement][ASM][AssetStrategy][Revision] disabled icon restore | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3898 | [Improvement][ASM][BE+FE] Abbreviate number when exceeding digit threshold | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis |  | [RCA][createNewAnalysis] Incident Timeline - Export PDF | 28 |  |  | 1 | baseline | removed | remove
asm | ai | EAPM-347 | [ASM][AssetStrategy][RisksAndTasks] Risk tap Details - Integrate AI Suggestion | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3411 | [RCA][createNewAnalysis] Finding | 29 |  |  | 1 | baseline | moved | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-3412 | [RCA][createNewAnalysis] Logic Tree | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Logic Tree - Box Details | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4516 | [RCA][createNewAnalysis] Logic Tree - Box Details - Actions | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Verification Action | 29 |  |  | 1 | baseline | split | breakdown 5217, move to sprint 30
rca | Case creation - Create/Edit Analysis | EAPM-4567 | [RCA][createNewAnalysis] Verification Action - Noti | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3414 | [RCA][createNewAnalysis] RCA Recommendations | 30 |  |  | 1 | baseline | split | breakdown 5234
rca | Case creation - Create/Edit Analysis | EAPM-3415 | [RCA][createNewAnalysis] Other Recommendations | 30 |  |  | 1 | baseline | split | breakdown 5235
rca | Case creation - Create/Edit Analysis | EAPM-4568 | [RCA][createNewAnalysis] Reference Document - Table 1 | 30 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4569 | [RCA][createNewAnalysis] Reference Document - Table 2 | 30 |  |  | 1 | baseline | moved | move to backlog
rca |  | EAPM-5493 | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | 30 |  |  | 1 |  | added | add on, no impact
rca |  | EAPM-5158 | [Improvement][RCA][createNewAnalysis] change source of PTTEP Risk Matrix + Add last updated date | 30 |  |  | 1 |  | added | add on, no impact
rca |  | EAPM-5241 | [Improvement][RCA][createNewAnalysis] Verification Actions - Table List - allow assigned group email from azure + add column "Last Updated by" | 30 |  |  | 1 |  | added | add on, no impact
rca |  | EAPM-5397 | [RCA] Sharepoint Structure | 30 |  |  | 1 |  | added | add on, no impact
rca |  | EAPM-5395 | [Improvement][RCA][createNewAnalysis] add asset when create new RCA + add validate input format "RCA Case Name" | 30 |  |  | 1 |  | added | add on, no impact
rca |  | EAPM-5434 | [Improvement][RCA][FE][createNewAnalysis] change save button name + change placeholder | 30 |  |  | 1 |  | added | add on, no impact
rca |  | EAPM-5572 | [ServerError] HTTP Status Error 5xx | 30 |  |  | 1 |  | added | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-3406 | [RCA][createNewAnalysis] Executive Summary | 31 |  |  | 1 | baseline | moved | move to sprint 30
rca | case approval | EAPM-5023 | [RCA][Approval Flow] Case Approval - Approval detail + progress - Fa view | 31 |  |  | 1 | baseline | moved | move to sprint 32
rca | case approval | EAPM-5237 | [RCA][Approval Flow] Case Approval - Approval detail + progress - approver view | 31 |  |  | 1 | baseline | moved | move to sprint 32
rca | Case creation - Create/Edit Analysis | EAPM-5812 | [Improvement][RCA][createNewAnalysis] Logic Tree - Main diagram | 31 |  |  | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM 5848 | [Improvement][RCA][createNewAnalysis] Add validation - Folder Name in Sharepoint | 31 |  |  | 1 |  | added | add on
rca | case approval | EAPM 5024 | [RCA][Approval Flow] Case Approval - Approval detail + progress - viewer | 32 |  |  | 1 | baseline
rca | case approval | EAPM 6178 | [RCA][Approval Flow] Case Approval - Approval Progress - Super User view | 32 |  |  | 1 | baseline
rca | case approval | EAPM 5847 | [RCA][Approval Flow] Case Approval - Approval History | 32 |  |  | 1 | baseline
rca | case approval | EAPM 5027 | [RCA][Approval Flow] Case Approval - Noti Email - Inform | 32 |  |  | 1 |  | moved | move to sprint 33
rca | Report | EAPM 5028 | [RCA] Export Report | 32 |  |  | 1 |  | moved | move to sprint 33
rca | case approval | EAPM-5022 | [RCA][Approval Flow] RCA Approval Tracking modal - Structure | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5026 | [RCA][Approval Flow] Case Status - Permission | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5059 | [RCA][UserManagement] Master Data Setting "RCA Type" | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5236 | [RCA][Approval Flow] Submit RCA Case - “Start Investigation” button | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6028 | [RCA][createNewAnalysis] Executive Summary - Design Request/Response JSON for AI | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6231 | [RCA] Add Permission to all pages in RCA | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6367 | [RCA][Approval Flow] Submit RCA Case - Flow Start Investigation | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6368 | [RCA][Approval Flow] Submit RCA Case - Waiting Verification | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6369 | [RCA][Approval Flow] Submit RCA Case - Approve | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6370 | [RCA][Approval Flow] Submit RCA Case - Implementing Action and Complete | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | Report | EAPM 5029 | [RCA] Export Report - ppt >> PDF | 33 |  |  | 1 | baseline
rca | RCA Dashboard. | EAPM-3417 | [RCA][createNewAnalysis] Dash Board - Graph | 33 |  |  | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Analysis(All) | 33 |  |  | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Verification (Pending) | 34 |  |  | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Recommendation (Pending) | 34 |  |  | 0 | baseline
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Azure | 34 |  |  | 0 | baseline | moved | move to sprint 31, breakerdown 5038, 5058
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - Add input setting | 35 |  |  | 0 | baseline | moved | move to sprint 31, breakerdown 5056, 5057, 5036, 5037
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - display | 35 |  |  | 0 | baseline | moved | move to sprint 31, breakdown 5034, 5035, 5020
rca | Noti Email |  | [RCA] Notification Email - Monthly 16th | 35 |  |  | 0 | baseline
rca | Noti Email |  | [RCA] Notification Email - Monthly 1st | 35 |  |  | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #1 | 36 |  |  | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #2 | 37 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #1 | 38 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #2 | 39 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #3 | 40 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #4 | 41 |  |  | 0 | baseline
handover | Document |  | [Document] system and user manual, sonaqube result | 42 |  |  | 0 | baseline
handover | Knowledge Transfer |  | [KT] knowledge transfer | 43 |  |  | 0 | baseline

## dashboard
Baseline vs Change — Project Scope Dashboard
Source: 'baseline' sheet (item-level plan) and 'sprintday' sheet (sprint calendar). Timeline and budget are FIXED — Sprint 18 to 43.
AS of 06 Aug 2026: not impact project timeline
Chart data (do not delete)
Module | Baseline | Current |  | Change type | Items
Added (new scope)
Broken down (re-planned)
Moved to another sprint
Removed
Sap
1 ¦ SCOPE: BASELINE vs CURRENT
Metric | Value | Comment
Baseline scope agreed (items) |  | At revision baseline on SOR 2026
Current scope in plan (items) |  | Everything in the plan today
Net change vs baseline (items) |  | Track of change (additional, in original)
Net change (%)
– New add-on requests |  | New scope
– Original baseline items broken down |  | Same scope, more detailed tickets
SAP Activity |  | Sap Activities
Items de-scoped / removed
Items moved to another sprint |  | Sequence changed, scope unchanged
Timeline (start – end) |  | Unchanged from baseline
2 ¦ CHANGE BY MODULE
Module | Baseline items | New items | Removed | Moved to another sprint | Current items | Net change
asm
rca
ui improvement
handover
Total

## dashboard v2 (hidden)
Baseline vs Change — Project Scope Dashboard
Source: 'baseline' sheet (item-level plan) and 'sprintday' sheet (sprint calendar). Timeline and budget are FIXED — Sprint 18 to 43.
AS of 06 Aug 2026
Chart data (do not delete)
Module | Baseline | Current |  | Change type | Items
Added (new scope)
Broken down (re-planned)
Moved to another sprint
Removed
1 ¦ SCOPE: BASELINE vs CURRENT
Metric | Value | Comment
Baseline scope agreed (items) |  | At revision baseline on SOR 2026
Current scope in plan (items) |  | Everything in the plan today
Net change vs baseline (items) |  | Track of change (additional, in original)
Net change (%)
– New add-on requests |  | New scope
– Original baseline items broken down |  | Same scope, more detailed tickets
Items de-scoped / removed
Items moved to another sprint |  | Sequence changed, scope unchanged
Timeline (start – end) |  | Unchanged from baseline
2 ¦ CHANGE BY MODULE
Module | Baseline items | New items | Removed | Moved to another sprint | Current items | Net change
asm
rca
ui improvement
handover
Total

## master plan
Project Plan: |  | Project start: | 2026-01-05
Project Actual: |  | Project end: | [6 empty] | Year 2026
|  | Baseline: | [6 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
[9 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
[9 empty] | sp18 | sp19 |  | sp20 |  | sp21 |  | sp22 |  | sp23 |  | sp24 |  | sp25 |  | sp26 |  | sp27 |  | sp28 |  | sp29 |  | sp30 |  | sp31 |  | sp32 |  | sp33 |  | sp34 |  | sp35 |  | sp36 |  | sp37 |  | sp38 |  | sp39 |  | sp40 |  | sp41 |  | sp42 |  | sp43 |  | sp44
Module | Feature | Start | End | Sprint | Working Day | % Plan | % Actual | status
MVP1: ASM+AI
| Revision | 2026-01-05 | 2026-01-23 | 18-19
| CMMS | 2026-01-26 | 2026-05-15 | 20-27
| AI | 2026-02-23 | 2026-03-06 | 22
MVP2: RCA
| Case Creation - Create/Edit Analysis | 2026-05-04 | 2026-07-10 | 27-31
| Case Approval | 2026-06-29 | 2026-07-24 | 31-32
| Report | 2026-07-13 | 2026-08-07 | 32-33
| RCA Dashboard. | 2026-07-27 | 2026-08-21 | 33-34
| User Management | 2026-08-10 | 2026-09-04 | 34-35
| Noti Email | 2026-08-24 | 2026-09-04 | 35
UI Improvement
| Requirement & Design | 2026-09-07 | 2026-10-02 | 36-37
| Implementation, Testing, and Deploy | 2026-10-05 | 2026-11-27 | 38-41
Handover
| Document | 2026-11-30 | 2026-12-11 | 42
| Knowledge Transfer | 2026-12-14 | 2026-12-25 | 43
Assumption:
1) the project plan based on the requirement baseline sheet "baseline"
2) additional improvement and scope can be discussed in terms of trade-off OR additional requirement
3) the actual % is weighted by working days, excluding holidays
Formulas:
Working Day = NETWORKDAYS([Start], [End], [1]holiday!$A2:A18)

## baseline
Module | Feature Name | User Story ID | User Story Description | Sprint | start | end | Status (1=Done, 0=Progress) | Is Baseline | Change Type | Note | Module ¦ Feature ¦ Sprint | [5 empty] | Baseline vs change record
asm | improvement - MyTasks | EAPM-906 | [Improvement][Home][GeneralDetails] My Tasks - Add checked Group Permission for Waiting for Approval Box. | 18 |  |  | 1 | baseline |  | email noti | Module | Sprint | start | end | Feature Name | Count of User Story Description | Module | Count of Is Baseline
asm | notiEmail | EAPM-278 | [ASM][AssetStrategy] Email Notification Message - Template 2 (Review) | 18 |  |  | 1 | baseline |  | email noti | asm |  |  |  |  | 90 | asm | 90
asm | improvement - RisksAndTasks | EAPM-923 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Add Description for Failure Impact + Change Field Name | 18 |  |  | 1 | baseline |  | email noti |  | 18 | 2026-01-05 | 2026-01-09 | revision | 8 | handover | 2
asm | improvement - TableList | EAPM-244 | [Improvement][ASM][AssetStrategy] Strategies Table List V3. - Add column | 18 |  |  | 1 | baseline |  | email noti |  | 19 | 2026-01-12 | 2026-01-23 | revision | 14 | rca | 41
asm | GCP | EAPM-922 | [ASM][AssetStrategy] Integrate FDP (GCP) - [BE] | 18 |  |  | 1 | baseline |  | integration |  | 20 | 2026-01-26 | 2026-02-06 | cmms | 14 | ui improvement | 6
asm | improvement - RisksAndTasks | EAPM-919 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk/Task Panel - Change Icon Yellow Alert to Arrow Icon + Abbreviate Interval + SCE Tag | 18 |  |  | 1 | baseline |  | integration |  | 21 | 2026-02-09 | 2026-02-20 | cmms | 8 | Total Result | 139
asm | asm | EAPM-882 | [ASM] Apply a consistent design standard to all action buttons. [FE] | 18 |  |  | 1 | baseline |  | integration |  | 22 | 2026-02-23 | 2026-03-06 | ai | 7
asm | improvement - TableList | EAPM-1071 | [Improvement][ASM][AssetStrategy] All Table List - Change Design the shown numbers as total, select items, filter results | 18 |  |  | 1 | baseline |  | integration |  |  |  |  | cmms | 4
asm | revision | EAPM-10 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 19 |  |  | 1 | baseline |  |  |  | 23 | 2026-03-09 | 2026-03-20 | cmms | 7
asm | revision | EAPM-11 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 19 |  |  | 1 | baseline |  |  |  | 24 | 2026-03-23 | 2026-04-03 | cmms | 11
asm | revision | EAPM-7 | [ASM][AssetStrategy][Revisions] Revision Details - Risks and Tasks | 19 |  |  | 1 | baseline |  |  |  | 25 | 2026-04-06 | 2026-04-17 | cmms | 5
asm | revision | EAPM-25 | [ASM][AssetStrategy][Revisions] Revision Details - Risks Details | 19 |  |  | 1 | baseline |  |  |  | 26 | 2026-04-20 | 2026-05-01 | cmms | 6
asm | revision | EAPM-26 | [ASM][AssetStrategy][Revisions] Revision Details - Task Details | 19 |  |  | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | cmms | 5
asm | revision | EAPM-8 | [ASM][AssetStrategy][Revisions] Revision Details - Risk Analysis | 19 |  |  | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | ai | 1
asm | revision | EAPM-9 | [ASM][AssetStrategy][Revisions] Revision Details - Maintenance Plans | 19 |  |  | 1 | baseline |  |  | rca |  |  |  |  | 64
asm | GCP | EAPM-1255 | [ASM][AssetStrategy] Trigger an update for all data retrieved from GCP. (Location, FDP, Maintenance Plan, ...) | 19 |  |  | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | Case creation - Create/Edit Analysis | 6
asm | improvement - MyTasks | EAPM-1302 | [Improvement][Home][GeneralDetails] My Task - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 28 | 2026-05-18 | 2026-05-29 | Case creation - Create/Edit Analysis | 10
asm | improvement - UserManagement | EAPM-1303 | [Improvement][Admin] User Management - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | Case creation - Create/Edit Analysis | 7
asm | improvement - MaintenancePlan | EAPM-1304 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Maintenance Plan table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | Case creation - Create/Edit Analysis | 4
asm | improvement - TableList | EAPM-1392 | [Improvement][ASM][AssetStrategy] Strategy Table list - Apply standard design for table list | 19 |  |  | 1 | baseline | [6 empty] | (empty) | 7
asm | improvement - Revision | EAPM-1393 | [Improvement][ASM][AssetStrategy][Revision] Revision Table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 31 | 2026-06-29 | 2026-07-10 | case approval | 2
asm | improvement - RisksAndTasks | EAPM-1394 | [Improvement][ASM][AssetStrategy][Overview] Risk Matrix by Active Strategy Table list - Apply standard design for table list | 19 |  |  | 1 | baseline | [6 empty] | Case creation - Create/Edit Analysis | 3
asm | improvement - TableList | EAPM-1150 | [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 20 |  |  | 1 | baseline |  |  |  | 32 | 2026-07-13 | 2026-07-24 | case approval | 14
asm | improvement - Excel | EAPM-349 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #1 | 20 |  |  | 1 | baseline | [6 empty] | Report | 1
asm | improvement - Excel | EAPM-1309 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #2 | 20 |  |  | 1 | baseline |  |  |  | 33 | 2026-07-27 | 2026-08-07 | RCA Dashboard. | 2
asm | improvement - MaintenancePlan | EAPM-2000 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add dropdown "Work Center" | 20 |  |  | 1 | baseline | [6 empty] | Report | 1
asm | improvement - RisksAndTasks | EAPM-1999 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details V3. | 20 |  |  | 1 | baseline |  |  |  | 34 | 2026-08-10 | 2026-08-21 | RCA Dashboard. | 2
asm | improvement - RisksAndTasks | EAPM-1585 | [Improvement][FE][ASM][RisksAndTasks] Risk Property - Add more suggestion to 3M, 6M, 12M, 18M, 24M | 20 |  |  | 1 | baseline | [6 empty] | User Management | 1
asm | improvement - RisksAndTasks | EAPM-1883 | [Improvement][ASM][RisksAndTasks] - Risk Detail / Task Detail - Add more suggestion | 20 |  |  | 1 | baseline |  |  |  | 35 | 2026-08-24 | 2026-09-04 | Noti Email | 2
asm | improvement - RisksAndTasks | EAPM-2003 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Change Logic | 20 |  |  | 1 | baseline | [6 empty] | User Management | 2
asm | improvement - RisksAndTasks | EAPM-2006 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details - Set default ROI to "-1" | 20 |  |  | 1 | baseline |  |  | handover |  |  |  |  | 2
asm | improvement - StrategySummary | EAPM-2004 | [Improvement][ASM][AssetStrategy][SummaryDetails] Change default "Plant Length =20" | 20 |  |  | 1 | baseline |  |  |  | 42 | 2026-11-30 | 2026-12-11 | Document | 1
sap | cmms | EAPM-1314 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | 20 |  |  | 1 | baseline |  |  |  | 43 | 2026-12-14 | 2026-12-25 | Knowledge Transfer | 1
asm | cmms | EAPM-599 | [ASM][AssetStrategy][MaintenancePlans] Table List - Submit Change Request Flow | 20 |  |  | 1 | baseline |  |  | ui improvement |  |  |  |  | 6
asm | cmms | EAPM-1305 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action | 20 |  |  | 1 | baseline |  |  |  | 36 | 2026-09-07 | 2026-09-18 | Requirement & Design | 1
asm | cmms | EAPM-1799 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action - Export Excel | 20 |  |  | 1 | baseline |  |  |  | 37 | 2026-09-21 | 2026-10-02 | Requirement & Design | 1
sap | cmms | EAPM-2423 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | 21 |  |  | 1 | baseline |  |  |  | 38 | 2026-10-05 | 2026-10-16 | Implementation, Testing, and Deploy | 1
asm | improvement - MaintenancePlan | EAPM-2487 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Converted interval value K = 000H | 21 |  |  | 1 | baseline |  |  |  | 39 | 2026-10-19 | 2026-10-30 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-33 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (RequestInfo) #1 | 21 |  |  | 1 | baseline |  |  |  | 40 | 2026-11-02 | 2026-11-13 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1306 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #1 | 21 |  |  | 1 | baseline |  |  |  | 41 | 2026-11-16 | 2026-11-27 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1801 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #2 | 21 |  |  | 1 | baseline |  |  | Total Result |  |  |  |  | 162
asm | cmms | EAPM-1955 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #3 | 21 |  |  | 1 | baseline
asm | cmms | EAPM-1307 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) - Add/Duplicate/Delete row | 21 |  |  | 1 | baseline
asm | improvement - RisksAndTasks | EAPM-2486 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Scale Bar - Icon U / M | 21 |  |  | 1 | baseline
asm | cmms | EAPM-1308 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (ObjectList) + Add/Duplicate/Delete row | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1310 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #1 | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1844 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #2 | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1311 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add/Duplicate/Delete row | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1312 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #1 | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1845 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #2 | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1313 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add/Duplicate/Delete row | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2745 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - CMMS Form(PreFilled) - MaintenancePlanItem - Case: Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2779 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2780 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add New Sub | 22 |  |  | 1 | baseline
asm | improvement - MaintenancePlan | EAPM-2759 | [ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Request Sub." | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1318 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (AttachJobCard) | 23 |  |  | 1 | baseline
asm | cmms | EAPM-32 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Initial + Before | 23 |  |  | 1 | baseline
asm | cmms | EAPM-1803 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - After | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2488 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Related Strategy | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2672 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Calculate Summary Interval | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2945 | [FE][POC][ASM][AssetStrategy][MaintenancePlan] POC CMMS Final Form - UI Screen + Export Excel | 23 |  |  | 1 | baseline
asm | improvement - MaintenancePlan | EAPM-2946 | [FE][Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Work Center" field | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2007 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Initial + Request Info | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2933 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Plan Item | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2934 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Item (Object List) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2935 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Header) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2936 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Operation) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2937 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Attach Job Card | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2362 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - save data to APM DB | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3352 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - "Submit / Back" Button | 24 |  |  | 1 | baseline
asm | GCP | EAPM-3448 | [BE][ASM][AssetStrategy] Sync all "ASM Strategies" to GCP | 24 |  |  | 1 | baseline
asm | Migrate Data | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 24 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3445 | [FE][RCA] POC powerpoint | 24 |  |  | 1 | baseline |  | rca
sap | sap | EAPM-3717 | [ASM] Update schema follow s4AHANA format | 25 |  |  | 1 | baseline
sap | cmms | EAPM-3727 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | 25 |  |  | 1 | baseline
asm | improvement - MaintenancePlan | EAPM-1160 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - After Submit CMMS - Add logic Submit button | 25 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3797 | [POC][FE][RCA] Logic Tree - Diagram | 25 |  |  | 1 | baseline |  | rca
asm | improvement - RisksAndTasks | EAPM-3875 | [Improvement][ASM][FE] Abbreviate number when exceeding digit threshold | 25 |  |  | 1 | baseline
asm | improvement - Overview | EAPM-4027 | [Improvement][ASM][BE] tuning performance Graph | 26 |  |  | 1 | baseline
sap | cmms | EAPM-4042 | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | 26 |  |  | 1 | baseline
asm | cmms | EAPM-3671 | [Improvement][AssetStrategy][CMMS] Add column “SCE Group” + Prefill Operation Short Text + Add K logic | 26 |  |  | 1 | baseline
asm | cmms | EAPM-3355 | [ASM][AssetStrategy][MaintenancePlans] Table List - Change Request No. - Hyperlink - modal Final, SG preview, related SG | 26 |  |  | 1 | baseline
asm | Migrate Data | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 26 |  |  | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 26 |  |  | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 27 |  |  | 1 | baseline
asm | cmms history log | EAPM-1316 | [ASM][AssetStrategy][CMMS] CMMS History Log - table + click button + Overview | 27 |  |  | 1 | baseline
asm | cmms history log | EAPM-2808 | [ASM][AssetStrategy][CMMS] CMMS History Log - Click Hyperlink - View CMMS Final Form Details | 27 |  |  | 1 | baseline
asm | cmms history log | EAPM-3926 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel (Submitted Final Form) | 27 |  |  | 1 | baseline
asm | cmms history log | EAPM-2809 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel Table View | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4289 | [RCA] Initial Layout | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3416 | [RCA][createNewAnalysis] modal input Case name >> save draft | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4296 | [RCA][Dashboard] RCA Analysis (All) - table list | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3420 | [RCA][createNewAnalysis] Common Header | 27 |  |  | 1 | baseline
asm | asm | EAPM-1800 | [ASM][FE] Upgrade Version Angular | 27 |  |  | 1 | baseline
asm | asm | EAPM-4447 | [ASM] Sustainable Tuning for support 2-3x or more data | 28 |  |  | 1 | baseline | moved | move to 28
sap | cmms | EAPM-4356 | [Improvement][SAP] change toast error message after submit CMMS | 27 |  |  | 1 | baseline
sap | cmms | EAPM-4355 | [Improvement][SAP] Error Handling from SAP response | 28 |  |  | 1 | baseline | moved | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-3407 | [RCA][createNewAnalysis] Team Member | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3408 | [RCA][createNewAnalysis] Case Background | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3409 | [RCA][createNewAnalysis] Problem Analysis | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3410 | [RCA][createNewAnalysis] Incident Timeline | 29 |  |  | 1 | baseline | moved | move to 29
asm | cmms | EAPM-4730 | [Improvement][ASM][CMMS] Submit CMMS - Add PackageNo not found page | 28 |  |  | 1 |  | added | add on
asm | cmms | EAPM-4731 | [Improvement][ASM][CMMS] Submit CMMS - Change logic field "Updated Field" | 28 |  |  | 1 |  | added | add on
asm | improvement - Revision | EAPM-3752 | [Improvement][ASM][AssetStrategy][Revision] disabled icon restore | 28 |  |  | 1 | baseline
asm | improvement - RisksAndTasks | EAPM-3898 | [Improvement][ASM][BE+FE] Abbreviate number when exceeding digit threshold | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis |  | [RCA][createNewAnalysis] Incident Timeline - Export PDF | 28 |  |  | 1 | baseline | removed | remove
asm | ai | EAPM-347 | [ASM][AssetStrategy][RisksAndTasks] Risk tap Details - Integrate AI Suggestion | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3411 | [RCA][createNewAnalysis] Finding | 29 |  |  | 1 | baseline | moved | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-3412 | [RCA][createNewAnalysis] Logic Tree | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Logic Tree - Box Details | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4516 | [RCA][createNewAnalysis] Logic Tree - Box Details - Actions | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Verification Action | 29 |  |  | 1 | baseline | split | breakdown 5217, move to sprint 30
rca | Case creation - Create/Edit Analysis | EAPM-4567 | [RCA][createNewAnalysis] Verification Action - Noti | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3414 | [RCA][createNewAnalysis] RCA Recommendations | 30 |  |  | 1 | baseline | split | breakdown 5234
rca | Case creation - Create/Edit Analysis | EAPM-3415 | [RCA][createNewAnalysis] Other Recommendations | 30 |  |  | 1 | baseline | split | breakdown 5235
rca | Case creation - Create/Edit Analysis | EAPM-4568 | [RCA][createNewAnalysis] Reference Document - Table 1 | 30 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4569 | [RCA][createNewAnalysis] Reference Document - Table 2 | 30 |  |  | 1 | baseline | moved | move to backlog
sap | cmms | EAPM-5493 | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | 30 |  |  | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5158 | [Improvement][RCA][createNewAnalysis] change source of PTTEP Risk Matrix + Add last updated date | 30 |  |  | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5241 | [Improvement][RCA][createNewAnalysis] Verification Actions - Table List - allow assigned group email from azure + add column "Last Updated by" | 30 |  |  | 1 |  | added | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-5397 | [RCA] Sharepoint Structure | 30 |  |  | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5395 | [Improvement][RCA][createNewAnalysis] add asset when create new RCA + add validate input format "RCA Case Name" | 30 |  |  | 1 |  | added | add on, no impact
rca | improve rca | EAPM-5434 | [Improvement][RCA][FE][createNewAnalysis] change save button name + change placeholder | 30 |  |  | 1 |  | added | add on, no impact
asm | asm | EAPM-5572 | [ServerError] HTTP Status Error 5xx | 30 |  |  | 1 |  | added | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-3406 | [RCA][createNewAnalysis] Executive Summary | 31 |  |  | 1 | baseline | moved | move to sprint 30
rca | case approval | EAPM-5023 | [RCA][Approval Flow] Case Approval - Approval detail + progress - Fa view | 31 |  |  | 1 | baseline | moved | move to sprint 32
rca | case approval | EAPM-5237 | [RCA][Approval Flow] Case Approval - Approval detail + progress - approver view | 31 |  |  | 1 | baseline | moved | move to sprint 32
rca | Case creation - Create/Edit Analysis | EAPM-5812 | [Improvement][RCA][createNewAnalysis] Logic Tree - Main diagram | 31 |  |  | 1 |  | added | add on
rca | Case creation - Create/Edit Analysis | EAPM 5848 | [Improvement][RCA][createNewAnalysis] Add validation - Folder Name in Sharepoint | 31 |  |  | 1 |  | added | add on
rca | case approval | EAPM 5024 | [RCA][Approval Flow] Case Approval - Approval detail + progress - viewer | 32 |  |  | 1 | baseline
rca | case approval | EAPM 6178 | [RCA][Approval Flow] Case Approval - Approval Progress - Super User view | 32 |  |  | 1 | baseline
rca | case approval | EAPM 5847 | [RCA][Approval Flow] Case Approval - Approval History | 32 |  |  | 1 | baseline
rca | case approval | EAPM 5027 | [RCA][Approval Flow] Case Approval - Noti Email - Inform | 32 |  |  | 1 |  | moved | move to sprint 33
rca | Report | EAPM 5028 | [RCA] Export Report | 32 |  |  | 1 |  | moved | move to sprint 33
rca | case approval | EAPM-5022 | [RCA][Approval Flow] RCA Approval Tracking modal - Structure | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5026 | [RCA][Approval Flow] Case Status - Permission | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | User Management | EAPM-5059 | [RCA][UserManagement] Master Data Setting "RCA Type" | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-5236 | [RCA][Approval Flow] Submit RCA Case - “Start Investigation” button | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | ai | EAPM-6028 | [RCA][createNewAnalysis] Executive Summary - Design Request/Response JSON for AI | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | User Management | EAPM-6231 | [RCA] Add Permission to all pages in RCA | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6367 | [RCA][Approval Flow] Submit RCA Case - Flow Start Investigation | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6368 | [RCA][Approval Flow] Submit RCA Case - Waiting Verification | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6369 | [RCA][Approval Flow] Submit RCA Case - Approve | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | case approval | EAPM-6370 | [RCA][Approval Flow] Submit RCA Case - Implementing Action and Complete | 32 |  |  | 1 |  | Split | breakdown to srpint 32
rca | Report | EAPM 5029 | [RCA] Export Report - ppt >> PDF | 33 |  |  | 1 | baseline
rca | RCA Dashboard. | EAPM-3417 | [RCA][createNewAnalysis] Dash Board - Graph | 33 |  |  | 1 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Analysis(All) | 33 |  |  | 1 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Verification (Pending) | 34 |  |  | 1 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Recommendation (Pending) | 34 |  |  | 0 | baseline
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Azure | 34 |  |  | 0 | baseline | moved | move to sprint 31, breakerdown 5038, 5058
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - Add input setting | 35 |  |  | 0 | baseline | moved | move to sprint 31, breakerdown 5056, 5057, 5036, 5037
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - display | 35 |  |  | 0 | baseline | moved | move to sprint 31, breakdown 5034, 5035, 5020
rca | Noti Email |  | [RCA] Notification Email - Monthly 16th | 35 |  |  | 0 | baseline
rca | Noti Email |  | [RCA] Notification Email - Monthly 1st | 35 |  |  | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #1 | 36 |  |  | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #2 | 37 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #1 | 38 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #2 | 39 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #3 | 40 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #4 | 41 |  |  | 0 | baseline
handover | Document |  | [Document] system and user manual, sonaqube result | 42 |  |  | 0 | baseline
handover | Knowledge Transfer |  | [KT] knowledge transfer | 43 |  |  | 0 | baseline

## sprintday (hidden)
| team velocity | 30 | story point/sprint
| full | 10 | working day/sprint
ref. holiday
Sprint | Start Date (Mon) | End Date (Fri) | Working Day | Est. Story Point | % Weight Resoure Sprint Utilize | Remark | Sprint | Average of % Weight Resoure Sprint Utilize
18 | 2026-01-05 | 2026-01-09 |  |  |  | half sprint | 18 | 50%
19 | 2026-01-12 | 2026-01-23 |  |  |  | full | 19 | 100%
20 | 2026-01-26 | 2026-02-06 |  |  |  | full | 20 | 100%
21 | 2026-02-09 | 2026-02-20 |  |  |  | full | 21 | 100%
22 | 2026-02-23 | 2026-03-06 |  |  |  | full | 22 | 90%
23 | 2026-03-09 | 2026-03-20 |  |  |  | full | 23 | 100%
24 | 2026-03-23 | 2026-04-03 |  |  |  | full | 24 | 100%
25 | 2026-04-06 | 2026-04-17 |  |  |  | full | 25 | 60%
26 | 2026-04-20 | 2026-05-01 |  |  |  | full | 26 | 90%
27 | 2026-05-04 | 2026-05-15 |  |  |  | full | 27 | 90%
28 | 2026-05-18 | 2026-05-29 |  |  |  | full | 28 | 100%
29 | 2026-06-01 | 2026-06-12 |  |  |  | full | 29 | 80%
30 | 2026-06-15 | 2026-06-26 |  |  |  | full | 30 | 100%
31 | 2026-06-29 | 2026-07-10 |  |  |  | full | 31 | 100%
32 | 2026-07-13 | 2026-07-24 |  |  |  | full | 32 | 100%
33 | 2026-07-27 | 2026-08-07 |  |  |  | full | 33 | 80%
34 | 2026-08-10 | 2026-08-21 |  |  |  | full | 34 | 90%
35 | 2026-08-24 | 2026-09-04 |  |  |  | full | 35 | 100%
36 | 2026-09-07 | 2026-09-18 |  |  |  | full | 36 | 100%
37 | 2026-09-21 | 2026-10-02 |  |  |  | full | 37 | 100%
38 | 2026-10-05 | 2026-10-16 |  |  |  | full | 38 | 90%
39 | 2026-10-19 | 2026-10-30 |  |  |  | full | 39 | 90%
40 | 2026-11-02 | 2026-11-13 |  |  |  | full | 40 | 100%
41 | 2026-11-16 | 2026-11-27 |  |  |  | full | 41 | 100%
42 | 2026-11-30 | 2026-12-11 |  |  |  | full | 42 | 90%
43 | 2026-12-14 | 2026-12-25 |  |  |  | full | 43 | 100%
44 | 2026-12-28 | 2027-01-08 |  |  |  | half sprint | 44 | 90%
[7 empty] | Grand Total | 92.22%
Formulas:
Working Day = NETWORKDAYS([Start Date (Mon)], [End Date (Fri)], holiday!$A2:A18)

## holiday (hidden)
Date | Holiday Name
2026-01-01 | New Year's Day
2026-03-03 | Makha Bucha Day
2026-04-06 | Chakri Memorial Day
2026-04-13 | Songkran
2026-04-14 | Songkran
2026-04-15 | Songkran
2026-05-01 | National Labor Day
2026-05-04 | Coronation Day
2026-06-01 | Sub. Visakha Bucha
2026-06-03 | Queen's Birthday
2026-07-28 | King's Birthday
2026-07-29 | Asarnha Bucha Day
2026-08-12 | Mother's Day
2026-10-13 | King Bhumibol Memorial
2026-10-23 | King Chulalongkorn Memorial
2026-12-07 | Sub. Father's Day
2026-12-31 | New Year's Eve

## baseline V3 (hidden)
Module | Feature Name | User Story ID | User Story Description | Sprint | start | end | Status (1=Done, 0=Progress) | Is Baseline | Change Record | note original | Module ¦ Feature ¦ Sprint
asm | revision | EAPM-906 | [Improvement][Home][GeneralDetails] My Tasks - Add checked Group Permission for Waiting for Approval Box. | 18 |  |  | 1 | baseline |  | email noti | Module | Sprint | start | end | Feature Name | Count of User Story Description
asm | revision | EAPM-278 | [ASM][AssetStrategy] Email Notification Message - Template 2 (Review) | 18 |  |  | 1 | baseline |  | email noti | asm |  |  |  |  | 90
asm | revision | EAPM-923 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Add Description for Failure Impact + Change Field Name | 18 |  |  | 1 | baseline |  | email noti |  | 18 | 2026-01-05 | 2026-01-09 | revision | 8
asm | revision | EAPM-244 | [Improvement][ASM][AssetStrategy] Strategies Table List V3. - Add column | 18 |  |  | 1 | baseline |  | email noti |  | 19 | 2026-01-12 | 2026-01-23 | revision | 14
asm | revision | EAPM-922 | [ASM][AssetStrategy] Integrate FDP (GCP) - [BE] | 18 |  |  | 1 | baseline |  | integration |  | 20 | 2026-01-26 | 2026-02-06 | cmms | 14
asm | revision | EAPM-919 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk/Task Panel - Change Icon Yellow Alert to Arrow Icon + Abbreviate Interval + SCE Tag | 18 |  |  | 1 | baseline |  | integration |  | 21 | 2026-02-09 | 2026-02-20 | cmms | 8
asm | revision | EAPM-882 | [ASM] Apply a consistent design standard to all action buttons. [FE] | 18 |  |  | 1 | baseline |  | integration |  | 22 | 2026-02-23 | 2026-03-06 | ai | 7
asm | revision | EAPM-1071 | [Improvement][ASM][AssetStrategy] All Table List - Change Design the shown numbers as total, select items, filter results | 18 |  |  | 1 | baseline |  | integration |  |  |  |  | cmms | 4
asm | revision | EAPM-10 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Summary | 19 |  |  | 1 | baseline |  |  |  | 23 | 2026-03-09 |  |  | 7
asm | revision | EAPM-11 | [ASM][AssetStrategy][Revisions] Revision Details - Strategy Summary - Tab Details | 19 |  |  | 1 | baseline |  |  |  | 24 | 2026-03-23 | 2026-04-03 | cmms | 11
asm | revision | EAPM-7 | [ASM][AssetStrategy][Revisions] Revision Details - Risks and Tasks | 19 |  |  | 1 | baseline |  |  |  | 25 | 2026-04-06 | 2026-04-17 | cmms | 5
asm | revision | EAPM-25 | [ASM][AssetStrategy][Revisions] Revision Details - Risks Details | 19 |  |  | 1 | baseline |  |  |  | 26 | 2026-04-20 | 2026-05-01 | cmms | 6
asm | revision | EAPM-26 | [ASM][AssetStrategy][Revisions] Revision Details - Task Details | 19 |  |  | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | cmms | 5
asm | revision | EAPM-8 | [ASM][AssetStrategy][Revisions] Revision Details - Risk Analysis | 19 |  |  | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | ai | 1
asm | revision | EAPM-9 | [ASM][AssetStrategy][Revisions] Revision Details - Maintenance Plans | 19 |  |  | 1 | baseline |  |  | rca |  |  |  |  | 57
asm | revision | EAPM-1255 | [ASM][AssetStrategy] Trigger an update for all data retrieved from GCP. (Location, FDP, Maintenance Plan, ...) | 19 |  |  | 1 | baseline |  |  |  | 27 | 2026-05-04 | 2026-05-15 | Case creation - Create/Edit Analysis | 6
asm | revision | EAPM-1302 | [Improvement][Home][GeneralDetails] My Task - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 28 | 2026-05-18 | 2026-05-29 | Case creation - Create/Edit Analysis | 10
asm | revision | EAPM-1303 | [Improvement][Admin] User Management - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 29 | 2026-06-01 | 2026-06-12 | Case creation - Create/Edit Analysis | 7
asm | revision | EAPM-1304 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Maintenance Plan table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | Case creation - Create/Edit Analysis | 4 | asm
asm | revision | EAPM-1392 | [Improvement][ASM][AssetStrategy] Strategy Table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 31 | 2026-06-29 | 2026-07-10 | case approval | 2 | rca
asm | revision | EAPM-1393 | [Improvement][ASM][AssetStrategy][Revision] Revision Table list - Apply standard design for table list | 19 |  |  | 1 | baseline | [6 empty] | Case creation - Create/Edit Analysis | 3 | ui improvement
asm | revision | EAPM-1394 | [Improvement][ASM][AssetStrategy][Overview] Risk Matrix by Active Strategy Table list - Apply standard design for table list | 19 |  |  | 1 | baseline |  |  |  | 32 | 2026-07-13 | 2026-07-24 | case approval | 14 | handover
asm | cmms | EAPM-1150 | [Improvement][ASM][AssetStrategy] Table List - Searching and Sorting field Unmitigated Matrix, Mitigated Matrix | 20 |  |  | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-349 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #1 | 20 |  |  | 1 | baseline |  |  |  | 33 | 2026-07-27 | 2026-08-07 | RCA Dashboard. | 2
asm | cmms | EAPM-1309 | [Improvement][ASM][AssetStrategy] Excel Template File V4. #2 | 20 |  |  | 1 | baseline | [6 empty] | Report | 1
asm | cmms | EAPM-2000 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add dropdown "Work Center" | 20 |  |  | 1 | baseline |  |  |  | 34 | 2026-08-10 | 2026-08-21 | RCA Dashboard. | 2
asm | cmms | EAPM-1999 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details V3. | 20 |  |  | 1 | baseline | [6 empty] | User Management | 1
asm | cmms | EAPM-1585 | [Improvement][FE][ASM][RisksAndTasks] Risk Property - Add more suggestion to 3M, 6M, 12M, 18M, 24M | 20 |  |  | 1 | baseline |  |  |  | 35 | 2026-08-24 | 2026-09-04 | Noti Email | 2
asm | cmms | EAPM-1883 | [Improvement][ASM][RisksAndTasks] - Risk Detail / Task Detail - Add more suggestion | 20 |  |  | 1 | baseline | [6 empty] | User Management | 2
asm | cmms | EAPM-2003 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Risk Details - Change Logic | 20 |  |  | 1 | baseline |  |  | handover |  |  |  |  | 2
asm | cmms | EAPM-2006 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Task Details - Set default ROI to "-1" | 20 |  |  | 1 | baseline |  |  |  | 42 | 2026-11-30 | 2026-12-11 | Document | 1
asm | cmms | EAPM-2004 | [Improvement][ASM][AssetStrategy][SummaryDetails] Change default "Plant Length =20" | 20 |  |  | 1 | baseline |  |  |  | 43 | 2026-12-14 | 2026-12-25 | Knowledge Transfer | 1
asm | cmms | EAPM-1314 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON | 20 |  |  | 1 | baseline |  |  | ui improvement |  |  |  |  | 6
asm | cmms | EAPM-599 | [ASM][AssetStrategy][MaintenancePlans] Table List - Submit Change Request Flow | 20 |  |  | 1 | baseline |  |  |  | 36 | 2026-09-07 | 2026-09-18 | Requirement & Design | 1
asm | cmms | EAPM-1305 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action | 20 |  |  | 1 | baseline |  |  |  | 37 | 2026-09-21 | 2026-10-02 | Requirement & Design | 1
asm | cmms | EAPM-1799 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - Summary Action - Export Excel | 20 |  |  | 1 | baseline |  |  |  | 38 | 2026-10-05 | 2026-10-16 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2423 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP - Mock Test JSON #2 | 21 |  |  | 1 | baseline |  |  |  | 39 | 2026-10-19 | 2026-10-30 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-2487 | [Improvement][ASM][AssetStrategy][MaintenancePlan] Converted interval value K = 000H | 21 |  |  | 1 | baseline |  |  |  | 40 | 2026-11-02 | 2026-11-13 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-33 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (RequestInfo) #1 | 21 |  |  | 1 | baseline |  |  |  | 41 | 2026-11-16 | 2026-11-27 | Implementation, Testing, and Deploy | 1
asm | cmms | EAPM-1306 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #1 | 21 |  |  | 1 | baseline |  |  | (blank) |  |  |  |  | 7
asm | cmms | EAPM-1801 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #2 | 21 |  |  | 1 | baseline |  |  |  | 30 | 2026-06-15 | 2026-06-26 | (blank) | 7
asm | cmms | EAPM-1955 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) #3 | 21 |  |  | 1 | baseline |  |  | Grand Total |  |  |  |  | 162
asm | cmms | EAPM-1307 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (MaintenancePlanItem) - Add/Duplicate/Delete row | 21 |  |  | 1 | baseline
asm | cmms | EAPM-2486 | [Improvement][ASM][AssetStrategy][RisksAndTasks] Scale Bar - Icon U / M | 21 |  |  | 1 | baseline |  |  | Baseline user story
asm | ai | EAPM-1308 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (ObjectList) + Add/Duplicate/Delete row | 22 |  |  | 1 | baseline |  |  | Module | Count of User Story Description
asm | ai | EAPM-1310 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #1 | 22 |  |  | 1 | baseline |  |  | asm | 90
asm | ai | EAPM-1844 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) #2 | 22 |  |  | 1 | baseline |  |  | handover | 2
asm | ai | EAPM-1311 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add/Duplicate/Delete row | 22 |  |  | 1 | baseline |  |  | rca | 57
asm | ai | EAPM-1312 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #1 | 22 |  |  | 1 | baseline |  |  | ui improvement | 6
asm | ai | EAPM-1845 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) #2 | 22 |  |  | 1 | baseline |  |  | (blank) | 7
asm | ai | EAPM-1313 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add/Duplicate/Delete row | 22 |  |  | 1 | baseline |  |  | Grand Total | 162
asm | cmms | EAPM-2745 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request - CMMS Form(PreFilled) - MaintenancePlanItem - Case: Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2779 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListHeader) - Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2780 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (TaskListOperation) - Add New Sub | 22 |  |  | 1 | baseline
asm | cmms | EAPM-2759 | [ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Request Sub." | 22 |  |  | 1 | baseline
asm | cmms | EAPM-1318 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Change Request Form (AttachJobCard) | 23 |  |  | 1 | baseline
asm | cmms | EAPM-32 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Initial + Before | 23 |  |  | 1 | baseline
asm | cmms | EAPM-1803 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - After | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2488 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Related Strategy | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2672 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - Strategy Preview - Calculate Summary Interval | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2945 | [FE][POC][ASM][AssetStrategy][MaintenancePlan] POC CMMS Final Form - UI Screen + Export Excel | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2946 | [FE][Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - Add logic to "Work Center" field | 23 |  |  | 1 | baseline
asm | cmms | EAPM-2007 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Initial + Request Info | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2933 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Plan Item | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2934 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Maintenance Item (Object List) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2935 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Header) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2936 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Task List (Operation) | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2937 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - tap Finalized - Attach Job Card | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2362 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - save data to APM DB | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3352 | [ASM][AssetStrategy][MaintenancePlan] CMMS Form Final - "Submit / Back" Button | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3448 | [BE][ASM][AssetStrategy] Sync all "ASM Strategies" to GCP | 24 |  |  | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 24 |  |  | 1 | baseline
asm | cmms | EAPM-3445 | [FE][RCA] POC powerpoint | 24 |  |  | 1 | baseline |  | rca
asm | cmms | EAPM-3717 | [ASM] Update schema follow s4AHANA format | 25 |  |  | 1 | baseline
asm | cmms | EAPM-3727 | [ASM][AssetStrategy][MaintenancePlans] Integrate SAP | 25 |  |  | 1 | baseline
asm | cmms | EAPM-1160 | [Improvement][ASM][AssetStrategy][MaintenancePlans] Table List - After Submit CMMS - Add logic Submit button | 25 |  |  | 1 | baseline
asm | cmms | EAPM-3797 | [POC][FE][RCA] Logic Tree - Diagram | 25 |  |  | 1 | baseline |  | rca
asm | cmms | EAPM-3875 | [Improvement][ASM][FE] Abbreviate number when exceeding digit threshold | 25 |  |  | 1 | baseline
asm | cmms | EAPM-4027 | [Improvement][ASM][BE] tuning performance Graph | 26 |  |  | 1 | baseline
asm | cmms | EAPM-4042 | [ASM][SAP] add temporary trigger button for test retry SAP failed - call api schedule SAP | 26 |  |  | 1 | baseline
asm | cmms | EAPM-3671 | [Improvement][AssetStrategy][CMMS] Add column “SCE Group” + Prefill Operation Short Text + Add K logic | 26 |  |  | 1 | baseline
asm | cmms | EAPM-3355 | [ASM][AssetStrategy][MaintenancePlans] Table List - Change Request No. - Hyperlink - modal Final, SG preview, related SG | 26 |  |  | 1 | baseline
asm | cmms | EAPM-2653 | [ASM][AssetStrategy] ASM Data Migration | 26 |  |  | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 26 |  |  | 1 | baseline
asm | cmms | EAPM-1317 | [ASM][AssetStrategy][MaintenancePlans] Submit Change Request Form - CMMS Form Final - Export Excel Finalized | 27 |  |  | 1 | baseline
asm | cmms | EAPM-1316 | [ASM][AssetStrategy][CMMS] CMMS History Log - table + click button + Overview | 27 |  |  | 1 | baseline
asm | cmms | EAPM-2808 | [ASM][AssetStrategy][CMMS] CMMS History Log - Click Hyperlink - View CMMS Final Form Details | 27 |  |  | 1 | baseline
asm | cmms | EAPM-3926 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel (Submitted Final Form) | 27 |  |  | 1 | baseline
asm | cmms | EAPM-2809 | [ASM][AssetStrategy][CMMS] CMMS History Log - table - Export Excel Table View | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4289 | [RCA] Initial Layout | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3416 | [RCA][createNewAnalysis] modal input Case name >> save draft | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4296 | [RCA][Dashboard] RCA Analysis (All) - table list | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3420 | [RCA][createNewAnalysis] Common Header | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-1800 | [ASM][FE] Upgrade Version Angular | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4447 | [ASM] Sustainable Tuning for support 2-3x or more data | 28 |  |  | 1 | baseline | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-4356 | [Improvement][SAP] change toast error message after submit CMMS | 27 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4355 | [Improvement][SAP] Error Handling from SAP response | 28 |  |  | 1 | baseline | move to 28
rca | Case creation - Create/Edit Analysis | EAPM-3407 | [RCA][createNewAnalysis] Team Member | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3408 | [RCA][createNewAnalysis] Case Background | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3409 | [RCA][createNewAnalysis] Problem Analysis | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3410 | [RCA][createNewAnalysis] Incident Timeline | 29 |  |  | 1 | baseline | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-4730 | [Improvement][ASM][CMMS] Submit CMMS - Add PackageNo not found page | 28 |  |  | 1 | add on | add on
rca | Case creation - Create/Edit Analysis | EAPM-4731 | [Improvement][ASM][CMMS] Submit CMMS - Change logic field "Updated Field" | 28 |  |  | 1 | add on | add on
rca | Case creation - Create/Edit Analysis | EAPM-3752 | [Improvement][ASM][AssetStrategy][Revision] disabled icon restore | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3898 | [Improvement][ASM][BE+FE] Abbreviate number when exceeding digit threshold | 28 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis |  | [RCA][createNewAnalysis] Incident Timeline - Export PDF | 28 |  |  | 1 | remove | remove
asm | ai | EAPM-347 | [ASM][AssetStrategy][RisksAndTasks] Risk tap Details - Integrate AI Suggestion | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3411 | [RCA][createNewAnalysis] Finding | 29 |  |  | 1 | baseline | move to 29
rca | Case creation - Create/Edit Analysis | EAPM-3412 | [RCA][createNewAnalysis] Logic Tree | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Logic Tree - Box Details | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4516 | [RCA][createNewAnalysis] Logic Tree - Box Details - Actions | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3413 | [RCA][createNewAnalysis] Verification Action | 29 |  |  | 1 | baseline | bread down 5217, move to sprint 30
rca | Case creation - Create/Edit Analysis | EAPM-4567 | [RCA][createNewAnalysis] Verification Action - Noti | 29 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-3414 | [RCA][createNewAnalysis] RCA Recommendations | 30 |  |  | 1 | baseline | breakdown 5234
rca | Case creation - Create/Edit Analysis | EAPM-3415 | [RCA][createNewAnalysis] Other Recommendations | 30 |  |  | 1 | baseline | breakdown 5235
rca | Case creation - Create/Edit Analysis | EAPM-4568 | [RCA][createNewAnalysis] Reference Document - Table 1 | 30 |  |  | 1 | baseline
rca | Case creation - Create/Edit Analysis | EAPM-4569 | [RCA][createNewAnalysis] Reference Document - Table 2 | 30 |  |  | 1 | baseline | move to backlog
|  | EAPM-5493 | [Improvement][MaintenancePlan][SAP] Integrate S4HANA - (B1) | 30 |  |  | 1 | baseline | add on, no impact
|  | EAPM-5158 | [Improvement][RCA][createNewAnalysis] change source of PTTEP Risk Matrix + Add last updated date | 30 |  |  | 1 | baseline | add on, no impact
|  | EAPM-5241 | [Improvement][RCA][createNewAnalysis] Verification Actions - Table List - allow assigned group email from azure + add column "Last Updated by" | 30 |  |  | 1 | baseline | add on, no impact
|  | EAPM-5397 | [RCA] Sharepoint Structure | 30 |  |  | 1 | baseline | add on, no impact
|  | EAPM-5395 | [Improvement][RCA][createNewAnalysis] add asset when create new RCA + add validate input format "RCA Case Name" | 30 |  |  | 1 | baseline | add on, no impact
|  | EAPM-5434 | [Improvement][RCA][FE][createNewAnalysis] change save button name + change placeholder | 30 |  |  | 1 | baseline | add on, no impact
|  | EAPM-5572 | [ServerError] HTTP Status Error 5xx | 30 |  |  | 1 | baseline | add on, no impact
rca | Case creation - Create/Edit Analysis | EAPM-3406 | [RCA][createNewAnalysis] Executive Summary | 31 |  |  | 1 | baseline | move to sprint 30
rca | case approval | EAPM-5023 | [RCA][Approval Flow] Case Approval - Approval detail + progress - Fa view | 31 |  |  | 1 | baseline | move to sprint 32
rca | case approval | EAPM-5237 | [RCA][Approval Flow] Case Approval - Approval detail + progress - approver view | 31 |  |  | 1 | baseline | move to sprint 32
rca | Case creation - Create/Edit Analysis | EAPM-5812 | [Improvement][RCA][createNewAnalysis] Logic Tree - Main diagram | 31 |  |  | 1 |  | add-on
rca | Case creation - Create/Edit Analysis | EAPM 5848 | [Improvement][RCA][createNewAnalysis] Add validation - Folder Name in Sharepoint | 31 |  |  | 1 |  | add-on
rca | case approval | EAPM 5024 | [RCA][Approval Flow] Case Approval - Approval detail + progress - viewer | 32 |  |  | 1 | baseline
rca | case approval | EAPM 6178 | [RCA][Approval Flow] Case Approval - Approval Progress - Super User view | 32 |  |  | 1 | baseline
rca | case approval | EAPM 5847 | [RCA][Approval Flow] Case Approval - Approval History | 32 |  |  | 1 | baseline
rca | case approval | EAPM 5027 | [RCA][Approval Flow] Case Approval - Noti Email - Inform | 32 |  |  | 1 |  | move to sprint 33
rca | Report | EAPM 5028 | [RCA] Export Report | 32 |  |  | 1 |  | move to sprint 33
rca | case approval | EAPM-5022 | [RCA][Approval Flow] RCA Approval Tracking modal - Structure | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-5026 | [RCA][Approval Flow] Case Status - Permission | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-5059 | [RCA][UserManagement] Master Data Setting "RCA Type" | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-5236 | [RCA][Approval Flow] Submit RCA Case - “Start Investigation” button | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6028 | [RCA][createNewAnalysis] Executive Summary - Design Request/Response JSON for AI | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6231 | [RCA] Add Permission to all pages in RCA | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6367 | [RCA][Approval Flow] Submit RCA Case - Flow Start Investigation | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6368 | [RCA][Approval Flow] Submit RCA Case - Waiting Verification | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6369 | [RCA][Approval Flow] Submit RCA Case - Approve | 32 |  |  | 1 |  | breakdown to srpint 32
rca | case approval | EAPM-6370 | [RCA][Approval Flow] Submit RCA Case - Implementing Action and Complete | 32 |  |  | 1 |  | breakdown to srpint 32
rca | Report | EAPM 5029 | [RCA] Export Report - ppt >> PDF | 33 |  |  | 0 | baseline
rca | RCA Dashboard. | EAPM-3417 | [RCA][createNewAnalysis] Dash Board - Graph | 33 |  |  | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Analysis(All) | 33 |  |  | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Verification (Pending) | 34 |  |  | 0 | baseline
rca | RCA Dashboard. |  | [RCA][createNewAnalysis] Dash Board - Table List - RCA Recommendation (Pending) | 34 |  |  | 0 | baseline
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Azure | 34 |  |  | 0 | baseline | move to sprint 31, breakerdown 5038, 5058
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - Add input setting | 35 |  |  | 0 | baseline | move to sprint 31, breakerdown 5056, 5057, 5036, 5037
rca | User Management |  | [RCA][UserAccount] User Management - Role&Permissions - Approval Flow - display | 35 |  |  | 0 | baseline | move to sprint 31, breakdown 5034, 5035, 5020
rca | Noti Email |  | [RCA] Notification Email - Monthly 16th | 35 |  |  | 0 | baseline
rca | Noti Email |  | [RCA] Notification Email - Monthly 1st | 35 |  |  | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #1 | 36 |  |  | 0 | baseline
ui improvement | Requirement & Design |  | design and feedback loop #2 | 37 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #1 | 38 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #2 | 39 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #3 | 40 |  |  | 0 | baseline
ui improvement | Implementation, Testing, and Deploy |  | implement, deploy, and testing #4 | 41 |  |  | 0 | baseline
handover | Document |  | [Document] system and user manual, sonaqube result | 42 |  |  | 0 | baseline
handover | Knowledge Transfer |  | [KT] knowledge transfer | 43 |  |  | 0 | baseline

## summary
Baseline vs Current Scope (by change type)
Sources:
[9 empty] | Module | Baseline | Added | Split | Moved | Removed
ASM
RCA
UI Improvement
Handover
SAP
Module | Baseline | Current
asm
rca
ui improvement
handover
sap
Sprint by sprint breakdown
SPRINT-BY-SPRINT BREAKDOWN
Sprint | Date Range | ASM | SAP | RCA | UI IMP | HANDOVER | Total
Sprint 18 | 05 Jan 2026 | [6 empty] | Legend:
Sprint 19 | 12 Jan 2026 | [6 empty] | Blue
Sprint 20 | 26 Jan 2026 | [6 empty] | Orange
Sprint 21 | 09 Feb 2026 | [6 empty] | Green
Sprint 22 | 23 Feb 2026 | [6 empty] | Dark Orange
Sprint 23 | 09 Mar 2026 | [6 empty] | Gray
Sprint 24 | 23 Mar 2026
Sprint 25 | 06 Apr 2026
Sprint 26 | 20 Apr 2026
Sprint 27 | 04 May 2026
Sprint 28 | 18 May 2026
Sprint 29 | 01 Jun 2026
Sprint 30 | 15 Jun 2026
Sprint 31 | 29 Jun 2026
Sprint 32 | 13 Jul 2026
Sprint 33 | 27 Jul 2026
Sprint 34 | 10 Aug 2026
Sprint 35 | 24 Aug 2026
Sprint 36 | 07 Sep 2026
Sprint 37 | 21 Sep 2026
Sprint 38 | 05 Oct 2026
Sprint 39 | 19 Oct 2026
Sprint 40 | 02 Nov 2026
Sprint 41 | 16 Nov 2026
Sprint 42 | 30 Nov 2026
Sprint 43 | 14 Dec 2026
TOTAL